# Detailed Meeting Summary

Meeting: Meeting with [C.P.A.]#Collaboration(16 pers.) (1).docx
Date: 19 October 2026

# Meeting Objective

The meeting was conducted to align stakeholders on the vision, architecture, delivery approach, governance model, staffing plan, and implementation roadmap for the MATRIX AI initiative. The discussion also included demonstrations of recent Databricks AI capabilities and how they could influence the future analytical ecosystem across markets. [Meeting wi...pers.) (1) | Word]

# 1. AI Vision and Databricks Demonstration

The discussion started with a review of work completed during a Databricks pilot conducted earlier in the year.

The presenters demonstrated how AI capabilities can significantly accelerate analytical solution development. Examples included:

- Recreating dashboards automatically from uploaded screenshots.

- Generating visualizations through conversational prompts.

- Producing recommendations directly from analytical outputs.

- Enabling users to interact with dashboards through natural language.

- Leveraging Databricks Genie for conversational analytics. [Meeting wi...pers.) (1) | Word]

A key point repeatedly emphasized was that analytics development is changing fundamentally. Historically, dashboard creation required significant manual effort from developers and analysts. The demonstrated AI capabilities suggested that many of these activities could be partially automated in the future. [Meeting wi...pers.) (1) | Word]

Participants discussed how such capabilities could eventually reduce reliance on traditional BI development practices and create opportunities for self-service business intelligence. [Meeting wi...pers.) (1) | Word]

# 2. Assessment of the Existing Mexico Solution

The group explored whether the current Mexico implementation should be migrated directly into Databricks or redesigned.

While participants agreed the current architecture was not originally designed to support AI-driven use cases, it was also recognized that the solution contains substantial business value and already demonstrates a mature KPI structure. [Meeting wi...pers.) (1) | Word]

Key observations included:

- The Mexico data model enabled successful AI experiments despite not being intentionally built for AI.

- Existing KPI definitions provide a good starting point for semantic and AI layers.

- The solution should be treated as a foundation rather than copied unchanged.

- Some business logic remains undocumented and would need formalization. [Meeting wi...pers.) (1) | Word]

The discussion concluded that the future-state platform should evolve the current design rather than simply replicate it. [Meeting wi...pers.) (1) | Word]

# 3. Future AI Agent Ecosystem

A significant portion of the session focused on defining what the future analytical environment should look like beyond traditional dashboards.

Several types of AI agents were proposed:

### KPI Agent

Focused on KPI interpretation, explanations, trends, and business performance questions. [Meeting wi...pers.) (1) | Word]

### Raw Data Agent

Designed to investigate detailed transaction-level questions such as orders, deliveries, or operational records. [Meeting wi...pers.) (1) | Word]

### Knowledge Assistant

Responsible for providing business context, documentation, process knowledge, and guidance. [Meeting wi...pers.) (1) | Word]

### Commercial Agreements Agent

Intended to support customer agreement analysis, contract terms, compliance checks, and customer-specific commercial conditions. Examples involving Walmart agreements were discussed. [Meeting wi...pers.) (1) | Word]

### Enterprise Analytics Agent

Envisioned as an advanced assistant capable of correlating information across:

- Sell-in

- Sell-out

- Inventory

- Promotions

- Market share

- Perfect store metrics

The long-term objective is a connected ecosystem of specialized agents that collaborate to answer business questions. [Meeting wi...pers.) (1) | Word]

# 4. KPI Harmonization and KPI Dictionary

This was one of the most extensive discussion topics.

Participants agreed that KPI definitions currently represent one of the major risks to the program because definitions, formulas, business logic, and technical implementations are not consistently documented across markets. [Meeting wi...pers.) (1) | Word]

The team discussed the need for a formal KPI dictionary containing:

- KPI name

- Business definition

- Calculation methodology

- Technical implementation

- SQL logic

- Business rules and assumptions

- Source systems

The KPI dictionary was viewed as serving multiple purposes:

- Business documentation.

- Development documentation.

- Semantic-layer foundation.

- AI knowledge source.

- Cross-market harmonization mechanism. [Meeting wi...pers.) (1) | Word]

There was agreement that relying on AI alone to reverse-engineer undocumented KPI logic would introduce unacceptable risks. Formal documentation is therefore required. [Meeting wi...pers.) (1) | Word]

# 5. Prototype Strategy

The team agreed that Mexico and Wacam should serve as the initial prototype.

The prototype was expected to validate:

- Architecture decisions.

- Configurability.

- KPI framework.

- Databricks implementation patterns.

- Reusability across markets. [Meeting wi...pers.) (1) | Word]

Participants repeatedly stressed that the objective was not to build a one-off solution but to establish a repeatable onboarding framework for future markets. [Meeting wi...pers.) (1) | Word]

The prototype was identified as the project's critical path because future regional rollouts would depend on its success. [Meeting wi...pers.) (1) | Word]

# 6. Delivery Philosophy: "Pizza Slice" Approach

A delivery model was proposed in which implementation occurs one end-to-end business slice at a time.

Examples of individual slices included:

- Mexico/Wacam business capabilities.

- Brazil rollout.

- Argentina rollout.

- Inventory domain.

- Shipment domain. [Meeting wi...pers.) (1) | Word]

The rationale was that addressing discrete business domains separately would simplify implementation, improve focus, and reduce risk. [Meeting wi...pers.) (1) | Word]

# 7. Separation of Analytical and Operational Capabilities

An architectural debate occurred around whether operational data access should be embedded into KPI-focused analytical solutions.

The consensus was that operational and analytical use cases should remain separate.

Examples discussed:

### Analytical Use Cases

- KPI analysis.

- Trend analysis.

- Root-cause investigations.

- Executive reporting.

### Operational Use Cases

- Individual order tracking.

- Specific delivery inquiries.

- Record-level research.

Participants believed separation would improve maintainability, performance, scalability, and user experience. [Meeting wi...pers.) (1) | Word]

# 8. Market Harmonization Discussion

Several participants discussed the difficulty of achieving global KPI consistency.

Different markets currently operate with:

- Different business processes.

- Different source systems.

- Different reporting logic.

- Different KPI definitions. [Meeting wi...pers.) (1) | Word]

Rather than attempting global harmonization upfront, the agreed sequence was:

- Complete Mexico KPI alignment.

- Complete Wacam KPI alignment.

- Harmonize Mexico and Wacam.

- Expand toward broader global harmonization. [Meeting wi...pers.) (1) | Word]

This approach was considered lower risk and more realistic. [Meeting wi...pers.) (1) | Word]

# 9. Manual Files and Data Inputs

The discussion addressed heavy use of manual files in certain processes.

Concerns raised:

- Different file structures across markets.

- Local workarounds.

- Lack of standardization.

- Operational overhead. [Meeting wi...pers.) (1) | Word]

The target state is a standardized template structure and common ingestion approach that can be reused globally. [Meeting wi...pers.) (1) | Word]

# 10. Brazil Discovery Discussion

Participants discussed the complexity of Brazil and the need for a dedicated discovery effort.

Reasons cited included:

- Existing local solutions.

- Market-specific logic.

- SAP complexity.

- Significant local variations. [Meeting wi...pers.) (1) | Word]

The group agreed that virtual discovery would be insufficient and that in-person workshops would likely be required.

An estimated two-week discovery period in Brazil was discussed. [Meeting wi...pers.) (1) | Word]

# 11. Argentina (SoCo) Discovery Discussion

The team concluded that Argentina should not be grouped with Brazil for discovery purposes.

The rationale was that:

- The business context differs.

- The solutions differ.

- The complexity profile differs.

- Independent assessment would lead to better outcomes. [Meeting wi...pers.) (1) | Word]

# 12. Inventory and Shipment Streams

Participants reviewed organizational structures around Inventory and Shipment domains.

The prevailing view was that both areas have strong dependencies and should therefore be managed together as a single delivery stream wherever practical. [Meeting wi...pers.) (1) | Word]

# 13. Governance, Quality and Engineering Standards

The discussion touched on governance requirements for large-scale implementation.

Topics raised included:

- Metric-view governance.

- Dashboard governance.

- Data quality controls.

- Observability.

- Cost monitoring.

- Development standards.

- Architecture consistency. [Meeting wi...pers.) (1) | Word]

Regular engineering reviews and quality controls were identified as necessary throughout implementation. [Meeting wi...pers.) (1) | Word]

# 14. Resource Planning and Staffing

A substantial discussion took place regarding staffing.

Concerns included:

- Resource availability.

- Existing project commitments.

- Need for experienced personnel.

- Critical-path dependency on specific individuals. [Meeting wi...pers.) (1) | Word]

The leadership team was asked to identify:

- Prototype team members.

- Key technical architects.

- Primary delivery leads.

- Regional discovery resources. [Meeting wi...pers.) (1) | Word]

Mariusz Małkowicz</Project Person> was repeatedly referenced regarding staffing, prioritization, and resource planning discussions. [Meeting wi...pers.) (1) | Word]

# Delivery Roadmap Discussed

| Period | Target Outcome |
| --- | --- |
| January | Prototype team and environment readiness |
| February-March | Architecture finalization and implementation |
| April | System testing |
| May-June | Business testing and validation |
| July-August | Integration Testing and UAT |
| September | Production readiness |
| October | Go-Live target |

[Meeting wi...pers.) (1) | Word]

# Decisions

- MATRIX AI will be delivered as a new AI-first platform rather than a migration project. [Meeting wi...pers.) (1) | Word]

- Mexico and Wacam will serve as the prototype foundation. [Meeting wi...pers.) (1) | Word]

- Delivery will follow a pizza-slice implementation model. [Meeting wi...pers.) (1) | Word]

- Analytical and operational AI capabilities will remain separate. [Meeting wi...pers.) (1) | Word]

- Mexico and Wacam KPIs must be harmonized before global rollout. [Meeting wi...pers.) (1) | Word]

- Manual file structures should be standardized. [Meeting wi...pers.) (1) | Word]

- Brazil requires on-site discovery activities. [Meeting wi...pers.) (1) | Word]

- Argentina discovery should be separate from Brazil. [Meeting wi...pers.) (1) | Word]

- Inventory and Shipment should be treated as a combined stream. [Meeting wi...pers.) (1) | Word]

- AI readiness is a mandatory design principle. [Meeting wi...pers.) (1) | Word]

# Action Items

- Mariusz Małkowicz and leadership to define the prototype team structure. [Meeting wi...pers.) (1) | Word]

- Identify and secure critical-path resources. [Meeting wi...pers.) (1) | Word]

- Build a consolidated KPI inventory for Mexico and Wacam. [Meeting wi...pers.) (1) | Word]

- Document KPI definitions, formulas, and technical logic. [Meeting wi...pers.) (1) | Word]

- Harmonize Mexico and Wacam KPI frameworks. [Meeting wi...pers.) (1) | Word]

- Create the KPI dictionary structure. [Meeting wi...pers.) (1) | Word]

- Develop the configurable architecture framework. [Meeting wi...pers.) (1) | Word]

- Plan and execute Brazil discovery workshops. [Meeting wi...pers.) (1) | Word]

- Reverse-engineer Brazil and Argentina solutions. [Meeting wi...pers.) (1) | Word]

- Define governance for metric views and dashboards. [Meeting wi...pers.) (1) | Word]

- Establish observability, monitoring, and cost-management controls. [Meeting wi...pers.) (1) | Word]

- Define migration approach from GCP to Databricks. [Meeting wi...pers.) (1) | Word]

# Key Risks

- Incomplete KPI documentation.

- Resource availability constraints.

- Cross-market KPI harmonization complexity.

- Unclear migration ownership.

- Dependencies on platform and domain teams.

- Organizational adoption of AI-driven ways of working. [Meeting wi...pers.) (1) | Word]