# Day 4 Workshop Summary (22 Oct 2026)

Workshop Focus: Assumptions Review, Timeline Validation, Dependency Management, Scope Freeze Approach, Requirements Governance, Benchmarking Strategy, Resource Mobilization, Travel Planning, Architecture Alignment, and Project Management Framework. [Assumption...ine review | Word]

# Executive Summary

Day 4 focused on validating the project assumptions, reviewing the detailed timeline, and establishing how the team will handle uncertainty, particularly around dependencies, requirements maturity, architecture decisions, and onboarding of Brazil and SoCo (Argentina).

A major theme throughout the session was balancing two competing objectives:

- Moving fast enough to demonstrate a configurable solution by January-February.

- Avoiding project paralysis while waiting for perfect requirements, finalized core domains, or fully provisioned target environments.

The workshop resulted in agreement that the project must continue progressing even when information is incomplete. The team aligned on a governance-driven approach where assumptions, dependencies, and unresolved requirements are documented, tracked, and progressively resolved rather than treated as blockers. [Assumption...ine review | Word]

# 1. Dependency Management Philosophy

One of the earliest discussions challenged how dependencies were documented.

The delivery team initially presented several items as prerequisites for starting work, including:

- Core domain readiness

- Data product readiness

- Access to source applications

- Architecture decisions

- Databricks migration readiness

MDLZ Team (Marcelo) pushed back on describing these elements as "prerequisites" or "blocking dependencies." His view was that waiting for all prerequisites to be completed would significantly delay delivery. [Assumption...ine review | Word]

### Agreed Direction

Dependencies should be treated as:

- Constraints

- Inputs

- Decisions requiring monitoring

Rather than:

- Stop conditions

- Project blockers

The expectation is that teams continue with:

- Discovery

- Reverse engineering

- Design

- Architecture preparation

- KPI harmonization

even if dependent teams are not fully ready. [Assumption...ine review | Word]

# 2. Core Domain and Data Product Alignment

A substantial conversation focused on Core Domains.

Concerns raised:

- Core domain designs may continue to evolve.

- Product organizations are undergoing reorganization.

- Some teams have competing priorities.

- Existing roadmaps may not align with MATRIX AI timelines. [Assumption...ine review | Word]

### Decision

The project will use a "snapshot" approach.

The team agreed to establish a reference state as of approximately 2 November and proceed using that version of architecture and domain understanding.

Subsequent changes will be managed through governance rather than repeatedly re-planning the entire project. [Assumption...ine review | Word]

### Action

The team will organize follow-up sessions with Core Domain teams to:

- Review domain designs.

- Understand current maturity.

- Socialize architecture direction.

- Identify fit-gap areas. [Assumption...ine review | Word]

# 3. Requirement Sign-Off Strategy

One of the most important discussions focused on requirement finalization.

The original proposal suggested workshops would result in signed-off requirements very early in the process.

Several concerns were raised:

- Brazil requirements are not fully known.

- SoCo requirements are not fully known.

- Legacy solutions contain undocumented logic.

- Significant reverse engineering remains necessary. [Assumption...ine review | Word]

### MDLZ Team (Marcelo)'s Position

Requirements should not delay delivery.

If only partial understanding exists:

- Deliver what is known.

- Build configurable structures.

- Refine business logic later. [Assumption...ine review | Word]

Examples discussed:

- Revenue formulas

- KPI calculations

- Country-specific logic

The expectation is that some KPI logic will inevitably change during testing.

This is considered normal and already accounted for in the schedule. [Assumption...ine review | Word]

# 4. Scope Freeze and Hard Stop Definition

A major alignment point concerned requirement growth.

### Initial Concern

Without a formal stop point:

- New requirements could continue indefinitely.

- New country specifics could appear during implementation.

- Testing and deployment timelines would be threatened. [Assumption...ine review | Word]

### Final Agreement

End of March becomes the primary governance checkpoint.

By then:

- Core KPI logic should be understood.

- Country-specific features should be identified.

- Major requirements should be documented.

- Feature inventory should be substantially complete. [Assumption...ine review | Word]

After March:

- New requests may still appear.

- Each request will be evaluated individually.

- Large changes require governance review.

- Not all requests will automatically be accepted. [Assumption...ine review | Word]

# 5. Prototype Versus Full Product

A detailed discussion clarified expectations regarding January-February deliverables.

There were differing interpretations regarding whether the project should deliver:

- Fully completed country solutions.

- Or proof that the configurable framework works.

### Final Alignment

The January-February milestone should demonstrate:

- Configurable architecture.

- Country parameterization.

- KPI configuration capability.

- Reusable framework design.

The expectation is not that every Brazil or SoCo customization is fully implemented by that point. [Assumption...ine review | Word]

# 6. Local Features Versus Global Features

A lengthy debate focused on country-specific functionality.

Examples discussed:

- Brazil-specific document structures.

- Historical master-data handling.

- Local pricing processes.

- Price Value Chain functionality.

- Country-specific sales processes. [Assumption...ine review | Word]

### Different Perspectives

#### Delivery Team Concern

Too many local features could create:

- Architectural complexity.

- Unused global components.

- Increased maintenance effort.

#### MDLZ Team (Marcelo)'s Perspective

Local innovations should not automatically remain local.

A capability developed in one country might become valuable elsewhere in the future.

Examples mentioned:

- Europe potentially reusing Brazil capabilities.

- Other markets potentially leveraging Price Value Chain logic. [Assumption...ine review | Word]

### Decision

The platform should behave like a configurable service catalog:

- Global by default.

- Configurable when needed.

- Local capabilities can be promoted to global reusable features. [Assumption...ine review | Word]

# 7. Architecture and Databricks Dependencies

The workshop reviewed architecture assumptions.

Questions covered:

- Databricks readiness

- AWS migration timing

- Repository setup

- CI/CD alignment

- Environment provisioning

- Federated integrations [Assumption...ine review | Word]

### Key Alignment

The team will:

- Continue building using currently available environments.

- Use existing GCP setup where required.

- Migrate later according to platform timelines.

- Avoid treating environment readiness as a project blocker. [Assumption...ine review | Word]

### March Reference Point

Repeatedly throughout the workshop, participants aligned around March as the target date for:

- Migration readiness.

- Repository alignment.

- Architecture confirmation.

- AWS/Databricks decisions. [Assumption...ine review | Word]

# 8. Architecture Review with Data Engineering

Specific attention was given to technical architecture validation.

### Decision

An architecture workshop will be organized with:

- Krzysztof

- Data Engineering leadership

- Relevant architecture stakeholders

Purpose:

- Clarify target architecture.

- Validate assumptions.

- Review Databricks direction.

- Resolve open technical questions before development scales. [Assumption...ine review | Word]

The team agreed this session should occur during the following week and serve as the authoritative alignment point for technical design. [Assumption...ine review | Word]

# 9. Benchmarking and Testing Strategy

A substantial portion of the session focused on benchmarking.

### Core Principle

Every stream should have a reference point wherever possible.

Examples include:

- Existing systems

- Legacy reports

- Local dashboards

- Source applications

- Existing market reporting solutions [Assumption...ine review | Word]

### Challenge Areas

For some domains:

- No benchmark currently exists.

- No consolidated reporting exists.

- Reference systems are difficult to access. [Assumption...ine review | Word]

Examples discussed:

#### Perfect Store

- Local dashboards exist.

- Different business units use different tools.

- MC1 solutions may need to be used as benchmarks.

#### Market Share

- Raw source files available.

- Existing reporting less standardized.

#### Shipments

- Local reporting exists but requires inventorying. [Assumption...ine review | Word]

# 10. Data Validation Philosophy

The group discussed what should happen when new calculations differ from current reports.

### Concern

During previous implementations:

- New calculations exposed defects in existing business logic.

- Reported numbers changed.

- Business users challenged the outputs. [Assumption...ine review | Word]

### Agreed Approach

Current solutions become the baseline benchmark.

However:

- Existing logic may be incorrect.

- Differences should trigger investigation.

- Valid improvements should not be rejected simply because they differ from historical reports. [Assumption...ine review | Word]

The workshop recognized that business-rule refinement will continue through testing and stabilization. [Assumption...ine review | Word]

# 11. Governance After Go-Live

A future-state governance model was discussed.

Participants emphasized that once KPIs move into a governed Databricks environment:

- KPI logic changes cannot happen informally.

- Business users cannot directly alter calculations.

- Changes must follow governance processes.

- Ownership and approval workflows must exist. [Assumption...ine review | Word]

The discussion positioned this as a significant operational improvement over many existing local processes. [Assumption...ine review | Word]

# 12. Resource Mobilization

The team reviewed the initial delivery staffing model.

Proposed resources include:

### Discovery Team

- Business Analysts

- Senior Lead Analysts

### Architecture Team

- Data Architects

- Technical Architects

### Engineering Team

- Data Engineers

- Front-End Engineers

### Program Support

- Project Management

- Training and Adoption resources [Assumption...ine review | Word]

Parallel discovery activities are planned for:

- Brazil

- Argentina / SoCo

with multiple workshop tracks running simultaneously. [Assumption...ine review | Word]

# 13. Training and Change Management

Training was identified as a missing component in the draft plans.

The team agreed the project requires:

- Adoption planning

- User training

- Training materials

- Knowledge-transfer support

- Databricks learning support

- Change management activities [Assumption...ine review | Word]

The intention is to leverage:

- Existing Databricks Academy content

- Internal enablement materials

- Dedicated adoption specialists where possible. [Assumption...ine review | Word]

# 14. Travel and Workshop Planning

Travel planning became a priority topic.

### Key Points

The team plans to:

- Conduct Brazil workshops on-site.

- Run Argentina workshops in parallel.

- Begin travel planning immediately. [Assumption...ine review | Word]

### Concern Raised

Airfare, availability, and regional events could impact scheduling.

### Agreement

Resource names should be finalized immediately so travel bookings can begin without delay. [Assumption...ine review | Word]

# 15. Governance and Operating Model

The team agreed that governance structure must be finalized before kickoff.

Topics discussed:

- Meeting cadence

- Steering structures

- Working groups

- Stakeholder participation

- Decision-making process

- Escalation paths

- Standard templates and reporting mechanisms [Assumption...ine review | Word]

The goal is to establish governance from Day 1 rather than introducing controls later in the project. [Assumption...ine review | Word]

# 16. Project Management Framework

Toward the end of the session, MDLZ Team (Marcelo) presented examples of project-management artifacts and recommended creating a highly structured execution model. [Assumption...ine review | Word]

The proposed framework includes:

### Activity Management

For each activity:

- Inputs

- Outputs

- Supplier

- Consumer

- Exit criteria

- Dependencies

- Definition of Done

### Quality Controls

For each control:

- Description

- Measurement approach

- Examples

- Applicable processes

- Success criteria

### Documentation Standards

Standardized definitions to reduce interpretation differences across:

- Poland

- India

- Philippines

- LATAM teams [Assumption...ine review | Word]

A major concern was ensuring that a 30+ person global delivery team interprets requirements consistently. [Assumption...ine review | Word]

# Key Decisions

- Dependencies will be tracked as constraints and assumptions rather than project blockers. [Assumption...ine review | Word]

- A snapshot of architecture and domain readiness around 2 November will be used as the baseline for planning. [Assumption...ine review | Word]

- End of March becomes the primary requirement and scope-governance checkpoint. [Assumption...ine review | Word]

- January-February milestones focus on proving configurability rather than delivering all regional customizations. [Assumption...ine review | Word]

- Local capabilities may be promoted into reusable global platform features. [Assumption...ine review | Word]

- Development will continue using current environments while migration activities progress separately. [Assumption...ine review | Word]

- Benchmarking should leverage existing local reporting where available. [Assumption...ine review | Word]

- KPI and business-rule governance will be required after go-live. [Assumption...ine review | Word]

- Training and adoption activities must be included in the delivery plan. [Assumption...ine review | Word]

# Action Items

| Action | Owner |
| --- | --- |
| Organize architecture alignment workshop with Krzysztof and Data Engineering stakeholders | Architecture Team |
| Replace November dependency deadlines with March governance checkpoints where appropriate | Planning Team |
| Update assumptions and dependency register based on workshop decisions | Vadzim Nazarau / Planning Team |
| Schedule Core Domain alignment sessions | Project Leadership |
| Define benchmark sources for each workstream | Functional & Technical Leads |
| Finalize resource nominations and workshop assignments | Lingaro Leadership |
| Finalize Brazil and Argentina travel plans | PMO / Workstream Leads |
| Update timeline and Gantt plan reflecting scope-freeze decisions | Planning Team |
| Define governance meetings, templates and reporting standards | PMO & Leadership |
| Incorporate training, adoption and change management workstreams into the project plan | Program Management Team |
| Prepare detailed project execution framework including Definition of Done, suppliers, consumers and quality gates | Delivery Leadership |
| Share final staffing proposal and travel assignments | Resource Management Team |

[Assumption...ine review | Word]

# Main Outcome

The workshop successfully transformed several rigid assumptions into a more pragmatic execution model. Rather than waiting for complete requirements, finalized architectures, or fully mature dependencies, the team agreed to proceed with a configurable solution framework, govern uncertainty formally, establish March as the primary alignment checkpoint, and focus on demonstrating a working scalable architecture as early as January-February. [Assumption...ine review | Word]