## Slide 1: Weekly Status Update date

## Slide 2
AGENDA – 90 MINUTES MEETING
Section | Produced by | Content | Time
Bravos / High fives | Project Lead | Named recognition with the standard legend: above & beyond · outstanding performance · innovation · milestone win · precision · teamwork · delivery success. Keep it — it is the only page in the pack that builds the team. | 15 min
High Risks | PMO with risk owners | Risk # · Title · Score (movement, e.g. VH → H) · Status with dated update · Owner · Due · Impact on which workstream. Closed risks struck through and kept visible for one week. | 
Change / Decision Log | PMO with change owners | DEC or CHG · ID · Title · Description · Owner · Confirmed on · Workstream · Category (tier) · Dated status. Every decision taken anywhere in the governance model lands here. | 
High-Level Timeline | PMO | Gantt by sub-wave in weekly buckets, with phase colors, tollgates, and the three May 2027 go-lives marked. Status per objective: Complete / On track / Off track / Blocked / Not started. | 
Program Status Report — Overall | Project Lead | Executive summary page. Status headline (% completion, movement week on week, overall RAG and the one reason for it) · milestone status table by sub-wave with estimated end, % complete with movement, RAG and a summary line · Very High and High risks repeated. This is the page that gets forwarded. | 10 min
Workstream 4-box | Sub-wave leads | Workstream detailed update … total of updates = 11 | 5 min each 55 min total
Q&A | Project Lead | Open for Q&A session | 10 min

## Slide 3
BRAVOS
Free text

## Slide 4
HIGH RISKS / Dependencies
ID Number | Risk description and impact assessment | Mitigation / Resolution update | Workstreams impacted | Status | Owner | Due
R01 | Project documentation creation disabled - until MDLZ sets up the project GitHub repository and gives the Lingaro team access. Impact: HLD/TDD, living playbooks and CDRB evidence package delayed. | Repository and access requested from MDLZ. Until then documentation is drafted in Lingaro workspace and moved to GitHub as soon as access is granted. | All workstreams | A | Ana Sola/Vadzim Nazarau | Nov 4th
R02 | To work in compliance with MONDELEZ POET, the Lingaro team needs the current version of the POET documentation and related materials. Impact: deliverables and ways of working may need rework if not aligned with POET. | Current POET documentation and templates requested from MDLZ PMO. Lingaro to align WoW, templates and tollgate evidence within 1 week of receipt. | All workstreams | A | Vadzim N. / MDLZ PMO | Nov 13th
R03 | Databricks cost monitoring and the related MDLZ information cannot be set up until Lingaro gets access to MDLZ Databricks cost monitoring. Impact: no cost baseline from prototype phase; cost monitoring deliverable delayed. | Access requested. Cost tags and cost-monitoring design prepared in parallel, so tracking starts as soon as access is granted. | All workstreams (cross-stream) | A | Vadzim N. / MDLZ Platform | Nov 20th
R04 | Names of the governance SPOCs (D&A Data Product & Engineering, D&A Architects, Product Stream teams, Data Governance) not yet provided. Impact: Lingaro cannot align development approach, WoW and design decisions with the governance bodies. | MDLZ to share the SPOC list. Lingaro to set up intro and alignment sessions with each body within 1 week of nomination. | All workstreams | A | Vadzim N. / MDLZ PM | Nov 13th
R05 | Project timeline needs to be replanned: business availability changed and planned travel moved from Nov 9th to beginning of December. Impact: requirements sign-off (planned Nov 30th) and prototype milestones (Jan 31st / Feb 28th) at risk. | Revised timeline being prepared with the new workshop dates. Preparation brought forward (reverse engineering, elicitation plan) and remote sessions held in November. Revised plan to be presented for approval. | 1, 2, 3, 5, 6 (workshop-dependent) | R | Vadzim N. | Nov 13th
R06 | Project timeline at risk because remote meetings with business are less effective than onsite workshops (shorter slots, slower decisions, lower engagement). Impact: slower requirements elicitation and sign-off. | Structured agendas and pre-reads sent in advance; decisions logged in Jira and the decision log; sign-off progress tracked weekly; escalation to project leadership if sign-offs slip. | 1, 2, 3, 5, 6 (workshop-dependent) | A | Vadzim N. / MDLZ Biz leads | Ongoing – weekly

## Slide 5
CHANGE / DECISION LOG
Change Number | Change Title | Change Description / Impact | Decision made | Workstreams impacted | Owner | Due | Status
CHG-01 | Timeline replan – workshop dates | Business availability moved onsite workshops from Nov 9th to beginning of December. Impact on requirements sign-off and prototype milestones (see R05). | Pending – revised timeline and development plan to be reviewed | 1, 2, 3, 5, 6 | Vadzim N. | Nov 9th | Pending

## Slide 6: Executive timeline (Plan in a Page)
Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Integration Testing
(~75 per BU / Function)
Biz Impact
Training design & Build
Training
Sign-off
Train-Trainers
UAT
(~200 per BU / Function)
Go
Live
HYPERCARE
ADOPTION
SUSTAIN
1. OTC / EPOS / Master Data
Production Readiness
Full Setup
Interactive final build and improvements , defects fixes, monitoring, quality improvements, changes, cost monitoring, jobs scheduling, data governance, refresh validation, consumption layers, KPIs logics fine tuning, scalability / reusability confirmation, Global rollout playbook
2. MDLZ INVENTORY & SHIPMENT
3. MARKET MEASUREMENT AND PROMOTIONS
4. MEXICO DSD
PROTOP. TESTING
5. BRAZIL PVC / VR / EASTER
6. STORE OPERATIONS (PERFECT & RIGHT STORE)
7. SNACKSYNC
FULL CODE MIGRATION
TO DATABRICKS
AWS
PROJECT
UNIT TESTING
DBX-AWS DEV
KEY USER TESTING IN
DBX-AWS DEV
(~20 PER BU/FUNCTION)
WE ARE HERE!
Phase 01 – Blueprint & Build into Databricks-GCP Dev
Phase 02
Migration
DBX– AWS
Dev
Phase 03 – Testing & Improvements into
DBX–AWS Dev
Phase 03 – Acceptance into
DBX–AWS QA
Phase 04 – Production
DBX–AWS Prod
Phase 05 – Hypercare
DBX–AWS Prod
Business Commitment 20%-35%
Business Commitment 30%-40%

## Slide 7
PROGRAM STATUS REPORT – EXECUTIVE UPDATE
A | A |  | G | A | G | A | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
EXECUTIVE STATUS HEADLINE
Program kicked off: delivery team onboarded and assigned to all 7 workstreams; preparation underway (Accesses to ). Development that does not depend on workshops starts Nov 9th. Onsite workshops moved from Nov 9th to beginning of December due to business availability – timeline replan required (R05, R06). Help needed from MDLZ: GitHub repository and access (R01), POET documentation (R02), Databricks cost-monitoring access (R03), governance SPOC names (R04).
Date | Nov 4TH, 2026
Workstreams | Phase | Status | Status Summary | Risk / Mitigation update
1. OTC / EPOS / Master Data | Blueprint / Prototype build | A | Team onboarding in progress. Mondelez accesses provision – in progress. WC & MX: Core domain lift and shift to DBX on GCP planned – pending accesses. BR & SC: reverse engineering of existing Sell-In/Sell-Out planned – pending accesses. Onsite workshops Brazil moved to beginning of December. Onsite workshops Argentina planned – pending accesses to start reverse engineering. | R05, R06: timeline replan in progress; remote business sessions in November.
2. MDLZ INVENTORY & SHIPMENT | Blueprint / Prototype build | A | Team onboarding in progress. Mondelez accesses provision – in progress. Combined Brazil workshop (+WC, MX, SC) to be rescheduled. | R05: workshop date to be confirmed in revised plan.
3. MARKET MEASUREMENT AND PROMOTIONS | Blueprint / Prototype build | A | Team onboarding in progress. Mondelez accesses provision – in progress. Market Share & Promotions discovery for MX starts Nov 9th; KPI inventory across LA. Combined Brazil workshop to be rescheduled. | R05, R06: remote sessions with Market Share leads until onsite workshop.
4. MEXICO DSD | Blueprint / Prototype build | G | Team onboarding in progress. Mondelez accesses provision – in progress. Migration from existing GCP solution: federated integration, mapping to core domains and KPI inventory start planned Nov 7th – Pending accesses. | R04: DP&E SPOC needed for core-domain fit/gap.
5. BRAZIL PVC / VR / EASTER | Blueprint / Prototype build | A | Team onboarding in progress. Mondelez accesses provision – in progress. Reverse engineering of existing Brazil PVC/VR/Easter pipelines, stored procedures and DAX logic planned – accesses to solutions pending. Brazil workshop moved to beginning of December | R05, R06: reverse engineering continues remotely; questions list prepared for workshop.
6. STORE OPERATIONS (PERFECT & RIGHT STORE) | Blueprint / Prototype build | A | Team onboarding in progress. Mondelez accesses provision – in progress. Perfect Store analysis (LA) and Right Store MX DSD mockup planned. MDLZ accesses pending. Brazil workshop (+WC, MX, SC) moved to beginning of December. | R05: source access for Perfect/Right Store to be confirmed.
7. SNACKSYNC | Blueprint / Prototype build | G | Team onboarding in progress. Mondelez accesses provision – in progress. SnackSync assessment (data quality, completeness, schema) planned once SnackSync DB for analytics planned for start – Late November. | 
EXECUTIVE STATUS HEADLINE
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 8
1. OTC / EPOS / Master Data
A | A |  | G | A | G | A | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Nov 4th, 2026
Key Accomplishments
✓ Delivery team established; DE members assigned to OTC, EPOS and Master Data ✓ MDLZ accounts requested; team onboarding started ✓ Internal kick-off held: scope, timeline, ways of working ✓ Preparation started: capture of existing Brazil & Southern Cone code (reverse engineering – access pending) ✓ Requirements elicitation plan draft – planned.
Data Engineering Lead | Małgorzata Mańka/Michał Herman
Gen BI Lead | TBD
Type | Number | Description / Mitigation | Status | Owner | Due
Risk | R05 | Travel moved to early Dec – revised plan; remote sessions in Nov | R | Vadzim N. | Nov 13th
Risk | R06 | Remote sessions less effective – pre-reads, weekly sign-off tracking | A | Vadzim N. | Weekly
Risk | R04 | Governance SPOCs not named – DP&E core-domain alignment | A | MDLZ PM | Nov 13th
Act. | A01 | Confirm new Brazil & Argentina travel dates and participants | A | Vadzim N. | Nov 13th
Act. | A02 | Complete MDLZ accounts setup and team onboarding | A | MDLZ / Lingaro | Nov 9th
Key upcoming activities & decisions
WC & MX (1a): ▪ Sell-In report assessment & preselection: Nov 4th (dependency on resources – OSA MX, Wacam PODs) ▪ Sell-Out report assessment: Nov 4th (dependency on resources – OSA MX, Wacam PODs) BR & SC (1b): ▪ Reverse engineering of Sell-In / Sell-Out logic (Nov 4th – 18th). Dependency accesses provision. ▪ Remote business sessions in November; onsite workshops Brazil & Argentina – beginning of December
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Working prototype: WC & MX by Jan, BR & SC by Feb | A | Jan 31st / Feb 28th
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Lead | TBD (SPOC to be nominated)
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 9
2. MDLZ INVENTORY & SHIPMENT
A | G |  | G | A | G | A | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Nov 4th, 2026
Key Accomplishments
✓ DE members assigned to MDLZ Inventory & Shipments ✓ MDLZ accounts requested; team onboarding started ✓ Scope confirmed: internal stock snapshots (warehouse, plant) and shipments from OTM and SAP TM ✓ Workstream plan aligned with executive timeline (build Nov–Feb, testing in March)
Data Engineering Lead | Tomasz Skowroński/ Marek Kaczor
Gen BI Lead | TBD
Type | Number | Description / Mitigation | Status | Owner | Due
Dep. | D01 | Shipments core domain from DP&E needed by Nov 16th | A | MDLZ DP&E | Nov 16th
Risk | R05 | Nov 23rd workshop to be rescheduled in revised plan | R | Vadzim N. | Nov 13th
Risk | R04 | Governance SPOCs not named – core-domain alignment | A | MDLZ PM | Nov 13th
Risk | R01 | GitHub repository & access needed for documentation | A | MDLZ D&A | Nov 13th
Key upcoming activities & decisions
Activities planned after access provision: ▪ Federated integration GCP Harmonized → Databricks GCP ▪ Harmonize manual files into single entities before core domains ▪ Parameterized mapping layer to agnostic core-domain entities ▪ KPI inventory and harmonization across LA with Global D&A inventory ▪ Combined Brazil workshop (+WC, MX, SC) – new date in revised plan
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Feb 28th
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Lead | TBD (SPOC to be nominated)
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 10
3. MARKET MEASUREMENT AND PROMOTIONS
A | A |  | G | A | G | A | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Nov 4th, 2026
Key Accomplishments
✓ DE members assigned to Market Measurement & Promotions ✓ MDLZ accounts requested; team onboarding started ✓ MDLZ Market Share leads identified (Fabio A., Marvi M., Maria B., Gustavo P.) ✓ Scope confirmed: market share data & calculations (all 4 BUs); promotions (MX model exists, new for others)
Data Engineering Lead | Paweł Orzech/Przemysław Dzierżak
Gen BI Lead | TBD
Type | Number | Description / Mitigation | Status | Owner | Due
Dep. | D02 | Market share source access (planned Nov 1st) to confirm | A | MDLZ D&A | Nov 13th
Risk | R05 | Nov 23rd workshop to be rescheduled in revised plan | R | Vadzim N. | Nov 13th
Risk | R06 | Remote sessions less effective – pre-reads, weekly sign-off tracking | A | Vadzim N. | Weekly
Risk | R04 | Governance SPOCs not named | A | MDLZ PM | Nov 13th
Key upcoming activities & decisions
Activities planned after access provisioning. ▪ Market Share & Promotions discovery for Mexico ▪ Ingest FMT datasets with validated schemas, volumetrics and DQ controls ▪ Onboard Market Measurement & Promo sources into GCP Harmonized; metadata in Unity Catalog ▪ Remote sessions with Market Share leads; combined Brazil workshop – new date in revised plan
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Feb 28th
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Lead | Fabio A., Marvi M., Maria B., Gustavo P.
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 11
4. MEXICO DSD
G | G |  | G | G | G | A | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Nov 4th, 2026
Key Accomplishments
✓ DE and BI members assigned to Mexico DSD ✓ MDLZ accounts requested; team onboarding started ✓ Existing Mexico DSD solution on GCP confirmed as migration baseline (incl. suggested replenishment)
Gen BI Lead | Harish Ravi
Type | Number | Description / Mitigation | Status | Owner | Due
Risk | R04 | Governance SPOCs not named – DP&E fit/gap on hold | A | MDLZ PM | Nov 13th
Risk | R01 | GitHub repository & access needed for documentation | A | MDLZ D&A | Nov 13th
Risk | R03 | Cost-monitoring access needed for cost baseline | A | MDLZ Platform | Nov 20th
Key upcoming activities & decisions
Activities planned after Access provisioning: ▪ Federated integration GCP Harmonized → Databricks GCP ▪ Fit/gap analysis against agnostic core domain with DP&E ▪ KPI inventory and harmonization for Mexico DSD ▪ Right Store MX DSD mockup and redesign
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Feb 28th
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Lead | TBD (SPOC to be nominated)
Data Engineering Lead | Marcin Kostkiewicz/ Przemysław Dzierżak
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 12
5. BRAZIL PVC / VR / EASTER
A | A |  | G | A | G | A | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Nov 4th, 2026
Key Accomplishments
✓ DE members assigned to Brazil PVC / VR / Easter ✓ MDLZ accounts requested; team onboarding started ✓ Reverse engineering planned – pending accesses to Brazil PVC/PV/EASTER solutions: existing Brazil PVC, VR and Easter GCP pipelines, stored procedures and DAX logic
Data Engineering Lead | Przemysław Trzaska/Marek Kaczor
Gen BI Lead | TBD
Type | Number | Description / Mitigation | Status | Owner | Due
Risk | R05 | Brazil workshop moved to early Dec – sign-off at risk | R | Vadzim N. | Nov 13th
Risk | R06 | Remote sessions less effective – question list & pre-reads | A | Vadzim N. | Weekly
Act. | A03 | Share reverse-engineering findings & open questions | G | DE Lead | Nov 27th
Key upcoming activities & decisions
Actions planned after access provisioning: ▪ Document calculation flows, business rules and exception handling ▪ Extract GCP production reconciliation baselines ▪ Map legacy logic to the 8-block architecture and KPI engine design ▪ Formalize undocumented rules and workarounds into config objects ▪ Remote sessions with Brazil business in November; onsite workshop – beginning of December
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | A | Feb 28th
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Lead | TBD (SPOC to be nominated)
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 13
6. STORE OPERATIONS (PERFECT & RIGHT STORE)
A | A |  | G | A | G | A | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Nov 4th, 2026
Key Accomplishments
✓ DE and BI members assigned to Store Operations (Perfect & Right Store) ✓ MDLZ accounts requested; team onboarding started ✓ Scope confirmed: all applications for Perfect and Right Store across 4 BUs
Data Engineering Lead | Marcin Kostkiewicz/ Przemysław Dzierżak
Gen BI Lead | Harish Ravi
Type | Number | Description / Mitigation | Status | Owner | Due
Dep. | D03 | Perfect / Right Store source access to confirm | A | MDLZ D&A | Nov 13th
Risk | R05 | Workshop moved to early Dec – timeline replan | R | Vadzim N. | Nov 13th
Risk | R06 | Remote sessions less effective – pre-reads, weekly sign-off tracking | A | Vadzim N. | Weekly
Key upcoming activities & decisions
▪ Perfect Store analysis for LA planned start Nov 4th ▪ Right Store MX DSD mockup review and redesign ▪ Store Ops ingestion analysis prep (for probable MC-1 Business trip)
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Feb 28th
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Lead | TBD (SPOC to be nominated)
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 14
7. SNACKSYNC
G | G |  | G | G | G | A | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Nov 4th, 2026
Key Accomplishments
✓ DE and BI members not yet assigned to SnackSync (pending new team members interviews finalization)
Data Engineering Lead | TBD
Gen BI Lead | TBD
Type | Number | Description / Mitigation | Status | Owner | Due
Dep. | D04 | SnackSync DB for analytics needed by Nov 16th | A | MDLZ D&A | Nov 16th
Risk | R04 | Governance SPOCs not named | A | MDLZ PM | Nov 13th
Risk | R01 | GitHub repository & access needed for documentation | A | MDLZ D&A | Nov 13th
Key upcoming activities & decisions
Activities to be done after team assignment to Snacksync stream: ▪ Assess SnackSync data quality, completeness and schema consistency ▪ Document SnackSync logic, refresh cadence and known gaps ▪ Federated integration from SnackSync into Databricks Harmonized Layer ▪ Fit/gap of SnackSync data against EPOS and Store Ops core domains
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Feb 28th
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Lead | TBD (SPOC to be nominated)
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 15: Q&A

## Slide 16: 1. PROTOTYPE OTC / EPOS
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25
. Inventory and harmonize KPI definitions across Wacam & Mexico with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
AI / BI, Genie Agent, Knowledge, Orchestration
BR & SC
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
. Establish federated integration from GCP Harmonized Layer into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for WC & MX
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
SonarQube and AI audit review
. AI/BI dashboard prototypes per persona for MX & WC
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
. Inventory and harmonize KPI definitions across Brazil & S. Cone with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Onboard BR & SC onto KPI engine proven with WC & MX, config-only, zero code changes
. Market-specific rules (currency, UOMs, hierarchies) via parameterized config tables
. Refresh Metric Views from certified WC & MX template, proving global reusability
. KPI-by-KPI reconciliation vs legacy GCP to confirm calculation parity
. Validates parametrization design for future market rollouts
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
Travel Argentina
Travel Brazil
Travel Argentina
Travel Brazil
Travel Argentina

## Slide 17: 2. MDLZ INVENTORY & SHIPMENT
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across full LA with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
(+WC + MX + SC)
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for full LA
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
SonarQube and AI audit review
. AI/BI dashboard prototypes per persona for full LA
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
Travel Brazil
(+WC + MX + SC)

## Slide 18: 3. MARKET MEASUREMENT AND PROMOTIONS
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across full LA with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
(+WC + MX + SC)
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for full LA
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
SonarQube and AI audit review
. AI/BI dashboard prototypes per persona for full LA
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
Travel Brazil
(+WC + MX + SC)
. Ingest FMT datasets with validated schemas, volumetrics, and refresh cadence with DQ gate controls applied
. Onboard new Market Measurement & Promo sources into GCP Harmonized
. Federated integration into Databricks
. Metadata and lineage registered in Unity Catalog

## Slide 19: 4. MEXICO DSD
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across MEXICO DSD with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for MEXICO DSD
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
SonarQube and AI audit review
. AI/BI dashboard prototypes per persona for MEXICO DSD
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
Travel Mexico

## Slide 20: 5. BRAZIL PVC / VR / EASTER
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across BRAZIL with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for BRAZIL
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
. AI/BI dashboard prototypes per persona for BRAZIL
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
. Ingest FMT datasets with validated schemas, volumetrics, and refresh cadence with DQ gate controls applied
. Onboard new Market Measurement & Promo sources into GCP Harmonized
. Federated integration into Databricks
. Metadata and lineage registered in Unity Catalog
Reverse-engineer Brazil PVC/VR/Easter GCP pipelines, stored procs, and DAX logic
Document calculation flows, business rules, and exception handling
Extract GCP production reconciliation baselines
Map legacy logic to 8-Block Architecture and KPI engine design
Formalize undocumented rules and workarounds into config objects
Travel Brazil
Travel Brazil
Travel Brazil

## Slide 21: 6. STORE OPERATIONS (PERFECT & RIGHT STORE)
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across full LA with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
(+WC + MX + SC)
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for full LA
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
. AI/BI dashboard prototypes per persona for full LA
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
. Ingest FMT datasets with validated schemas, volumetrics, and refresh cadence with DQ gate controls applied
. Onboard new Market Measurement & Promo sources into GCP Harmonized
. Federated integration into Databricks
. Metadata and lineage registered in Unity Catalog
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Evaluate MC1 ingestion and standardization via SnackSync in GCP
Assess data quality, completeness, and schema consistency for Store Ops
Document SnackSync logic, refresh cadence, and known gaps
Federated integration from SnackSync into Databricks Harmonized Layer

## Slide 22: WORKSHOPS IN A PAGE
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
Travel Brazil
Travel Argentina
Travel Brazil
Travel Argentina
Travel Brazil
Travel Argentina
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Mexico
Travel Brazil
Travel Brazil
Travel Brazil
Travel Brazil
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
OTC / EPOS
Inventory/ Shipment
Market Measurement / Promotions
Mexico DSD
Brazil PVC/ VR/ Easter
Store Operations

## Slide 23: 7. SNACKSYNC
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
WE ARE HERE!