STATEMENT OF WORK (SOW)

Data and Analytics Services: “Matrix AI”

This Statement of Work (the “SOW”) is effective as of November 2, 2026 (“Effective Date”) by and between by and between Mondelez Mexico S. de R.L. de C.V., having address at Av. 18 de noviembre 1028, Col. Camino a Manzanilla, Puebla, 72304, Mexico (“Buyer”) and Lingaro Mexico S. de R.L. de C.V., having an address at Calle Obrero Mundial number exterior 644, interior floor 2 office 201, Colonia Atenor Salas, Benito Juarez, Zip Code 03010 in Mexico City (“Seller”).

Mondelez Global LLC (“MONDELEZ”) and Lingaro sp. z. o.o. (“Supplier”) entered into the Product Engagement Agreement, dated April 12th, 2024 (the “Product Engagement Agreement”) for the provision of Data and Analytics Services.

Unless the context otherwise indicates, capitalized terms that are used but not defined in this Statement of Work shall have the meaning assigned to such terms in the Product Engagement Agreement.

- Summary.

| Program Name description | MATRIX AI — Latin America Data & Analytics Program Delivery Model: Cross-Stream Product Program (Platform + Product Stream Orchestration) |
| --- | --- |
| Program Name | Matrix AI |
| AR number |  |
| Cost Center / WBS number |  |
| Seller’s Name | Lingaro |
| Start Date | 02 November 2026 |
| End Date | 31 December 2027 fully delivered and 31 March 2028 with Warranty clauses |
| Work Location(s) | Remotely |
| Seller Delivery Manager (SPOC) | Tim Kemp tim.kemp@lingarogroup.com |
| Buyer Delivery Manager (SPOC) | Ana Sola ana.sola@Mondelez.com |
| Buyer Procurement Contact | Slav Denyakin slav.denyakin@Mondelez.com |
| Delivery Model: Product-Oriented Delivery | Cross-Stream Product Program (Platform + Product Stream Orchestration) |
| Commercial Model | Fixed-Price Product Build Phase (Introduction Stage) |
| Currency | USD |
| Fees at Risk % | 0% |

- Financial details:

| Statement of Work | Net Fees* (Tracked in EAC) | Expenses | Total Budget (USD) |
| --- | --- | --- | --- |
| Original SOW | 0% |  |  |
| Investment | 0% |  |  |
| Total | 0% |  |  |

*Taxes are not included in the Fees above.

- Objectives. Specified Buyer’s objectives for this SOW:

Background:

Mondelez International operates a complex, multi-market commercial analytics landscape across Latin America. Analytical products for Mexico, Wacam, Brazil, and Southern Cone have been running in production on Google Cloud Platform (GCP), supporting Sales, Marketing, and Supply Chain decision-making. However, the majority of KPI calculations currently reside within Power BI semantic layers rather than in the data platform, creating a fragmented, difficult-to-govern, and non-scalable analytical estate where the same KPI can produce different results depending on the report, the market, or the analyst.

This fragmented state presents three critical business risks: (i) KPI inconsistency across the four Business Units undermines executive confidence in commercial reporting; (ii) the absence of pre-calculated, governed KPIs in the data lake prevents adoption of enterprise-grade AI capabilities (Databricks Genie, AI/BI Dashboards, Knowledge Assistants); and (iii) each market's analytics codebase has diverged to the point where onboarding a new market requires duplicating and rewriting the entire pipeline rather than configuring the existing one.

Addressing these risks requires a fundamental re-architecture: migrating the commercial, marketing and supply chain analytical platform from GCP to Databricks on AWS; adopting a configuration-driven design that treats every market difference as a data parameter rather than a code branch; implementing a governed KPI registry and calculation engine as the single source of truth across all four markets (Mexico, Wacam, Brazil, Southern Cone - full Latin American Business Units); and establishing end-to-end data quality and costs monitoring, governance processes, alerts, and lineage reporting.

This Statement of Work formalizes the engagement between MONDELEZ and Lingaro to execute that transformation as a fixed-price product build contract, covering the Introduction (Build, Launch & Hypercare) stage of the MATRIX AI product lifecycle. The engagement is organized into delivery into five phases, each governed by the CDRB (Configuration-Driven Review Board) quality framework (Sections A through L, as defined in Appendix A) and subject to formal phase-gate acceptance:

- Phase 1 — Blueprint & Working Prototype (November 2026 – January 2027): Solution architecture design, KPI harmonization across all four BUs, configuration object creation, core domain fit/gap analysis and build in alignment with Data Product & Engineering (DP&E), and delivery of a full Latin American working prototype in the existing Databricks development environment. The core domain work in this phase shall be guided by DP&E, who shall determine whether the Supplier consumes and validates canonical core domain entities built by DP&E, or whether the Supplier builds those entities under DP&E technical direction. Blueprint and build in November and December 2026, Prototype demonstration by January 2027.  Data Quality & Observability — Design: Define the end-to-end data quality framework architecture, including DQ expectation rules for every pipeline stage (ingestion, harmonization, core domain, KPI calculation, publication, metric views). Design the jobs monitoring architecture (improvement of 30% in the performance of the pipelines): run log schema, watermark tracking per market, duration and row-count capture per procedure, and quality gate result recording (CDRB K01). Design the cost tracking model: compute cost tagging strategy by layer, market, and procedure; cost allocation methodology; and budget threshold definitions per pipeline tier (CDRB G07). Design alert routing rules: failure alerts, SLA-breach alerts, DQ threshold breach alerts, and cost overrun alerts, with ownership mapping to responsible teams (CDRB K02). Design the monitoring dashboard wireframes for DQ pass/fail rates, job execution status, runtime trends, and cost-per-run views. All designs documented and reviewed as part of the Blueprint deliverable. Training & Enablement: Develop the Training Needs Assessment and Training Strategy, identifying all user personas (commercial analysts, KAMs, field sales, trade marketing, technical operations, data engineers). Curate and assign foundational Databricks training paths from Databricks Academy free courses (Data Engineering, Databricks SQL, Unity Catalog Fundamentals) and Pluralsight courses (Databricks for Data Engineers, Apache Spark Fundamentals) for the Lingaro and MONDELEZ technical product teams. Begin development of custom MONDELEZ-specific training modules covering the MATRIX-AI 8-block pipeline architecture, CDRB quality framework, configuration-driven design principles, and the KPI registry governance model. For Data Governance, it also includes the following as scope: 1. Connect all DBx/AWS tables to Ataccama for Tech metadata and profiling (as Knowledge catalog) and for Lineage purposes. 2. Create all Business terms/KPI/Business rules/etc in Ataccama (as Business glossary) 3. Map Knowledge catalog with Business glossary. 4. Convert Business rule to DQ rules 5. Create Monitoring projects for DQ rules and enable regular checks.

- Phase 2 — Migration & Scalability Proof (February – March 2027): Full migration from the Databricks exploration zone to the Databricks AWS Development environment. Unit testing, golden data tests, and parallel-run reconciliation against legacy GCP. Configuration only (zero code changes) as proof of global scalability. CDRB final sign-off on all procedures and reconciliation evidence. Data Quality & Observability — Build & Test: Implement DQ expectation rules at every quality gate across all 8 pipeline blocks; build automated DQ checks for key uniqueness, null-key rates, orphan records, row-count reconciliation, and missing conversion factors (CDRB E03). Build the jobs monitoring infrastructure: run log tables capturing status, rows read/written, watermark position, duration, and quality gate results for every procedure execution; per-market watermark tracking ensuring isolated re-run capability (CDRB K01). Build the cost tracking infrastructure: apply compute cost tags by layer, market, and procedure across all pipeline jobs; implement cost aggregation views queryable via SQL and Genie (CDRB G07). Build the alert framework: configure automated failure alerts, SLA-breach alerts, DQ threshold breach alerts, and cost overrun alerts with routing to responsible teams (CDRB K02). Build the operational runbook for each job and failure scenario, including the single-market re-run procedure and parameter-driven backfill process (CDRB K03). Test all monitoring, alerting, and cost tracking components as part of the migration validation; verify run logs, alert delivery, and cost tag accuracy in the DEV environment. Training & Enablement: Complete foundational Databricks and Pluralsight course assignments for all technical team members with tracked certification progress. Develop custom MONDELEZ training materials for Unity Catalog metric views, row-level security administration, Genie space configuration, and AI/BI dashboard design patterns. Build hands-on lab environments in the DEV workspace for guided exercises. Deliver initial Train-the-Trainer sessions to the MONDELEZ business product team (designated trainers from each BU) covering platform architecture fundamentals, the KPI dictionary, and Genie natural-language querying basics.

- Phase 3 — Project Team Testing & User Testing in DEV (April – June 2027): End-to-end testing and validation by the product team (April), followed by full user testing with business stakeholders from all four markets (May–June). Synthetic market test (CDRB) with the fictional market "ZZ" demonstrating configuration-only onboarding. All critical and high-priority defects resolved before promotion to the Quality environment. Data Quality & Observability — Deploy Dashboards & Validate: Deploy the full suite of monitoring dashboards in the DEV environment: (a) Data Quality Dashboard showing DQ pass/fail rates by domain, market, pipeline layer, and date, with drill-down to individual rule failures and trend analysis; (b) Jobs Monitoring Dashboard showing real-time and historical job execution status, runtime per procedure, watermark positions per market, success/failure rates, and SLA compliance indicators; (c) Cost Monitoring Dashboard showing compute cost per run broken down by layer, market, and procedure, with daily/weekly/monthly cost trends, budget utilization percentage, and cost anomaly detection; (d) Genie-queryable cost and monitoring views enabling natural-language queries such as "what was the pipeline cost for Brazil last week" or "which procedure exceeded its runtime budget yesterday." Validate all alerting end-to-end: simulate job failures, DQ breaches, SLA violations, and cost overruns to confirm alerts route correctly to the owning teams. Validate the operational runbook: execute the single-market re-run procedure, a parameter-driven backfill, and a load rollback using the documented steps, confirming idempotent re-execution and correct cost tagging of re-runs (tagged as run_type = reprocess). Training & Enablement: Deliver comprehensive Train-the-Trainer program to the MONDELEZ business product team, covering all custom training modules: Genie space usage per business persona, AI/BI dashboard interpretation and self-service exploration, KPI dictionary navigation and business rule understanding, data quality monitoring dashboards, and the configuration-driven onboarding process. Trainers complete certification assessments and conduct supervised pilot training sessions with a small group of end users. Finalize all custom MONDELEZ training materials including user guides, quick-reference cards, video walkthroughs, and FAQ documents. Integrate relevant Databricks Academy and Pluralsight course links into the training portal as self-service learning paths for ongoing skill development.

- Phase 4 — Integration Testing & UAT in Quality Environment (July – August 2027): Solution promoted to the Quality environment. Integration testing, including cross-domain data flows and multi-market concurrent execution. Full User Acceptance Testing with business stakeholders. Final parallel-run reconciliation against legacy GCP pipeline with KPI-by-KPI sign-off. Go/no-go decision for production release. Data Quality & Observability — QA Hardening & Sign-Off: Promote all monitoring dashboards, alert configurations, cost tracking, and runbooks to the Quality environment. Execute full monitoring validation in QA: confirm DQ dashboards reflect Quality environment data correctly; confirm job monitoring dashboards track QA pipeline executions with accurate runtime and row-count metrics; confirm cost tracking tags apply correctly in the QA compute cluster with cost views matching actual Databricks billing; confirm all alerts fire correctly in QA (failure, SLA breach, DQ breach, cost overrun). Conduct performance benchmarking against CDRB G01 budgets in the Quality environment: each procedure within 30% of improvement, full daily chain within 30% of improvement, publish layer within 30% of improvement. Validate runtime monitoring captures these benchmarks and raises alerts on exceedances. Validate end-to-end data lineage in Unity Catalog from source record to KPI output to metric view (CDRB K04). Sign off on all observability components as part of the go/no-go production readiness decision. Training & Enablement: Certified MONDELEZ trainers (Train-the-Trainer graduates) lead end-user training sessions for all four BUs, supported by the Supplier. Training delivered per persona: (a) commercial analysts and KAMs receive Genie querying, AI/BI dashboard, and KPI interpretation training; (b) trade marketing and field sales receive operational dashboard and sell-in/sell-out analysis training; (c) technical operations and data governance teams receive Unity Catalog administration, DQ monitoring, job monitoring dashboards, cost monitoring dashboards, and runbook training including the single-market re-run procedure. All training sessions are conducted in the Quality environment using real data. Collect training effectiveness feedback and address gaps before go-live. Publish the complete training portal with Databricks Academy paths, Pluralsight courses, and all custom MONDELEZ materials accessible to every user.

- Phase 5 — Go-Live, Hypercare & Transition to Support (September – December 2027): Production deployment across all four Latin American markets. Hypercare stabilization support. Publication of the Global Scalability Playbook (Appendix). Knowledge of transfer and formal Transition to Support. Data Quality & Observability — Production Monitoring & Stabilization: Activate all monitoring dashboards, alert configurations, and cost tracking in the Production environment from day one. During Hypercare, the Supplier shall actively monitor: DQ dashboards for data quality regressions across all four markets; job monitoring dashboards for runtime anomalies, failure patterns, and SLA compliance; cost monitoring dashboards for compute cost trends, budget adherence, and cost anomalies per layer, market, and procedure. Tune alert thresholds based on production data patterns (DQ tolerances, runtime baselines, cost baselines). Execute and validate the operational runbook in production for at least one single-market re-run, one parameter-driven backfill, and one load rollback to confirm procedures of work in the production environment. Deliver the final cost baseline report: documented compute cost per market per month, cost per pipeline layer, and projected annual run cost for budget planning. Training & Enablement: Supplier provides dedicated training support during Hypercare, including drop-in help sessions for end users encountering issues in the production environment; refresher training sessions for areas identified as gaps during UAT feedback; advanced training modules for power users covering custom Genie space creation, advanced KPI analysis techniques, and metric view interpretation. Execute formal knowledge transfer to the MONDELEZ operational and support teams, covering pipeline operations and re-run procedures, configuration table maintenance for future market onboardings, KPI registry governance and update workflows, DQ monitoring alert response and resolution procedures, job monitoring dashboard usage and SLA tracking, cost monitoring dashboard interpretation and budget escalation procedures. Hand over all training materials, lab environments, monitoring dashboards, alert configurations, runbooks, and the training portal to MONDELEZ for ongoing ownership. Ongoing learning paths via Databricks Academy and Pluralsight remain available as self-service resources for new team members and continuous skill development. Product Continuity Planning: The Transition to Support is not a termination of the MATRIX AI product but the beginning of its Evaluation phase within the POET Product Lifecycle Management framework. During Hypercare, the parties shall jointly develop a Product Continuity Plan that defines:

  - Steady-state product team composition: the ongoing MATRIX AI product team structure for continuous product ownership post-Hypercare, covering MONDELEZ-side roles (Product Lead, Business Analysts, Data Governance representative) and any ongoing Supplier capacity required to sustain and evolve the product;

  - Post-Go-Live product roadmap: the product roadmap for the first two quarters following Go-Live, including a prioritized backlog of known enhancements, additional market onboarding opportunities, and new data product candidates surfaced during the build phases;

  - Ongoing operating model: the delivery methodology for continuous product evolution post-Hypercare, defining the appropriate POET multi-speed model for each work type — Kanban for business-as-usual support and minor enhancements, Scrum sprints for significant new feature delivery or market onboarding;

  - POET governance cadence: the ongoing governance structure aligned to POET Product Council and Platform Council reporting, including the MATRIX AI product's position within the relevant Product Stream(s) and the D&A Platform Line, and the agreed reporting cadence for TCO, adoption, and value realization metrics.

  - Should MONDELEZ elect to engage the Supplier for ongoing product capacity beyond Hypercare, such engagement shall be structured as persistent product team capacity under a separate SOW, consistent with POET funding principles.

Vision & Strategic Objectives

The MATRIX-AI Analytics Platform is designed to serve as Mondelez International's global, scalable commercial and supply chain analytics product, with Latin America as the first deployment and the proof point for worldwide rollout. The strategic objectives driving this engagement are:

(a) One product, all markets — configuration-driven scalability: A single codebase where every market difference (for example business rules, KPI formulas, document classifications, currency policies, cut-off rules) is externalized into versioned configuration assets. Adding a new market requires only configuration rows, zero code changes. The architecture shall be proven through the configuration-only and validated through a synthetic market test (CDRB).

(b) Governed KPI accuracy — single source of truth: A KPI registry serving as the authoritative, executable source of truth for every formula, filter, aggregation rule, unit-of-measure expansion, currency conversion, and business definition. All KPIs shall be pre-calculated in the data platform (not in front-end tools), visible and auditable across all markets and consumers, and governed through CDRB Section F quality criteria.

(c) Enterprise-grade Generative AI readiness: Governed metric views and semantic layers registered in Unity Catalog, enabling business users to query the platform in natural language through Databricks Genie Agents, Supervisor Agents, AI/BI Dashboards, and Knowledge Assistants, with responses grounded exclusively in certified, row-level-security-protected KPI data. No AI consumer shall access raw pipeline tables directly.

(d) Latin America as the Global Lighthouse — Program Orchestration: MATRIX AI operates as a program umbrella that orchestrates the delivery of multiple data products across Product Streams (Marketing, Sales & eCommerce; Supply Chain) and the Data & Analytics Platform Line (Databricks). The four-market Latin American deployment serves as the definitive proof that the platform architecture and the configuration-driven product model are globally scalable. Success is measured not only by technical scalability but by the program's ability to coordinate cross-stream priorities, harmonize KPIs across business domains, and enable each Product Stream to independently consume governed data products through a shared platform foundation. Success is measured by: (i) All markets onboarded through configuration only with zero code changes; (ii) the synthetic market "ZZ" test passes all CDRB criteria end-to-end; (iii) the Global Scalability Playbook (Appendix) documents the configuration-only onboarding path with 20 validated examples; and (iv) all CDRB quality sections are signed off across the full solution.

(e) Full audit trail, data lineage, and access governance: End-to-end visibility from source system to dashboard and AI consumer, with data lineage tracked in Unity Catalog and aligned with the MONDELEZ enterprise data governance platform (Ataccama) for cataloguing, lineage, and data quality governance. The Supplier shall follow the Data Governance team's processes and provide all required metadata, lineage documentation, and data quality rule definitions to enable Ataccama registration — the Supplier is not required to operate Ataccama directly. Row-level security enforced at the metric view layer, least-privilege access throughout the pipeline (CDRB), and automated data quality monitoring with alerts at every processing stage (CDRB).

(f) Measurable Business Value Delivery — The MATRIX AI platform shall demonstrate measurable business outcomes, not only technical completeness. Success shall be evaluated through the HEART Framework (Happiness, Engagement, Adoption, Retention, Task Success) and Business Value Metrics (KPI consistency, decision-making acceleration, executive confidence, self-service enablement), consistent with the MONDELEZ POET principle that every product must deliver measurable business value by connecting customer needs, business goals, and technology capabilities to ensure outcomes — not just outputs.

3.1 POET Organizational Positioning

MATRIX AI is positioned within the MONDELEZ POET operating model as a cross-stream program that orchestrates delivery across the following POET organizational units:

Product Streams touched:

- Marketing, Sales & eCommerce — OTC, Promotions, Market Share, EPOS, Perfect & Right Store, DSD Mexico

- Supply Chain — Inventory, Shipments

Platform Line leveraged:

- Data & Analytics Platforms — Databricks (AWS), Unity Catalog, AI/BI, Genie Agents

Program orchestration scope: MATRIX AI does not own a single product backlog. Instead, it orchestrates the interdependencies between multiple data products (each of which may evolve into a standalone product within its respective Product Stream) and the shared D&A platform layer. This orchestration includes:

- Cross-stream KPI harmonization — Ensuring KPI definitions, calculation engines, and semantic layers are consistent across Product Streams, governed through a unified KPI Registry;

- Platform foundation delivery — Delivering the shared 8-block pipeline architecture, configuration layer, and consumption infrastructure on the D&A Platform Line (Databricks);

- Data product enablement — Enabling each Product Stream to independently own and evolve its data products (e.g., OTC analytics, Market Share analytics) once the platform foundation and harmonized KPI layer are in place;

- Regional coordination — Coordinating delivery across four Latin American markets (Mexico, Wacam, Brazil, Southern Cone) under the POET Hub & Spoke model, where the global platform architecture serves as the Hub and each market's configuration serves as the Spoke.

Hub & Spoke alignment: Consistent with the POET key design principle that "Hubs define shared standards, reusable capabilities, and guardrails" while "Spokes tailor and innovate for market-specific needs", MATRIX AI's architecture externalizes all market differences into versioned configuration tables (the Spoke), while the pipeline codebase, KPI calculation engine, and semantic layer remain globally standardized (the Hub). Source Mondelēz_POET_WS2A - Key Design Decisions, Tech Capability Model & L1-L3 P&P Hierarchy_07102025.md

Post-program product transition: Upon successful completion of the MATRIX AI program, the individual data products enabled by this engagement (e.g., OTC Analytics, Market Share Analytics, Inventory Analytics) are expected to transition into the backlogs of their respective Product Streams for ongoing ownership and evolution, consistent with POET's principle of continuous product ownership. The shared platform components will continue to be governed through the D&A Platform Line. This transition plan shall be documented in the Product Continuity Plan.

- Scope. The scope of the Services to be performed pursuant to this SOW is defined in the Product Engagement Agreement or otherwise specified in this SOW.

The Supplier shall design, build, test, and deploy the MATRIX-AI Analytics Platform: a global, scalable, configuration-driven data and analytics product built on Databricks, using Latin America as the global lighthouse. The platform shall replace the existing GCP-based analytical solution and enable enterprise-grade KPI calculation, governed data products, and Generative AI capabilities (AI/BI Dashboards, Genie Agents, Knowledge Assistants and AI Supervisors) across all four Latin American Business Units (Mexico, Wacam, Brazil, and Southern Cone).

The Services shall be delivered as a fixed-price engagement across all build phases, each governed by the CDRB quality framework and AI tools to prove the code review matches with product design principals and envision (Appendix).

4.1 Business Processes and Data in Scope:

The platform shall cover the following business domains, including all associated data sources, manual files, and end-to-end pipelines built in Databricks:

| # | Product Stream | Business process / Topics | Coverage |
| --- | --- | --- | --- |
| 1 | Supply Chain (ISC) | OTC — Order-to-Cash | Sales orders, invoices, deliveries, order schedule & status, on-time delivery, billing accuracy, open order buckets |
| 2 | Supply Chain (ISC) | Mondelez Inventory | Internal stock snapshots, warehouse and plant-level inventory positions |
| 3 | MSE — Sales & eCommerce | EPOS / Channel Inventory | Electronic Point-of-Sale sell-out data, channel inventory positions, store-level granularity |
| 4 | MSE — Sales & eCommerce | E-RTM / Snacksync | Expansion of EPOS / Channel Inventory / Perfect & Right Store |
| 5 | MSE — Marketing | Market Share | All market measurement data and calculations |
| 6 | Cross-Stream (Platform) | Master Data Hierarchies | All Customer, Product and Calendar hierarchies, including alternative hierarchies |
| 7 | MSE — Sales & eCommerce | Perfect & Right Store | Data in scope for all applications for Perfect and Right Store Operations |
| 8 | Supply Chain (ISC) | Shipments | Data sources from OTM (Oracle Transportation Management) and SAP TM (Transportation Management) |
| 9 | MSE — Marketing | Promotions | Full data in scope for promotions |
| 10 | MSE — Sales & eCommerce | DSD Mexico | Full Mexico DSD data in scope with DSD suggested replenishment |
| 11 | MSE — Sales & eCommerce | Brazil VR / PVC / One Click / Lenses / Easter | Assess, improve and build Brazil-specific analytical products (VR = Variable Remuneration, PVC = Price Value Chain, Lenses Daily Sales and Easter |
| 12 | Cross-Stream (Platform) | Cross functional datasets | Integrated views with configurable matching rules per market across all datasets |
| 13 | Cross-Stream (Platform) | Historical data loads | Historical data from other databases based on the business processes in scope |

4.2 Technical Architecture: 8-Block Pipeline

The Supplier shall implement the end-to-end pipeline following the 8-block architecture. Every step must follow the standard template (Contract, Context, Config, Extract, Transform, Quality Gate, Load, Log):

Block 1 — Source Ingestion (work with D&A Data Onboarding):

(a) Establish federated connections from GCP layers to bring data for the prototype build in Databricks;

(b) Ingest all required data to build the full solution into Databricks, following D&A Data Onboarding standards and processes;

(c) For the ingestion of new data sources, the Supplier shall assess the data required, perform harmonization and simplification as applicable, and provide all technical documentation (including data specifications, mapping definitions, transformation logic, and quality requirements) to the D&A Data Engineering team for Data Onboarding execution;

(d) The D&A Data Engineering team shall bear primary responsibility for the execution of data ingestion activities. However, in the event that the D&A Data Engineering team lacks sufficient resources to execute the data ingestion within the agreed timelines, the Supplier shall provide qualified resources to perform the ingestion work. Such resources shall operate under the guidance, processes, and standards defined by the D&A Data Engineering team, ensuring consistency with enterprise data onboarding practices.

Block 2 — Harmonization & Standardization: Cleansing, type enforcement, naming standardization, unity of measure and currency conversions, deterministic de-duplication, and Data Quality expectations with failure logging. The Supplier shall provide the Data Governance team with all DQ rule definitions, thresholds, and failure logging specifications implemented at this layer, following the Data Governance team's process for Ataccama registration.

(a) Design, build, and maintain the harmonization and standardization layer responsible for cleansing, type enforcement, naming standardization, unit normalization, and structural alignment of all ingested data, producing a consistent, source-agnostic foundation for downstream Core Domain entities (Block 3);

(b) The Supplier shall work collaboratively with D&A Data Product & Engineering (DP&E), D&A Architects, the relevant Product Stream teams, and the D&A Data Governance team to assess, define, and validate the complete set of harmonization rules, standardization policies, and data quality thresholds per data source and business domain, ensuring that all transformations are traceable, auditable, and consistent with enterprise data governance standards;

(c) For each new or migrated data source, the Supplier shall assess the data structures and quality characteristics, harmonize and simplify naming conventions, data types, units of measure, calendar formats, and classification hierarchies as applicable, and provide all technical documentation (including harmonization rule specifications, standardization mappings, data type conversion policies, naming convention dictionaries, and quality threshold definitions) to D&A Data Product & Engineering, D&A Architects, and the D&A Data Governance team for review and approval;

(d) The D&A Data Product & Engineering (DP&E) team shall bear primary responsibility for the governance, validation, and execution of harmonization and standardization activities, ensuring alignment with enterprise data product standards and the harmonization design. However, in the event that the DP&E team lacks sufficient resources to execute the harmonization and standardization work within the agreed timelines, the Supplier shall provide qualified resources to perform the work. Such resources shall operate under the guidance, processes, and standards defined by the DP&E team and D&A Architects, ensuring consistency with enterprise data product and governance practices;

(e) As an output of this work, the Supplier shall deliver a Harmonization & Standardization Playbook documenting, at minimum:

(i) the complete inventory of harmonization rules and standardization mappings per data source, market, and business domain;

(ii) guidelines for adding, modifying, and retiring harmonization rules through governed processes when new data sources or markets are onboarded;

(iii) the data quality validation framework applied at the harmonization layer, including pre- and post-transformation quality checks;

(iv) naming convention standards and data type enforcement policies applicable across all markets; and

(v) step-by-step instructions enabling Product Stream teams to independently extend and manage harmonization rules following the defined standards.

Block 3 — Core Domain Build: Canonical entities with reusable assets for all markets, aligned with DP&E global canonical core domain standards. DP&E shall determine the delivery model for each core domain entity:

(a) Design and build canonical entities with reusable assets for all markets, aligned with D&A Data Product & Engineering (DP&E) guidance and enterprise data modeling standards;

(b) For the development of new core domain entities, the Supplier shall assess the business and data requirements, harmonize and simplify data structures as applicable, and provide all technical documentation (including entity definitions, relationship models, data lineage specifications, and quality requirements) to the D&A Data Product & Engineering team for review and alignment;

(c) The D&A Data Product & Engineering team shall bear primary responsibility for the governance and approval of core domain design decisions. However, in the event that the D&A Data Product & Engineering team lacks sufficient resources to execute the core domain build within the agreed timelines, the Supplier shall provide qualified resources to perform the build work. Such resources shall operate under the guidance, processes, and standards defined by the D&A Data Product & Engineering team, ensuring consistency with enterprise data product practices.

Block 4 — Market Configuration Layer: Versioned, market-keyed configuration tables (examples like market scope, document types, reason codes, item categories, cut-off rules, open order buckets, FX policies, business rules, KPI registry, Data Quality thresholds) plus a shared, unit-tested utility function library. New markets onboard via configuration only.

(a) Design, build, and maintain versioned, market-keyed configuration tables (including, but not limited to, market mappings, calendar definitions, currency conversion rules, SISO customer chain mappings, and KPI adjustment parameters) that drive all market-specific behavior across the pipeline without code changes;

(b) The Supplier shall work collaboratively with D&A Architects and the relevant Product Stream teams to assess, define, and validate the complete set of configuration objects required per market, ensuring that all business rules and market-specific logic are captured as data-driven configuration rather than hardcoded logic;

(c) For each new configuration object, the Supplier shall harmonize and simplify existing business rules from legacy systems (including GCP stored procedures and Power BI DAX measures), and provide all technical documentation (including configuration object specifications, versioning policies, validation rules, and dependency mappings) to the D&A Architects and Product Stream teams for review and approval;

(d) As an output of this work, the Supplier shall deliver a Market Configuration Playbook documenting, at minimum:

(i) the complete inventory of configuration objects per market and business process;

(ii) guidelines for adding, modifying, and retiring configuration entries;

(iii) the versioning and governance model for configuration changes;

(iv) validation and testing procedures to ensure configuration integrity before deployment; and

(v) step-by-step instructions enabling Product Stream teams to independently manage and extend market configurations following the defined standards.

Block 5 — KPI Calculation Engine: Parameterized engine reading Core Domains and Configuration only. Where DP&E provides global KPI pre-calculations as part of the canonical core domain layer, the Supplier shall consume and validate those pre-calculated KPIs against LA business definitions before building additional KPI logic. Where DP&E determines the Supplier shall build KPI pre-calculations, the Supplier shall do so under DP&E technical direction. Narrow output: KPI code, grain keys, UoM, value. New markets onboard via configuration only.

(a) Design, build, and maintain a parameterized KPI calculation engine that reads exclusively from Core Domain entities (Block 3) and Market Configuration tables (Block 4), calculating all KPIs in base units (kilograms and local currency) and expanding to additional units and currencies through configuration-driven conversion rules;

(b) The Supplier shall work collaboratively with D&A Architects, the relevant Product Stream teams, and Business Analysts to assess, define, and validate the complete inventory of KPI calculations per market and business process, ensuring that all calculation logic, filters, adjustments, calendar rules, and aggregation methods are fully parameterized and governed through the KPI Registry;

(c) For each new or migrated KPI, the Supplier shall harmonize and simplify existing calculation logic from legacy systems (including GCP stored procedures and Power BI DAX measures), and provide all technical documentation (including KPI specifications, formula definitions, filter conditions, adjustment rules, unit conversion policies, and additivity declarations) to the D&A Architects and Product Stream teams for review and sign-off;

(d) As an output of this work, the Supplier shall deliver a KPI Calculation Engine Playbook documenting, at minimum:

(i) the complete KPI inventory per market and business process with calculation specifications;

(ii) guidelines for adding, modifying, and retiring KPIs through configuration changes only;

(iii) the governance model for KPI definition changes, including Data Steward approval workflows;

(iv) reconciliation and validation procedures to ensure calculation accuracy against legacy outputs before deployment; and

(v) step-by-step instructions enabling Product Stream teams to independently extend and manage KPI calculations following the defined standards.

Block 6 — KPI Publication / Data Products: Generic publish layer (example as read base → evaluate composites → expand UoM → expand calendar → apply FX → persist). New KPI domains follow the same pattern without new publish logic. New markets onboard via configuration only.

(a) Implement a generic publish layer (e.g., read base → evaluate configuration → calculate → publish) that transforms KPI engine outputs into consumable data products for downstream consumption layers;

(b) The Supplier shall work collaboratively with D&A Architects and the relevant Product Stream teams to define the optimal consumption patterns and data delivery strategies for KPIs and data, ensuring alignment with the specific requirements of Dashboards (AI/BI) and Agents (Genie Agents, Knowledge Assistants, Supervisor Agents);

(c) As an output of this collaboration, the Supplier shall deliver a KPI Publication & Consumption Playbook documenting, at minimum:

(i) the recommended consumption patterns per persona and use case;

(ii) data product structure and formatting standards for each consumption channel;

(iii) guidelines for registering and exposing KPIs to the semantic layer for dashboard and agent consumption;

(iv) decision criteria for selecting the appropriate consumption method (Dashboard vs. Genie Agent vs. Knowledge Assistant); and

(v) step-by-step instructions enabling Product Stream teams to independently publish and consume KPIs following the defined patterns.

Block 7 — Semantic Layer (Unity Catalog Metric Views): reusable views with row-level security registered in Unity Catalog. No consumer accesses raw pipeline tables directly. New markets onboard via configuration only. Develop automated process to generate metric views with new / existent KPIs.

(a) Design, build, and maintain reusable metric views within Unity Catalog with row-level security (RLS), registered as governed assets that serve as the single authoritative semantic interface between the KPI Calculation Engine (Block 5) and all downstream consumption channels (Block 8);

(b) The Supplier shall work collaboratively with D&A Architects, the relevant Product Stream teams, and the D&A Data Governance team to assess, define, and validate the complete set of metric views required per business domain and persona, ensuring that all semantic definitions, access policies, and metadata annotations are consistent with enterprise governance standards and Ataccama cataloguing requirements;

(c) For each new or migrated metric view, the Supplier shall harmonize and simplify existing semantic definitions from legacy systems, and provide all technical documentation (including metric view specifications, RLS policies, column-level descriptions, lineage mappings, local language synonyms, search tags, and Genie readiness annotations) to the D&A Architects, Product Stream teams, and the D&A Data Governance team for review and approval;

(d) As an output of this work, the Supplier shall deliver a Semantic Layer Playbook documenting, at minimum:

(i) the complete inventory of metric views per business domain, persona, and consumption channel;

(ii) guidelines for creating, modifying, and retiring metric views through governed processes;

(iii) the RLS design model and access governance framework, including role-to-market and role-to-function mappings;

(iv) metadata completeness standards and validation procedures to ensure all views meet Unity Catalog and Ataccama registration requirements; and

(v) step-by-step instructions enabling Product Stream teams to independently manage and extend metric views following the defined standards.

Block 8 — Consumption Layer: (a) AI/BI Dashboards on metric views, (b) Genie Agents per persona, (c) Knowledge Assistants, (d) Functional/Cross-Functional Supervisor Agents.

(a) Design, build, and deploy the end-user consumption interfaces that leverage the Semantic Layer (Block 7) as their sole data source, including:

(i) AI/BI Dashboards on metric views,

(ii) Genie Agents per persona,

(iii) Knowledge Assistants for natural-language data exploration, and

(iv) Functional and Cross-Functional Supervisor Agents for automated analytical workflows;

(b) The Supplier shall work collaboratively with D&A Architects, the relevant Product Stream teams, and Business Analysts to assess, define, and validate the consumption requirements per persona, business unit, and use case, ensuring that all dashboards, agents, and assistants are aligned with business needs, user experience standards, and the POET product-centric delivery model;

(c) For each consumption channel, the Supplier shall define and document detailed use cases covering, at minimum:

(i) AI/BI Dashboards — executive scorecards, market-level performance monitoring, KPI trend analysis, drill-down by business process and market, and comparative cross-market views;

(ii) Genie Agents — persona-specific natural-language querying for commercial analysts, supply chain managers, and market leads, including contextual KPI exploration, ad-hoc filtering, and exception-based alerting;

(iii) Knowledge Assistants — self-service data discovery, KPI definition look-up, methodology explanation, and guided analytical narratives for business users with varying levels of technical proficiency; and

(iv) Functional and Cross-Functional Supervisor Agents — automated monitoring of KPI thresholds, anomaly detection, proactive insight generation, and orchestrated analytical workflows spanning multiple business domains. Each use case shall specify the target persona, business scenario, expected interaction pattern, data requirements from the Semantic Layer, and measurable success criteria;

(d) For each new or migrated consumption artifact, the Supplier shall harmonize and simplify existing reports and analytical interfaces from legacy systems (including Power BI dashboards and ad-hoc reporting tools), and provide all technical documentation (including dashboard specifications, agent configuration definitions, use case specifications, persona-to-consumption mappings, interaction design guidelines, and access governance policies) to the D&A Architects, Product Stream teams, and Business Analysts for review and approval;

(e) As an output of this work, the Supplier shall deliver a Consumption Layer Playbook documenting, at minimum:

(i) the complete inventory of consumption artifacts and associated use cases per persona, business unit, and consumption channel;

(ii) guidelines for creating, modifying, and retiring dashboards, agents, and assistants through governed processes;

(iii) the persona-to-consumption mapping framework, defining which user roles access which interfaces and with what permissions;

(iv) design standards and best practices for dashboard layout, agent prompt engineering, and assistant knowledge base configuration;

(v) the full use case catalog with traceability from business requirements to consumption artifacts; and

(vi) step-by-step instructions enabling Product Stream teams to independently build, manage, and extend consumption artifacts following the defined standards.

4.3 Activities in Scope

(a) Architecture & Pipeline Design — 8-block model, CDRB Section A compliance.

(b) KPI Harmonization — Full LA inventory (code, formula, filters, adjustments, units, calendars, additivity, owner, version), signed off by all four BUs.

(c) Configuration Object Design — AI-assisted conversion of GCP stored procedures and Power BI DAX measures into externalized configuration objects, including mapping with users for rules outside of existent tools.

(d) Core Domain & KPI Engine Build — Core domain fit/gap analysis under DP&E guidance, followed by: (i) consuming and validating canonical core domain entities and global KPI pre-calculations built by DP&E; or (ii) where DP&E determines the Supplier shall build, building core domain entities and KPI pre-calculations under DP&E technical direction; and (iii) full KPI engine in Databricks, with unit testing, golden-data tests, and parallel-run reconciliation vs. legacy GCP. The delivery model (consume or build) for each entity shall be determined by DP&E during the fit/gap analysis.

(e) Semantic Layer & Consumption Build — Metric views, RLS (Row Level Security), Genie spaces, AI/BI dashboards, Knowledge Assistants and Supervisor Agents. Develop automated process to generate metric views with new / existent KPIs.

(f) Data Quality & Governance — Data Quality rules, automated reconciliation, Unity Catalog lineage, full audit trail (CDRB). The Supplier shall work with the MONDELEZ Data Governance team throughout the engagement, following their established processes and providing all required information — including DQ rule definitions, data lineage documentation, metadata descriptions, and dataset cataloguing inputs — to enable the Data Governance team to register and govern MATRIX AI assets in Ataccama. The Supplier is not required to perform any work directly in Ataccama.

(g) Testing & Reconciliation — Unit tests, golden-data tests, parallel-run reconciliation and legacy defect tracking.

(h) Global Scalability Proof — Config-only onboarding with true prototype / demonstration with zero code changes to onboard a new market like USA or Canada.

(i) Global Scalability Playbook — Architecture overview, onboarding checklist, synthetic market evidence, unique KPI handling, effort estimates, governance, and documented config-only onboarding examples.

(j) Migration Support — Databricks Exploration zone to Databricks AWS Dev for the full product build after blueprint / prototype phase.

(k) UAT Support — Defect management (logging, tracking, clarification, resolution).

(l) Hypercare & T2S — Post go-live stabilization and knowledge transfer.

(m) Delivery Management — Consolidated delivery coordination across workstreams (Daily Scrum, Weekly 4-Box, Monthly Leadership Update).

(n) Training & Enablement — Development of training materials for all user personas (commercial analysts, KAMs (Key Account Manager), field sales, trade marketing, and technical operations). Includes platform navigation guides, Genie space usage documentation, AI/BI dashboard interpretation guides, and KPI dictionary reference materials. Training content shall cover the Databricks environment, Unity Catalog metric views, Genie natural-language querying, and the configuration-driven onboarding process for future markets.

(o) Data Quality Monitoring & Alerts — End-to-end automated data quality monitoring framework covering every pipeline stage (ingestion, harmonization, core domain, KPI calculation, publication, and metric views). Includes: DQ expectation rules at every quality gate; automated alerts routed to the owning team when a quality threshold is breached or a DQ gate fails; a reconciliation dashboard tracking DQ pass/fail rates by domain, market, and pipeline layer; and anomaly detection for unexpected data volume changes, null-key rates, and orphan records (CDRB).

(p) Jobs Monitoring, Cost Tracking & Operational Dashboards — Comprehensive pipeline observability covering: (i) end-to-end job monitoring with complete run logs recording status, rows read/written, watermark position, duration, and quality gate results for every procedure (CDRB); (ii) automated failure and SLA-breach alerts routed to the responsible team with zero reliance on user-reported discovery (CDRB); (iii) compute cost tracking tagged by layer, market, and procedure, with monitoring dashboards and Genie-queryable cost views enabling identification of expensive operations and budget adherence verification (CDRB); (iv) runtime budget tracking confirming each procedure completes within 30% of improvement against existing procedures, the full daily chain within 30% of improvement against existing chain, and the publish layer within 30% of improvement (CDRB); and (v) data lineage visibility in Unity Catalog from source record through every pipeline layer to the final KPI output (CDRB).

(q) Operational Runbook & Re-Run Playbook — A documented, reviewed operational runbook for every job and failure scenario, covering: how to re-run a failed job safely (idempotent execution guaranteed); how to execute a parameter-driven backfill for historical data reprocessing; how to roll back a failed load without data loss; how to handle known issues and edge cases; and escalation procedures for unresolved failures. The runbook shall be published, reviewed by at least one team member not involved in writing it, and maintained as a living document through Hypercare (CDRB K03). Includes a re-run playbook with step-by-step procedures for full-history reprocessing, incremental catch-up runs, and market-specific reprocessing scenarios.

Single-Market Re-Run: The pipeline architecture enforces market isolation through per-market parameterization, partitioning, and independent watermarks (CDRB H03, H04, G02), enabling any failed market run to be re-executed for a specific date range without triggering, scanning, or affecting any other market's data, with compute cost proportional only to the failed market's volume.

4.4 Exclusions

(a) Databricks platform infrastructure provisioning and licensing (provided by Buyer).

(b) Business process re-engineering or organizational change management beyond training materials.

(c) Power BI report development beyond migration of existing dashboards to new metric views.

(d) Any work not covered by a mutually executed Change Order.

4.5 Program Team Integration Model. The Supplier team shall operate as an integrated delivery unit within the MONDELEZ MATRIX AI program team, consistent with POET's partner integration framework. The Supplier team shall operate as an integrated delivery unit within the MONDELEZ MATRIX AI program team, consistent with POET's partner integration framework. Under this model, the Supplier provides specialist data engineering, architecture, and GenBI capability that is not currently available within the MONDELEZ D&A organization, embedded within the program team structure. MONDELEZ retains product ownership, business analysis, data governance, and strategic direction for the enabled data products.

The program team composition for the MATRIX AI engagement shall include:

Core Team (persistent for the duration of the engagement and into steady-state planning):

MONDELEZ: Product Manager / Owner, Business Analysts per Business Unit, Data Product & Engineering (DP&E) Representatives (for core domain design direction and data product alignment), Data Governance Representatives (including Ataccama process owners for cataloguing, lineage, and DQ governance), Business Stakeholders.

Supplier: Senior Architect, Lead Data Engineer, Delivery Lead, Data Engineers, GenBI Engineer, QA / Testing. All team members, regardless of employer, shall participate in the unified agile ceremonies defined in Section 6 and collaborate as a single cross-functional program delivery team. The Supplier team shall be visible in the MONDELEZ Jira project and capacity planning, consistent with POET ways of working.

Build Team (Phases 1–5, scaling to demand):

Supplier: Data Engineers, GenBI Engineer, QA / Testing

MONDELEZ: Business Stakeholders, UAT participants

Scrum Master (mandatory):

Supplier: Scrum Master to facilitate agile ceremonies, remove impediments, and ensure delivery cadence. A Scrum Master shall be designated within the delivery team (Supplier) to facilitate agile ceremonies (Sprint Planning, Daily Stand-Ups, Retrospectives, Backlog Refinement), remove impediments, and maintain delivery cadence. This role is consistent with the POET mandatory POD composition and may be fulfilled by a dedicated individual or a team member with dual responsibilities, provided ceremony facilitation is not compromised.

The Core Team composition informs the steady-state team definition in the Product Continuity Plan (Phase 5). Build Team roles may transition to flex capacity post-Go-Live depending on the selected POET delivery model.

The integrated program team shall be right-sized consistent with POET team structure principles (typically 3–11 members per delivery stream). Where the MATRIX AI program operates across multiple business domains simultaneously, the team may organize into domain-aligned delivery streams (e.g., OTC, Supply Chain, Market Share), each maintaining POET team sizing guidelines while coordinating through the Cross-Stream Coordination governance defined in Section 6.

4.6 Snacksync Integration Assessment

The Supplier shall conduct a technical assessment of the existing Snacksync solution to evaluate its compatibility and integration feasibility with the MATRIX AI platform and its business process data. This assessment shall be structured as follows:

(a) Technical Assessment Phase (November 2026 – January 2027): The Supplier shall perform a comprehensive technical review of the current Snacksync solution, including its data architecture, data models, interfaces, and integration points. As an output of this assessment, the Supplier shall deliver a formal Technical Requirements Document specifying the conditions, dependencies, and technical requirements necessary to integrate the Snacksync solution with MATRIX AI business processes data.

(b) Technical Recommendations (by January 2027): In the event that the technical assessment identifies impediments to integration, the Supplier shall provide detailed technical recommendations outlining the specific changes, remediations, or adaptations required to enable integration. These recommendations shall be delivered no later than January 2027.

(c) Integration Feasibility Gate (April 2027): If the technical issues identified in subsection (b) above are resolved and validated by April 2027, the Snacksync integration shall continue as part of the MATRIX AI program scope, and the Supplier shall incorporate the integration work into the subsequent delivery phases. If the identified technical issues are not resolved by April 2027, the Snacksync integration shall be deemed out of scope for this SOW. In such case, the Supplier shall nonetheless ensure that the MATRIX AI platform architecture and configuration layer remain ready for future Snacksync integration, meaning the necessary configuration setup, data model placeholders, and integration touchpoints shall be built and maintained within the platform so that Snacksync can be onboarded through configuration-only changes, without requiring re-architecture or code modifications, once the technical prerequisites are met. Any further development, testing, or deployment work related to the actual Snacksync integration beyond this configuration readiness shall require a separate Change Order executed by both parties.

(d) Clarifications: The Snacksync assessment and integration activities described in this subsection are limited to technical evaluation and requirements definition. Any development, remediation, or re-engineering work required on the Snacksync solution itself to meet the integration requirements shall be the responsibility of the Buyer or the Snacksync solution owner, unless otherwise agreed through a Change Order.

- Deliverables. The following deliverables (“Deliverables”) will be produced during the course of this SOW:

The following deliverables shall be produced during the course of this SOW. Each deliverable includes measurable success criteria and CDRB quality gate references to ensure objective, evidence-based acceptance. Deliverables are organized by capability area to reflect the end-to-end product design: every deliverable must demonstrate global scalability (configuration-only market onboarding, zero code changes) and governed data quality as core acceptance conditions.

| # | Deliverable | Description | Measurable Success Criteria |
| --- | --- | --- | --- |
| D1 | 8-Block Pipeline Architecture | End-to-end data pipeline implementing all 8 blocks (Source Ingestion, Harmonization, Core Domain, Market Configuration, KPI Calculation, KPI Publication, Semantic Layer, Consumption) following the standard stored procedure template (Contract, Context, Config, Extract, Transform, Quality Gate, Load, Log). | 100% of procedures follow the 8-block template (CDRB D01). Market is a parameter on every procedure with zero market-specific code branches (CDRB A03). Environment is a setting, not code (CDRB A04). All layers have a single orchestrator (CDRB A05). Architecture design note approved before building (CDRB L01). Pipeline architecture design note reviewed by DP&E to confirm alignment with global data product architecture standards, particularly for Blocks 2 (Harmonization) and 3 (Core Domain), and to confirm the delivery model (consume or build) for each core domain component. |
| D2 | Core Domain Model (Canonical Entities) | Source-agnostic, reusable core domain entities for all Business Domains and data in scope, aligned with DP&E canonical core domain standards. The Supplier shall first conduct a fit/gap analysis under DP&E guidance to determine the delivery model for each entity. Where DP&E has built canonical entities, the Supplier shall consume and validate them for LA requirements. Where DP&E determines the Supplier shall build, the Supplier shall do so under DP&E technical direction, ensuring consistency with the global canonical design. Each entity with declared grain, business key, and standardized attributes (kg, local currency) | Every table has a declared identity with uniqueness enforced (CDRB B01). Market boundaries from configuration only (CDRB B02). Business classifications from reference tables only (CDRB B03). Measurements standardized (CDRB B04). Core tables describe what happened, not KPI outcomes (CDRB B05). Every record traceable (CDRB B06). No data silently lost (CDRB B07). Core domain fit/gap analysis completed and approved by DP&E before core domain build or consumption commences, documenting the delivery model (consume or build) for each entity. All consumed DP&E entities validated for LA requirements with documented results. The Supplier shall provide the Data Governance team with complete metadata descriptions (entity name, grain, business key, attribute definitions, source lineage, and data classification) for all core domain entities — whether consumed from DP&E or Supplier-built — following the Data Governance team's process for Ataccama cataloguing. |
| D3 | Market Configuration Layer (Configuration Tables + Shared Functions) | Versioned, market-keyed configuration tables externalizing all market-specific business rules from code: market scope, document types, reason codes, item categories, cut-off rules, open order buckets, FX policies, Business rules, KPI registry, and DQ thresholds. Plus a library of shared, unit-tested utility functions. | All business rules stored as configuration rows, not code (CDRB C01). No hidden numbers or dates in procedures (CDRB C02). No copy-paste procedures; similar logic parameterized (CDRB C03). Single source per reference dataset (CDRB C04). Configuration changes governed with version history (CDRB C05). Adding a new market requires only configuration rows, zero code changes. |
| D4 | KPI Calculation Engine & Registry as configurable asset | Parameterized KPI engine reading from Core Domains and Market Configuration only. KPI registry as the single source of truth for every formula, filter, aggregation rule, unit-of-measure expansion, currency conversion, and business definition. Output in narrow format. Generic 6-step publish layer. | All KPIs calculated in base units only (CDRB F01). Mutually exclusive population rules (CDRB F02). Composite KPIs from registry (CDRB F03). FX and adjustment policies declared (CDRB F04). Additivity declared per KPI (CDRB F05). Long/narrow model throughout (CDRB F06). Every KPI has a registered owner (CDRB F07). Dictionary generated from code, not manually maintained (CDRB F08). Business rules data-driven (CDRB F09). Calendar aggregation from daily grain (CDRB F10). The Supplier shall provide the Data Governance team with all KPI registry metadata (KPI code, formula, filters, aggregation rules, unit-of-measure, currency, calendars, owner, version, and business definition) in the format and cadence required by the Data Governance team for Ataccama registration. The KPI registry metadata shall be kept current as KPIs are added or modified throughout the engagement.. |
| D5 | Semantic Layer & Consumption (Metric Views, Dashboards, Genie, AI Agents) | Unity Catalog metric views with row-level security. AI/BI dashboards connected to metric views. Genie spaces per business persona. Knowledge Assistants and Supervisor Agents. No consumer accesses raw pipeline tables directly. Metric view creation automated, including new KPIs. | All metric views in Unity Catalog with RLS. Genie benchmark: ≥ 50 business questions answered correctly. Existing dashboards migrated with side-by-side validation. No consumer accesses raw tables. Additionally: (a) Genie self-service rate: ≥ 30% of standard analytical queries resolved via Genie without analyst intervention; (b) HEART Engagement baseline: usage analytics instrumentation deployed and tracking weekly active users, session length, and feature interaction depth across AI/BI Dashboards and Genie Spaces. Sensitive data classified and protected (CDRB I03). Full audit trail (CDRB I04). Least-privilege access confirmed (CDRB I01). |

| # | Deliverable | Description | Measurable Success Criteria |
| --- | --- | --- | --- |
| D6 | KPI Harmonization & Sign-Off | Complete Latin American KPI inventory harmonized across all four BUs: code, kind, formula, filters, adjustments, unit list, currency list, calendars, additivity, owner, and version. Formal sign-off from business owners in all four markets. | 100% of KPIs in scope have a registered definition in the KPI registry with owner, formula, and version. Zero KPI definition conflicts remain unresolved. Parallel-run reconciliation confirms new pipeline KPI outputs match legacy GCP within agreed tolerance, KPI-by-KPI, market-by-market, month-by-month (CDRB J03). Legacy defects tracked and resolved (CDRB J04). For every KPI in scope, the Supplier shall populate a KPI Dictionary entry containing, at minimum, the following 25 fields per KPI per market (based on the MONDELEZ KPI Dictionary template): (1) Global KPI ID — unique identifier for the KPI across all markets; (2) Global KPI Business Name — the standard KPI name used globally; (3) Market KPI ID — unique identifier for the market-specific instance of the KPI; (4) Market KPI Business Name — the KPI name as used locally in each market; (5) Local Language Synonyms and Search Tags — alternative names, abbreviations, and local-language terms to enable conversational search and cross-market alignment (minimum 3 per KPI per market); (6) Region — MONDELEZ region (e.g. Latin America); (7) Business Unit — MONDELEZ Business Unit (e.g. Mexico, Brazil); (8) Cluster — market cluster grouping; (9) Market — commercial market; (10) Data Steward — named individual accountable for the KPI definition and quality; (11) Technical KPI Name — the identifier used in the data platform code; (12) Unit of Measure — the base unit in which the KPI is expressed (e.g. local currency, kilograms, cases); (13) Source Data Fields — the specific data fields and tables that feed the KPI; (14) Source Data Lineage Description — narrative explaining the end-to-end data flow from source system to KPI output; (15) Technical Calculation Definition — the complete calculation logic including filters, formula, and adjustments; (16) Global Alignment Confirmation — statement confirming whether the market calculation aligns with the global KPI definition, with explanation of any discrepancies; (17) Filter Description — plain-language explanation of which records are included or excluded and why; (18) Formula Description — plain-language explanation of how the KPI value is calculated; (19) Adjustment Description — plain-language explanation of any post-calculation corrections or data quality adjustments applied; (20) Calendar Grain — the lowest time granularity at which the KPI is calculated (e.g. day, week, month); (21) Customer Grain — the lowest customer hierarchy level at which the KPI is calculated (e.g. store, ship-to, sold-to); (22) Product Grain — the lowest product hierarchy level at which the KPI is calculated (e.g. SKU, brand); (23) Aggregation Method — how the KPI is combined across dimensions (e.g. sum, average, count distinct) and whether it is additive, semi-additive, or non-additive; (24) Pipeline Procedure Name — the name of the data pipeline job that produces the KPI; (25) Output Table — the target table where the calculated KPI result is stored |
| D7 | Data Quality Framework | End-to-end automated data quality monitoring covering every pipeline stage. DQ expectation rules at every quality gate. Automated alerts on threshold breaches. Reconciliation dashboard tracking DQ pass/fail rates by domain, market, and layer. The Supplier shall provide the Data Governance team with all DQ rule definitions, threshold configurations, and quality gate specifications implemented in the Databricks pipeline, following the Data Governance team's process for Ataccama DQ rule registration. The Supplier is not required to operate Ataccama directly — the Data Governance team is responsible for Ataccama registration using the information provided by the Supplier. | Quality check before every load (CDRB E03). Deterministic de-duplication (CDRB E04). Re-run safety confirmed via automated tests (CDRB E05). Incremental processing by default with shared watermark (CDRB E01). Loads are all-or-nothing (CDRB E02). DQ dashboard deployed showing pass/fail rates by domain, market, and pipeline layer with drill-down capability. All DQ rule definitions, thresholds, and quality gate specifications documented and provided to the Data Governance team in the format required for Ataccama registration. Data Governance team confirms receipt and completeness of the DQ information package. |

| # | Deliverable | Description | Measurable Success Criteria |
| --- | --- | --- | --- |
| D8 | Jobs Monitoring, Alerts & Operational Dashboards | Comprehensive pipeline observability: run logs per procedure, automated failure and SLA-breach alerts, runtime tracking, and operational dashboards for real-time and historical pipeline status. | Complete run logs recording status, rows read/written, watermark position, duration, and quality gate results for every procedure (CDRB K01). Alerts configured for all failure and warning conditions with zero reliance on user-reported discovery (CDRB K02). Jobs Monitoring Dashboard deployed showing real-time execution status, runtime per procedure, watermark positions, and SLA compliance. Runtime budgets verified: each procedure ≤ 30% reduction from current pipeline, full chain 30% reduction from current pipeline, publish layer ≤ 30% reduction from current pipeline (CDRB G01). |
| D9 | Cost Monitoring & Budget Tracking | Compute cost tracking tagged by layer, market, and procedure. Cost monitoring dashboards and Genie-queryable cost views. Budget adherence reporting and cost anomaly detection. Unified cost-tracking dashboard covering Databricks compute, storage, Jobs API calls, and per-pipeline resource consumption. Baseline established in Phase 2, tracked monthly with trend analysis. The cost baseline shall additionally include: (a) TCO structure: Costs categorised into Run (operational/support) vs Change (enhancement/evolution) to enable ongoing Run vs Change ratio tracking per POET financial governance; (b) Platform cost apportionment: D&A platform costs apportioned to MATRIX AI documented using controllability and consumption metrics, providing the foundation for ongoing shared-cost allocation; (c) Product TCO formula: Direct Costs (MDLZ Loaded Costs + Service Provider + License Costs) + Apportioned Platform Costs, baselined at Go-Live to serve as the financial anchor for POET Product Council reporting. | Cost tags applied to all pipeline jobs by layer, market, and procedure (CDRB G07). Cost Monitoring Dashboard deployed showing cost per run, daily/weekly/monthly trends, budget utilization, and anomaly detection. Genie-queryable cost views operational. Processing proportional to change confirmed (CDRB G03). No slow patterns in critical paths (CDRB G05). Storage maintenance automated (CDRB G06). Final cost baseline report delivered: cost per market/month, per layer, and projected annual run cost. |
| D10 | Operational Runbook & Re-Run Playbook | Documented runbook for every job and failure scenario: single-market re-run, parameter-driven backfill, load rollback, known-issue handling, and escalation procedures. Re-run playbook for market-scoped reprocessing. | Operational runbook published and reviewed by at least one team member not involved in writing it (CDRB K03). Single-market re-run validated in production: failed market re-executed in isolation without affecting other markets, with compute cost proportional only to the failed market. Parameter-driven backfill validated. Load rollback validated. Data lineage visible end-to-end in Unity Catalog (CDRB K04). |
| D11 | Global Scalability Proof | Configuration-only onboarding ofsynthetic market test (CDRB H01) with fictional market "ZZ" (Canada or USA) demonstrating end-to-end configuration-only onboarding. | Synthetic market "ZZ" onboarded via configuration rows only, passes all 8 pipeline blocks end-to-end with zero code changes, confirmed by automated code diff (CDRB H01). Volume scalability: 3x data volume within 1.5x runtime (CDRB H02). Market isolation confirmed: concurrent multi-market runs with no shared temporary objects (CDRB H03). Flexible reprocessing confirmed for any date range via parameters (CDRB H04). New market through configuration only with parallel-run reconciliation within tolerance. |
| D12 | Global Scalability Playbook | Mandatory deliverable per Appendix C: architecture overview, configuration-only onboarding checklist, synthetic market test evidence, real market onboarding evidence, handling unique KPIs, effort estimates, governance, and 20 validated onboarding examples. | All Playbook sections complete and CDRB-reviewed (per Appendix C). 20 validated configuration-only onboarding examples documented with automated code-diff evidence. Effort estimation model endorsed by MONDELEZ project leadership. Governance model approved by MONDELEZ D&A leadership and Global D&A Product team. Playbook published and accessible to all stakeholders. |

| # | Deliverable | Description | Measurable Success Criteria |
| --- | --- | --- | --- |
| D13 | Testing & Reconciliation Evidence | Comprehensive testing package: unit tests for all shared functions, golden-data tests per procedure, parallel-run reconciliation against legacy GCP, and legacy defect resolution. | Unit test suite for every shared function (CDRB J01). Golden-data test per procedure with known inputs and verified outputs (CDRB J02). Parallel-run reconciliation passing for all KPIs, all markets, all months within agreed tolerance (CDRB J03). All identified legacy defects tracked with resolution status (CDRB J04). Automated re-run test passing in CI pipeline (CDRB E05). |
| D14 | Documentation & Governance Artifacts | Complete technical and business documentation: design notes, waiver register, KPI registry/dictionary in sync, legacy procedure mapping, and data lineage documentation. The Supplier shall additionally provide the Data Governance team with a complete metadata package covering all MATRIX AI datasets, tables, KPI definitions, data lineage maps, data classification tags, and DQ rule inventories, in the format required by the Data Governance team for Ataccama registration. This metadata package is a Supplier deliverable obligation; Ataccama registration is the responsibility of the Data Governance team. | Design note approved before build for every Tier 1 component (CDRB L01). All waivers explicit and time-bound (CDRB L02). Registry and dictionary in sync with automated drift check (CDRB L03). Every legacy procedure mapped to its replacement with decommission schedule (CDRB L04). Complete metadata package provided to the Data Governance team covering: (a) all dataset and table metadata descriptions; (b) data lineage from source to KPI output; (c) data classification and sensitivity tags; (d) all DQ rule definitions and thresholds; and (e) KPI registry export. Data Governance team confirms receipt and completeness of the metadata package for Ataccama registration. |
| D15 | Training Materials & Enablement Program | Complete training package: Training Needs Assessment, custom MONDELEZ training modules, Databricks Academy and Pluralsight learning paths, hands-on lab environments, user guides, quick-reference cards, video walkthroughs, and training portal. Train-the-Trainer certification program and end-user training delivery support. | Training materials cover all user personas (technical and business). Train-the-Trainer program, hands-on lab environments, and end-user training delivery for all four BUs completed: designated MONDELEZ trainers certified and capable of delivering training independently. Success criteria additionally include: (a) Training satisfaction: ≥ 4.0/5.0 average rating from post-training surveys across all BUs; (b) Adoption readiness: ≥ 80% of identified target users have completed onboarding training before Go-Live; (c) Self-sufficiency: ≥ 60% of trained users demonstrate ability to independently navigate AI/BI Dashboards and formulate Genie queries during hands-on assessment. Training portal published with Databricks Academy paths, Pluralsight courses, and all custom materials. Training effectiveness feedback collected and gaps addressed before go-live. |
| D16 | Delivery Management Services | Consolidated delivery management across both workstreams: planning, scheduling, risk and opportunity management, status reporting per the governance model (Daily Scrum, Weekly 4-Box, Monthly Leadership Update), and post-phase retrospective and lessons learned. | Biweekly consolidated status reports delivered on schedule. RAID log maintained and current. All milestone dates met or formally re-baselined via change control. Post-phase retrospective conducted and improvement actions documented for product continuity. |

5.1 KPI Dictionary Completeness

For every KPI in scope, the Supplier shall populate a KPI Dictionary entry containing, at minimum, the following 25 fields per KPI per market, based on the MONDELEZ KPI Dictionary template. Those are must have information, but should consider potential increase of 20% additional fields.

| # | Field | Scope | Description | Purpose | Example |
| --- | --- | --- | --- | --- | --- |
| 1 | Global KPI ID | GLOBAL | Unique identifier for the KPI across all markets | Registry key — single reference ID across all markets and regions | 100083 |
| 2 | Global KPI Business Name | GLOBAL | The standard KPI name used globally | Human-readable canonical name that is the single global reference for this metric | Month Closure Sell-Out |
| 3 | Market KPI ID | BU | Unique identifier for the market-specific instance of the KPI | Identifies each market's own implementation of the global KPI | 100083_0000001 |
| 4 | Market KPI Business Name | BU | The KPI name as used locally in each market | Local market name — may differ from the global canonical name | Month Closure Sell-Out |
| 5 | Local Language Synonyms and Search Tags | BU | Alternative names, abbreviations, and local-language terms for this KPI | Enables conversational search (Genie) and cross-market alignment in local language — minimum 3 per KPI per market | Cierre de Mes; Cierre Mensual; Cierre Periodo |
| 6 | Region | BU | MONDELEZ region | Groups KPI instances by region for cross-market governance | LA |
| 7 | Business Unit | BU | MONDELEZ Business Unit owning this KPI instance | Identifies the organisational unit accountable for this KPI | Mexico |
| 8 | Cluster | BU | Market cluster grouping within the region | Supports regional grouping and cross-cluster comparisons | Mexico |
| 9 | Market | BU | Commercial market for this KPI instance | Identifies the specific commercial market | Mexico |
| 10 | Data Steward | BU | Named individual accountable for the KPI definition and quality | Ensures a single person is responsible for this KPI's accuracy and governance (CDRB F07) | (to be assigned per BU) |
| 11 | Technical KPI Name | BU | The identifier used in the data platform code | Links the business dictionary entry to the code implementation | calc_gross_profit_nr |
| 12 | Unit of Measure | BU | The base unit in which the KPI is expressed | Prevents cross-market unit mismatches — e.g. local currency vs. kg vs. cases (CDRB F01) | Local Currency (MXN); KG; Cases |
| 13 | Source Data Fields | BU | The specific data fields and tables that feed this KPI | Column-level traceability from source to KPI output — enables full audit trail (CDRB K04) | v_fct_detail_month_closure_mx.sell_out |
| 14 | Source Data Lineage Description | BU | Narrative explaining the end-to-end data flow from source system to KPI output | Plain-language lineage story for business users and Ataccama registration | SAP VBRP provides invoice-level data... flow: source > DC > DS > Metrics > KPI |
| 15 | Technical Calculation Definition | BU | The complete calculation logic including filters, formula, and adjustments | Authoritative technical specification — the single source of truth for how this KPI is calculated | Filter: ... > Formula: SUM(SAFE_CAST(...)) > Adjustments: same load pattern |
| 16 | Global Alignment Confirmation | BU | Statement confirming whether the market calculation aligns with the global KPI definition | Flags harmonisation gaps — where answer is No, a business reason must be provided and resolved before Gate 3 | Yes / No + explanation |
| 17 | Filter Description | BU | Plain-language explanation of which records are included or excluded and why | Business-readable filter logic for users and Genie | Select eligible records where source matches sell_in criteria |
| 18 | Formula Description | BU | Plain-language explanation of how the KPI value is calculated | Business-readable formula narrative — avoids reliance on technical code to understand the metric | Sum all qualifying records for the reporting period |
| 19 | Adjustment Description | BU | Plain-language explanation of any post-calculation corrections or data quality adjustments applied | Documents exceptions and corrections transparently for governance and audit | Full replace per pipeline run — prior values deleted before insert |
| 20 | Calendar Grain | BU | The lowest time granularity at which the KPI is calculated | Drives aggregation logic and prevents temporal accuracy errors | Day; Week; Month |
| 21 | Customer Grain | BU | The lowest customer hierarchy level at which the KPI is calculated | Prevents over-aggregation errors across customer hierarchies | Store; Ship-To; Sold-To |
| 22 | Product Grain | BU | The lowest product hierarchy level at which the KPI is calculated | Ensures correct product-level roll-up and prevents mix-level errors | SKU; Brand |
| 23 | Aggregation Method | BU | How the KPI is combined across dimensions — e.g. sum, average, count distinct | Additivity declaration (CDRB F05) — prevents incorrect cross-dimensional aggregation | Sum (additive across time and geography); Count Distinct (non-additive) |
| 24 | Pipeline Procedure Name | BU | The name of the data pipeline job that produces this KPI | Links the dictionary to the code — required for CDRB F08 auto-generation compliance | sp_ds_load_t_fct_otc_kpi_la |
| 25 | Output Table | BU | The target table where the calculated KPI result is stored | Enables output traceability, validation, and downstream consumption tracking | amer_p_matrix_mx.t_agg_kpi_otc_mx |

Acceptance Gate

All 25 fields above shall be fully populated per KPI per market before any KPI is registered in the KPI Calculation Engine (D4) or published to the Semantic Layer (D5). Incomplete entries are not eligible for CDRB F07 sign-off (named data steward registered) or CDRB F08 sign-off (dictionary auto-generated from code).

Governing Rules

(a) Auto-generation: The KPI Dictionary shall be auto-generated from the KPI registry code — not manually maintained (CDRB F08). Any code change affecting a KPI must update the registry in the same pull request, and the Dictionary is regenerated automatically.

(b) Named Data Steward: Every KPI must have a named Data Steward confirmed before Gate 2 sign-off (CDRB F07).

(c) Versioning: The Dictionary shall be versioned. Any change to a KPI definition must be traceable to a specific version with date, author, and change description, consistent with the KPI registry drift check (CDRB L03).

(d) Global Alignment: Global Alignment Confirmation indicates “No”, the discrepancy shall be documented with the business reason, reviewed by the MONDELEZ Product Lead, and resolved or explicitly accepted before Gate 3 (User Testing Complete).

(e) Ataccama handoff: The Supplier shall provide the completed KPI Dictionary to the MONDELEZ Data Governance team in the format required for Ataccama registration). The Data Governance team is responsible for Ataccama registration; the Supplier is responsible for providing complete, accurate, and timely Dictionary information.

(f) Genie Readiness: Local Language Synonyms and Search Tags shall include a minimum of three local language synonyms per KPI per market before the Genie Space for that market is deployed in Phase 4. These synonyms are the primary mechanism by which Genie recognizes business questions across markets and languages.

Responsible Party:

| Deliverable | Role Responsible | Buyer | Seller |
| --- | --- | --- | --- |
| D1: Pipeline Architecture | Architect, Data Engineer, GenBI | Assist | Primary |
| D2: Core Domain Model | Architect, Data Engineer | Assist | Primary |
| D3: Configuration Layer | Architect, Data Engineer | Assist | Primary |
| D4: KPI Engine & Registry | Architect, Data Engineer, GenBI | Assist | Primary |
| D5: Semantic Layer & Consumption | GenBI, Architect | Assist | Primary |
| D6: KPI Harmonization inventory | Architect, Data Engineer | Primary | Assist |
| D6: KPI Harmonization naming and business logics | BU Business Owners | Primary | Assist |
| D7: Data Quality Framework | Data Engineer, Architect | Assist | Primary |
| D8: Jobs Monitoring & Alerts | Data Engineer | Assist | Primary |
| D9: Cost Monitoring | Data Engineer | Assist | Primary |
| D10: Runbook & Re-Run Playbook | Data Engineer, PM | Assist | Primary |
| D11: Global Scalability Proof | Architect, Data Engineer | Assist | Primary |
| D12: Global Scalability Playbook | Architect | Assist | Primary |
| D13: Testing & Reconciliation | Data Engineer (build) / Testing Lead (validate) | Shared | Primary |
| D14: Documentation & Governance | Architect, Data Engineer | Assist | Primary |
| D15: Training & Enablement | Change Mgmt (strategy) / Seller (content build) | Primary | Primary |
| D16: Delivery Management | Delivery Lead | Assist | Primary |

*The Party with “Primary” responsibility shall have the obligation of completing that task or Deliverable and directing the Party with “Assist” responsibility. **The Party with “Assist” responsibility shall assist the Party with “Primary” responsibility.

- Approach and Activities

| Cadence | Activity | Duration | Owner | Lingaro Role | MONDELEZ Role | Output |
| --- | --- | --- | --- | --- | --- | --- |
| Daily | Stand-Up (per business process) | 10 min, virtual | Partner Delivery Lead | Report progress on assigned tasks, raise blockers, confirm deliverable status per business-process track | Confirm priorities, unblock dependencies, provide decisions on data or business-rule questions within 24 hours | Actions log updated; blockers escalated same day; daily progress confirmed per track |
| Weekly | CDRB Review | 60 min, structured review | Architecture Enabler | Submit procedures and configuration changes for review; present evidence against CDRB criteria; clear PR review queue; update CDRB section statuses | Participate in review for KPI accuracy, business-rule correctness, and data governance items; approve or request changes on business-owned criteria | CDRB section statuses updated (In Progress / Approved / Action Required); review decisions logged; quality gate evidence archived |
| Weekly | 4-Box Status Report | 90 min, PMO template | Partner Delivery Lead | Prepare and deliver consolidated status report covering scope, timeline, cost, and quality; update RAID log; present accomplishments, upcoming work, risks, and dependencies | Review status, provide timely decisions, resolve escalations, ensure MONDELEZ stakeholders participate when their input is required | Published 4-Box pack; RAID log current; decisions and change log updated; escalation list for Product Leadership Update |
| Mid-Month | Product Leadership Update (offline) | Email distribution | MDLZ D&A Lead + Partner Delivery Lead | Prepare executive update summarizing delivery progress, key risks, resource status, and items requiring leadership input; distribute 48 hours ahead | Review update, provide written decisions on escalations, confirm resource commitments, approve scope changes within threshold | Decisions documented with owners; escalations resolved or elevated to monthly Product Council / Platform Council; resource actions confirmed |
| Monthly | Executive Summary | 60 min, meeting + written report | Partner Delivery Lead + MDLZ D&A Lead | Deliver executive summary with milestone progress, investment tracking, CDRB quality gate status, cost baseline vs. actuals (including Run vs Change categorization from Phase 3 onward), risk and opportunity register, and product roadmap update aligned to Product Council reporting cadence | Provide strategic direction, approve major scope or timeline changes, endorse phase gates, confirm priorities for next month | Executive report distributed to Senior Leadership; investment tracking updated; milestone and gate status confirmed; risk register reviewed |

Code Design Review Board (CDRB)

- The CDRB will serve as the technical quality assurance forum for all deliverables. The CDRB reviews evidence against CDRB criteria (Sections A–L) and provides a quality recommendation (Recommend Approval / Recommend Revision / Escalate). The MONDELEZ Product Lead retains sole acceptance authority for all deliverables, informed by the CDRB recommendation. The Lingaro Project Lead is accountable for ensuring all CDRB evidence is complete and submitted; the MONDELEZ Product Lead is accountable for the accept/reject decision.

- CDRB section sign-off indicates that the technical quality criteria have been reviewed and recommended for acceptance by the CDRB forum. Formal deliverable acceptance at each phase gate is the sole authority of the MONDELEZ Product Lead (or designated delegate), consistent with the POET RACI where the Product Manager holds the 'A' (Accountable) for deliverable acceptance.

- CDRB recommendation of approval across all applicable sections constitutes the technical Definition of Done for each deliverable. The technical Definition of Done is a necessary but not sufficient condition for deliverable acceptance. Formal acceptance requires the MONDELEZ Product Lead's written approval, consistent with the POET RACI model.

- CDRB recommendation of approval across all applicable sections constitutes the technical Definition of Done for each deliverable. The technical Definition of Done is a necessary but not sufficient condition for deliverable acceptance. Formal acceptance requires the MONDELEZ Product Lead's written approval, consistent with the POET RACI model

- CDRB section statuses updated (In Progress / Recommended for Approval / Action Required); quality recommendation logged; evidence archived. Formal acceptance decision recorded by MONDELEZ Product Lead at Sprint Review or Phase Gate

Cross-Stream Coordination: Given MATRIX AI's cross-stream program nature, the following additional governance touchpoints apply:

- Product Council alignment: The MONDELEZ Product Lead shall ensure MATRIX AI deliverables impacting each Product Stream (MSE, Supply Chain) are surfaced at the relevant monthly Product Council for backlog alignment and priority confirmation;

- Platform Council alignment: The D&A Platform Line Lead (or delegate) shall be invited to the Fortnightly Design Authority to ensure platform architecture decisions align with the broader D&A Platform roadmap;

- Cross-stream dependency review: A monthly 30-minute dependency review shall be conducted to surface and resolve cross-stream data dependencies (e.g., master data hierarchies shared across OTC and Inventory, FX rates shared across all domains).

Data Governance

- The Supplier shall provide into monthly update the Data Governance Tooling Alignment Report to the MDLZ Data Governance forum, covering:

(i) Ataccama integration status per function (Catalog, DQ, Lineage) — connected / structured-for-import / not started;

(ii) inventory of any interim accelerators in use, with sunset timeline;

(iii) metadata completeness metrics (% of datasets catalogued, % of DQ rules registered, % of lineage mapped); and

(iv) any tooling changes proposed, for Data Governance forum approval before implementation.

6.1 POET Governance Integration

The MATRIX AI program governance operates within the POET three-tier framework as follows:

Tier 1 — Strategic: Investment decisions and portfolio prioritization affecting the MATRIX AI program or any of its enabled data products are escalated to the Investment Management Committee (quarterly) via the Product Group Manager through the Product Stream Lead. Enterprise-level technology strategy is set at the Quarterly MLT Meeting.

Tier 2 — Functional: Program-level outcomes, product readiness, roadmap alignment, and Run vs Change allocation are reported to the Product Council (monthly) and Platform Council (monthly); cross-product dependencies are resolved at the Quarterly Planning Meeting (quarterly); portfolio funding and prioritization are governed by the MDS Strategic Portfolio Board (monthly).

Tier 3 — Operational: Daily Stand-Ups, Weekly CDRB Reviews, and Sprint ceremonies constitute the operational governance layer. Architectural decisions are routed through the Technical Design Authority (weekly or ad-hoc).

The governance cadence defined in Section 6 governs the internal delivery management between Buyer and Seller. In addition, the MATRIX AI program — which enables multiple analytical data products across Product Streams and the D&A Platform Line — shall be integrated into the MONDELEZ POET governance framework as follows:

(a) Product Council / Platform Council: The MONDELEZ Product Lead shall present MATRIX AI program status, the readiness of enabled data products (e.g., OTC Analytics, Market Share Analytics, Inventory Analytics), cross-product dependencies, and risks at the monthly Product Council (for product-specific outcomes) and Platform Council (for shared platform components) as appropriate.

(b) Quarterly Planning Meeting: MATRIX AI delivery milestones, dependencies, and resource commitments shall be surfaced during the quarterly QPM to ensure alignment with enterprise priorities.

(c) Technical Design Authority & Architecture Review Board: significant architectural decisions (e.g., pipeline pattern changes, new consumption patterns, security model changes, Databricks workspace design) shall be presented to the Technical Design Authority (weekly or ad-hoc) for technical solutioning. Architecture decisions with enterprise-wide implications — including platform patterns intended for reuse across Product Streams — shall be escalated to the Architecture Review Board - ARB (fortnightly) for guardrail validation and exception approval. Detailed technical documentation (ARB templates) shall be prepared as part of Mondelēz methodology.

(d) Escalation Path: Escalations that cannot be resolved at the weekly 4-Box session shall follow the POET escalation hierarchy: Partner Delivery Lead → MONDELEZ Product Lead → Product Group Manager → Product Stream Lead → Investment Management Committee (for decisions exceeding defined thresholds). This replaces ad-hoc escalation mechanisms with the structured POET governance path

(e) MDS Strategic Portfolio Board: The MATRIX AI program shall be represented in the MDS Strategic Portfolio Board (monthly) for portfolio prioritization, capacity management, and funding decisions affecting the program or any of its enabled data products. The Product Lead shall provide TCO tracking, value realization metrics, and cross-product dependency status as inputs to the Board.

(f) Data Governance Committee: Given MATRIX AI's role in establishing the KPI Registry as the single source of truth and the configuration-driven data harmonization layer, the MONDELEZ Data Governance representative shall ensure that KPI definitions, data quality standards, master data hierarchies, and configuration governance are surfaced at the monthly Data Governance Committee for alignment with enterprise data governance standards.

(e) Data Governance Alignment: The Supplier shall participate in MONDELEZ Data Governance forums as directed by the Data Governance team, including periodic reviews of metadata completeness, DQ rule coverage, and data lineage documentation for Ataccama registration. The Supplier's obligation is to follow the Data Governance team's processes and provide all required information; the Data Governance team is responsible for Ataccama operations and governance decisions.

- Assumptions. The following assumptions have been made in developing this SOW. If any of these assumptions are not accurate, the schedule and/or costs may be impacted.

| Assumptions | Description |
| --- | --- |
| Working Days | Services will be provided on business days, Monday through Friday, excluding applicable public holidays, planned paid time off, and unplanned sick leave. The Supplier team is based in Poland and India, serving a product program that operates across Latin America (Mexico, Wacam, Brazil, Southern Cone). Given the significant time-zone difference (6 to 8.5 hours depending on season and market), the Supplier commits to the following extended working-hour schedule to ensure adequate real-time overlap with MONDELEZ stakeholders in Latin America: - Monday: up to 6:00 PM local time (Poland CET/CEST; India IST) - Tuesday through Thursday: up to 8:00 PM local time (Poland CET/CEST; India IST) - Friday: up to 6:00 PM local time (Poland CET/CEST; India IST) This schedule is a baseline commitment for the duration of the engagement, not subject to ad-hoc negotiation. It ensures a minimum daily overlap window with Latin American business hours for Daily Stand-Ups, CDRB reviews, workshops, KPI harmonization sessions, and UAT support. In the event of critical incidents, production failures, go-live preparations, or time-sensitive escalations, the Supplier team shall demonstrate flexibility to work extended hours beyond the schedule above, including evenings and, if necessary, weekends, until the issue is resolved. This flexibility is inherent to the fixed-price nature of this engagement and shall not result in additional fees or change orders. |
| Work Location | Work will be delivered remotely from Poland, India, and Mexico according to resource allocation. On-site travel to Latin American locations (Mexico, Brazil, Argentina, Colombia, Peru or Costa Rica) is required for key milestone events: Blueprint Workshop, UAT kick-off, Go-Live, and critical escalation meetings as agreed between the parties. All travel and accommodation costs are included in the fixed-price budget. No additional travel charges shall apply unless the Buyer requests travel beyond the agreed schedule, in which case costs will be pre-approved in writing. |
| Resource Allocations | Resources are assigned to the MATRIX AI product program on a full-time basis. 1 FTE is the equivalent of 8 hours per standard working day, subject to the extended working-hour schedule defined in the Working Days assumption above. The Supplier is responsible for ensuring sufficient resource capacity to meet all milestone dates and deliverable commitments. Where a workload gap is identified against committed capacity, the Supplier shall augment resources at its own cost, consistent with the fixed-price nature of this engagement. No overtime, additional compensation, or change orders shall apply for effort required to deliver the agreed scope within the agreed timeline. |
| Resource Utilization | The Supplier is responsible for planning and managing the utilization of its assigned resources to meet deliverable commitments and milestone dates. MONDELEZ is not responsible for managing the Supplier's resource allocation, workload balancing, or capacity planning. If the Supplier's resources are underutilized due to Buyer dependencies (e.g., delayed environment access, pending business decisions), the Supplier shall notify the Buyer in writing within 5 business days, and the parties shall agree on a revised timeline for the affected deliverables. |
| Product Delivery Accountability | The Supplier is responsible for the delivery of all deliverables (D1 through D16) within the agreed timeline, budget, and scope as defined in this SOW. This is a fixed-price product build engagement; the Supplier assumes full accountability for planning, executing, and delivering the agreed scope to the measurable success criteria, in alignment with the MONDELEZ POET product delivery framework. Failure to deliver shall be governed by the Fees at Risk provisions and the termination clauses of this SOW. |
| Resource Retention | The Supplier shall maintain continuity of key resources (Senior Architect, Lead Data Engineer, Delivery Lead) throughout the full duration of this SOW. If any key resource becomes unavailable for any reason, the Supplier shall: (a) notify MONDELEZ in writing within 3 business days; (b) provide a replacement of equal or greater skill level within 10 business days; and (c) execute a knowledge transfer at the Supplier's cost with no impact to milestone dates. Voluntary reassignment of key resources to other Supplier engagements is not permitted without MONDELEZ prior written consent. |
| Resource Replacement | If a resource must be replaced, the Supplier shall propose a replacement with equivalent or superior qualifications within 10 business days. MONDELEZ reserves the right to interview and approve any replacement resource before assignment. The Supplier shall execute and fund knowledge transfer between the departing and incoming resource at no additional cost to MONDELEZ. If the replacement causes a delay to any milestone, the Supplier shall augment capacity at its own cost to recover the schedule. MONDELEZ may request replacement of any resource for cause (performance, conduct, or skill mismatch) with 5 business days written notice. Performance-Based Replacement: If MONDELEZ requests the replacement of a resource due to underperformance, the Supplier shall, in addition to providing a qualified replacement within 10 business days, assign one additional resource of equivalent or superior skill level to the project for a minimum period of three (3) months. This additional resource shall be provided at the Supplier's sole cost with no additional fees to MONDELEZ, and is intended to recover any work delayed or quality shortfall caused by the underperforming resource. The three-month period begins on the date the additional resource starts working on the project. At the end of the three-month period, the Supplier may remove the additional resource only if all affected milestone dates are back on track and MONDELEZ confirms in writing that the recovery is satisfactory. |
| Tasks Allocation | The Supplier is responsible for planning, assigning, and managing tasks within its team to deliver the agreed deliverables. MONDELEZ provides business requirements, priorities, and acceptance decisions. Day-to-day task allocation, sprint planning, and technical work assignment are the Supplier's responsibility. MONDELEZ retains the right to review progress and redirect priorities through the governance cadence defined in Section 6. |
| Task Prioritization | MONDELEZ defines business priorities and the sequence in which deliverables and business domains are addressed. The Supplier is responsible for translating business priorities into technical execution plans, sprint backlogs, and resource assignments. Any conflict between business priorities and technical dependencies shall be resolved through the Weekly 4-Box governance session. The Supplier shall proactively flag priority conflicts that may impact milestone dates. |
| Knowledge transfer | All knowledge transfer costs arising from resource replacement are the responsibility of the Supplier, regardless of whether the replacement was initiated by the Buyer or the Supplier. The only exception is if MONDELEZ requests replacement of a resource without cause and outside the resource replacement process defined above, in which case the parties shall agree on a reasonable knowledge transfer period not to exceed 10 business days. The Supplier shall provide structured knowledge transfer to MONDELEZ as part of the fixed-price deliverables, including: (a) technical documentation of the complete solution architecture, pipeline design, and configuration framework (Deliverable D14); (b) training materials and Train-the-Trainer program for all user personas (Deliverable D15); (c) operational runbook and re-run playbook for the support team (Deliverable D10); and (d) formal Transition-to-Support handover during Phase 5 Hypercare. Knowledge transfer is a contractual obligation, not optional. The Supplier shall execute knowledge transfer following MONDELEZ's established methodology and transition framework, delivering structured handover sessions to both the MONDELEZ Application Management Services (AMS) team and the MONDELEZ Product team. This includes: (a) architecture and pipeline walkthrough sessions with the AMS team covering day-to-day operations, monitoring, alert response, incident management, re-run procedures, and configuration maintenance; (b) product knowledge sessions with the Product team covering the KPI registry governance model, configuration-driven market onboarding process, CDRB quality framework application, and the Global Scalability Playbook; (c) shadowed support period where the Supplier works alongside the AMS and Product teams during Hypercare to validate readiness; and (d) formal sign-off from both the AMS and Product team leads confirming that knowledge transfer is complete and the teams are capable of independent operation. The Supplier shall not be released from Hypercare obligations until both sign-offs are obtained. |
| Access | MONDELEZ will provide accesses, accounts, licenses, and privileges for the allocated resource to perform expected activities before the start date of engagement |
| Coordination | MONDELEZ is responsible for managing the work conducted by its employees and other vendors. |
| Travel Costs | All planned travel and accommodation costs are included in the fixed-price budget. This covers key milestone events as defined in the Work Location assumption. Any travel requested by MONDELEZ beyond the agreed schedule shall require prior written approval, and costs shall be invoiced at actuals with receipts. |
| Business / MONDELEZ Team | MONDELEZ shall designate a Business Product Owner and appropriate business representatives for each relevant business line. The Business Product Owner, supported by the respective business representatives, shall serve as the primary point of contact for the assigned Project Team and shall be accountable for coordinating decision-making, project / product activities, backlog prioritization, and the review and acceptance of project / product deliverables. The designated business representatives shall have sufficient knowledge, authority, and mandate to make, or obtain without undue delay, all material business decisions relating to their respective business lines. The Business Product Owner and business representatives shall remain reasonably available and responsive throughout the engagement to address queries, provide required inputs, resolve business matters, and facilitate the timely review and acceptance of project results. |
| Data Product & Engineering (DP&E) | MONDELEZ shall ensure that the Data Product & Engineering (DP&E) team is available to the Supplier for core domain and data product alignment throughout the engagement. Specifically: (a) DP&E shall provide access to the current canonical core domain entity definitions, data models, and global KPI pre-calculation standards; (b) DP&E shall designate a technical counterpart to participate in the core domain fit/gap analysis during Phase 1 and to determine the delivery model for each core domain entity — whether the Supplier consumes and validates DP&E-built entities, or whether the Supplier builds under DP&E technical direction; (c) DP&E shall review and approve the Supplier's core domain work (D2) — whether consumed or built — for consistency with global canonical core domain standards, before Gate 1 sign-off (working prototype) and Gate 2 sign-off (migration); (d) where DP&E canonical core domain entities are not yet available at the time the Supplier requires them, DP&E shall determine whether the Supplier builds interim entities under DP&E technical direction (structured for future convergence with the global canonical model) or waits for DP&E delivery. If DP&E availability or deliverables are delayed beyond the agreed timeline, the Supplier shall notify MONDELEZ in writing within 5 business days, and the parties shall agree on a revised approach for the affected core domain components through the Weekly 4-Box governance session. |
| Data Governance Team (Ataccama) | MONDELEZ shall ensure that the Data Governance team is available to the Supplier for data governance alignment throughout the engagement. Specifically: (a) the Data Governance team shall provide the Supplier with the required formats, templates, and process documentation for metadata submission, DQ rule registration, data lineage documentation, and dataset cataloguing in Ataccama; (b) the Data Governance team shall designate a counterpart to receive metadata and DQ information from the Supplier and to confirm completeness at each phase gate; (c) the Data Governance team shall provide timely feedback on submitted metadata packages to allow the Supplier to address any gaps before phase gate reviews. The Supplier is not required to perform any work directly in Ataccama. The Supplier's obligation is limited to following the Data Governance team's processes and providing all required information in the agreed format and cadence. |
| Software licenses | Supplier will not use, provide access to, or rely upon any software licenses owned by the Supplier for the performance of Services under this SOW. All tools, accounts, environments, and licenses required for service delivery will be provided solely by Buyer. |

7.1 POET Role Alignment: For the duration of this engagement, the parties acknowledge that this SOW operates within the MONDELEZ POET Product-Oriented Enterprise Transformation operating model. The following role mapping applies:

(a) The MONDELEZ Product Lead (Buyer SPOC) serves as the MDS Product Manager accountable for product vision, backlog prioritization, and outcome delivery;

(b) The Supplier Delivery Lead (Seller SPOC) operates as the delivery partner integrated within the product team structure, coordinating with the Scrum Master for sprint facilitation;

(c) A Scrum Master shall be designated within the delivery team (Supplier) to facilitate agile ceremonies and remove impediments;

(d) The MONDELEZ D&A Lead provides Product Group Manager-level governance and escalation;

(e) Post-Go-Live, the PSOM (Product Stream Operations Manager) role shall be assigned within MONDELEZ to manage live service stability, incidents, and SLAs upon Transition to Support;

(f) The Product Group Manager and Product Stream Lead serve as the escalation path for strategic decisions per the POET governance hierarchy.

(g) The technology stack for this program is aligned with the POET-Tooling Approach (Walk phase) and the March 2026 mandatory Ataccama integration directive issued by MDLZ Data Governance. The primary governance tooling is:

- Data Catalog: Ataccama (enterprise standard)

- Data Quality: Ataccama (enterprise standard), with Databricks-native inline DQ execution synced to Ataccama

- Data Lineage: Ataccama (enterprise standard) + Databricks Unity Catalog (platform-native)

- Pipeline Platform: Databricks on AWS (approved platform)

- Semantic Layer: Databricks Unity Catalog metric views

- Consumption: Databricks AI/BI Dashboards + Genie Spaces

- Code Quality: SonarQube + AI-assisted review (Supplier-provided, CDRB C.1–C.2)

- Delivery & Governance: Jira/Jira Align (POET standard per POET-Tooling Approach)

All roles shall operate in accordance with the POET "Typical Roles in a Product-Centric Operating Model" reference guide.

7.2 POET Capability Building Requirement

POET Capability Building: All team members assigned to the MATRIX AI program (Supplier and MONDELEZ) shall complete the foundational POET learning modules ('Getting into the Product Mindset' and 'Typical Roles in a Product-Centric Operating Model') within 30 days of onboarding. Completion is tracked as part of team health metrics. The Supplier shall ensure that replacement resources (per the Resource Replacement assumption) also complete these modules within 30 days of assignment.

7.3 Delivery Methodology

The Supplier shall deliver Phases 1 through 5 using a Scrum-based methodology with two-week sprint cadences. Sprint ceremonies (Sprint Planning, Backlog Refinement, Sprint Review, Sprint Retrospective) are mandatory and shall achieve ≥80% ceremony adherence, measured by the Scrum Master and reported at each Sprint Retrospective. During Hypercare (Phase 5), the Supplier may transition specific support workstreams to Kanban where the work is continuous and demand-driven (e.g., defect resolution, alert triage), with explicit approval from the MONDELEZ Program Lead. The methodology selection aligns with the POET multi-speed delivery principle: Scrum for planned feature delivery and market onboarding; Kanban for business-as-usual operational support.

7.4 Definition of Ready

A backlog item shall be considered 'Ready' for sprint commitment when: (a) the business requirement is confirmed by the MONDELEZ Product Lead or designated business representative; (b) acceptance criteria are defined and agreed by both parties; (c) technical dependencies are identified and either resolved or explicitly accepted as sprint risks; (d) a technical estimate is provided by the Supplier team; and (e) any required configuration table entries or reference data changes are documented. The Scrum Master shall confirm that all items in the sprint backlog meet the Definition of Ready before sprint commitment at Sprint Planning.

7.5 Definition of Done

A deliverable or sprint increment shall be considered 'Done' when: (a) code is complete and follows the 8-block procedure template (CDRB D01); (b) all applicable CDRB criteria for the relevant sections are met, with evidence submitted to the CDRB review queue; (c) unit tests and golden-data tests are passing (CDRB J01, J02); (d) SonarQube quality gate is passed with zero critical or blocker issues (Appendix C.1); (e) peer code review is completed and approved; (f) documentation is updated — design notes, KPI registry, data dictionary as applicable (CDRB L01, L03); and (g) the item is accepted by the MONDELEZ Product Lead or designated reviewer at Sprint Review. CDRB sign-off across all applicable sections constitutes the technical Definition of Done for each deliverable.

7.6 Sprint Tracking

All sprint work, backlog items, defects, and RAID log items shall be tracked in MONDELEZ Jira (or MONDELEZ-designated equivalent). The Supplier team shall maintain Jira boards current at all times, with story status, sprint assignments, and estimates reflecting the actual state of work. Jira is the system of record for sprint planning, backlog prioritization, velocity tracking, and sprint reporting. The Scrum Master shall ensure Jira data supports the sprint metrics reported at each Sprint Review and Sprint Retrospective.

- Timeline. This SOW shall be delivered fully by 31/December/2027 and fully completed by 31/03/2028 with the warranty cause.

- Work Product / Success Criteria.

- ACCEPTANCE CRITERIA. This SOW is a fixed-price product build engagement. The Supplier is responsible for delivering all deliverables (D1 through D16) to the measurable success criteria defined in Section 5. Acceptance of each deliverable is objective and evidence-based, governed by the CDRB quality framework (Sections A through L, Appendix A) and the Automated Quality Review framework (Appendix C). No deliverable shall be deemed accepted based solely on subjective assessment. In addition to deliverable-level acceptance criteria (which measure whether the product was built correctly), the parties shall jointly track Product Outcome Metrics (Section 9.1) from Phase 3 onward. These outcome metrics measure whether the product is delivering value — consistent with the MONDELEZ POET principle that success is defined by the outcomes the product drives, not simply by whether it was built and released. MONDELEZ shall review each deliverable within ten (10) business days of the Supplier's formal submission for acceptance. Acceptance, rejection, or conditional acceptance shall be communicated in writing. Rejection shall include specific deficiencies referencing the applicable CDRB criteria or success metrics. The Supplier shall have fifteen (15) business days to remediate and resubmit rejected deliverables at no additional cost.

- PHASE GATE ACCEPTANCE / PRODUCT INCREMENT REVIEW. In addition to individual deliverable acceptance, the following phase gates require formal MONDELEZ sign-off before the project may proceed to the next phase. Each phase gate requires: (a) all applicable deliverables accepted per the criteria above; (b) a complete and current Automated Quality Evidence Package per Appendix C (SonarQube dashboard, AI review log, architecture conformance report, reconciliation results, test pass rates); and (c) no open critical or high-priority defects unless explicitly deferred with MONDELEZ written approval.

| Phase Gate | Milestone Date | Deliverables Required | CDRB Sections Signed Off |
| --- | --- | --- | --- |
| Gate 1: Blueprint Sign-Off | January 2027 | D1 (design), D2 (design), D3, D4, D6 (inventory), D14 (design notes), D16 | A, C, D primary; B, E, F, G, I, J, K, L reviewed. Core domain fit/gap analysis completed under DP&E guidance and formally approved by DP&E, documenting the delivery model per entity (consume from DP&E or build under DP&E direction), and confirming that all entities — whether consumed or built — are consistent with global canonical core domain standards. |
| Gate 2: Migration Complete | March 2027 | D1, D2, D3, D4, D7, D8, D9, D10, D13 (unit/golden), D14, D16 | All A–L reviewed; J, K, L primary sign-off |
| Gate 3: User Testing Complete | June 2027 | D5, D6 (final), D11, D12, D13 (parallel-run), D15 (materials + T3), D16 — F, H primary; all A–L reviewed. Additionally: HEART baseline metrics established (Happiness NPS baseline, Engagement usage baseline, Adoption target population identified per BU) | F, H primary; all A–L reviewed |
| Gate 4: Integration Test & UAT Acceptance | August 2027 | All D1–D16 accepted — All A–L final sign-off; go/no-go decision. Additionally: HEART metrics tracked during UAT period; NPS baseline collected from UAT participants; Adoption onboarding plan confirmed for all 4 BUs; Product Outcome Metrics reporting dashboard deployed. | All A–L final sign-off; go/no-go decision |
| Gate 5: Production Readiness & Go-live | September & October 2027 | D10 (production validated), D12 (published), D14 (final) | Product team sign-off Each phase gate requires: (a) all applicable deliverables accepted per the criteria above; (b) a complete and current Automated Quality Evidence Package per Appendix C; (c) no open critical or high-priority defects unless explicitly deferred with MONDELEZ written approval; and (d) for Gate 5 specifically, a Product Value Realization Assessment confirming: (i) HEART metrics at or above agreed targets (NPS ≥ 30, Adoption ≥ 80%, Retention ≥ 70%); (ii) KPI consistency confirmed across all 4 BUs with zero unresolved executive-reported discrepancies; (iii) Product Outcome Metrics dashboard operational and transitioned to the product operations team; (iv) Product Continuity Plan documenting the transition from build-phase outcome tracking to persistent product health monitoring. |
| Gate 6: Hypercare & Transition to Support (T2S) | December 2027 | D15 (KT complete) — AMS + Product team sign-off; Hypercare exit confirmed. Additionally: HEART metrics at or above targets (NPS ≥ 30, Adoption ≥ 80%, Retention ≥ 70%); Business Value Metrics reviewed (KPI consistency confirmed, executive confidence assessed); Product Outcome Metrics dashboard transitioned to product operations team. | AMS + Hypercare exit confirmed |

- WARRANTY / PRODUCT STABILISATION COMMITMENT. The Supplier warrants that all deliverables for which it holds "Primary" responsibility (per Section 5 Responsible Party table) shall conform to the measurable success criteria defined above for a period of ninety (90) days following the Go-Live date (Gate 4 acceptance). During the warranty period, the Supplier shall remediate any defect, non-conformance, or regression at no additional cost to MONDELEZ. Defects discovered during the warranty period shall be classified as: Critical (KPI accuracy impact, data loss, or security breach) with a 4-hour response and 24-hour resolution target; High (functionality degraded, workaround available) with an 8-hour response and 3-business-day resolution target; Medium (cosmetic or minor functionality) with a 2-business-day response and 10-business-day resolution target. The warranty period shall be extended by the number of days any Critical defect remains unresolved beyond its resolution target. This is applicable for Blueprint / Working Prototype and Rollout phases.

| Deliverable | Acceptance Criteria | Evidence Required |
| --- | --- | --- |
| D1: Pipeline Architecture | 100% of procedures follow 8-block template (CDRB D01). Zero market-specific code branches (CDRB A03). Environment is a setting, not code (CDRB A04). SonarQube quality gate pass rate = 100%. | SonarQube dashboard, architecture conformance report (Appendix C.3), CDRB Section A/D sign-off. |
| D2: Core Domain Model | All entities built with declared identity and uniqueness enforced (CDRB B01). Market boundaries from config only (B02). No data silently lost (B07). Every record traceable (B06). Core domain fit/gap analysis approved by DP&E with documented delivery model per entity. All consumed DP&E entities validated with documented results. All Supplier-built entities (where directed by DP&E) reviewed by DP&E for global consistency. Evidence Required: Reverse-engineering architecture report, data lineage map, CDRB Section B sign-off, DP&E fit/gap approval with delivery model decisions, DP&E entity review sign-off. | Reverse-engineering architecture report, data lineage map, CDRB Section B sign-off. |
| D3: Configuration Layer | All configuration tables populated and versioned. All business rules as config rows (CDRB C01). No hardcoded values (C02). No duplicate procedures (C03). Adding a new market requires zero code changes. | SonarQube custom rule results (no hardcoded values), configuration dependency matrix (Appendix C.3), CDRB Section C sign-off. |
| D4: KPI Engine & Registry | All KPIs calculated in base units (CDRB F01). Composite KPIs from registry (F03). Every KPI has registered owner (F07). Dictionary generated from code (F08). All 4 BU business owners sign off. | KPI registry-to-code reconciliation report (Appendix C.3), AI review coverage log (Appendix C.2), signed BU acceptance forms, CDRB Section F sign-off. |
| D5: Semantic Layer & Consumption | All metric views in Unity Catalog with RLS. Genie benchmark: ≥ 50 business questions answered correctly. Existing dashboards migrated with side-by-side validation. No consumer accesses raw tables. | Genie benchmark test results, dashboard validation report, security audit (CDRB I01-I04), CDRB Section I sign-off. |
| D6: KPI Harmonization | 100% of in-scope KPIs registered with owner, formula, and version. Zero unresolved conflicts. Parallel-run reconciliation within tolerance, KPI-by-KPI, market-by-market (CDRB J03). | KPI registry export, parallel-run reconciliation report (automated, Appendix C.4), signed BU acceptance forms. |
| D7: Data Quality Framework | DQ checks at every quality gate (CDRB E03). De-duplication deterministic (E04). Re-run safety confirmed (E05). DQ dashboard deployed showing pass/fail by domain, market, layer. All DQ rule definitions and thresholds provided to the Data Governance team for Ataccama registration, with Data Governance team confirmation of receipt and completeness. Evidence Required: DQ dashboard screenshots/access, automated re-run test results (Appendix C.4), CDRB Section E sign-off, Data Governance team receipt confirmation for DQ information package. | DQ dashboard screenshots/access, automated re-run test results (Appendix C.4), CDRB Section E sign-off. |
| D8: Jobs Monitoring & Alerts | Run logs for every procedure (CDRB K01). Alerts for all failures and warnings with zero user-reported discovery (K02). Runtime budgets verified: procedure ≤ 30% reduction from current pipeline, full chain 30% reduction from current pipeline, publish layer ≤ 30% reduction from current pipeline (G01). | Jobs monitoring dashboard access, alert routing configuration evidence, runtime benchmark results, CDRB Sections G/K sign-off. |
| D9: Cost Monitoring | Cost tags applied by layer, market, procedure (CDRB G07). Cost dashboard deployed with Genie-queryable views. Final cost baseline report delivered. | Cost monitoring dashboard access, Genie cost query examples, cost baseline report document, CDRB Section G sign-off. |
| D10: Runbook & Re-Run Playbook | Runbook published and peer-reviewed (CDRB K03). Single-market re-run validated in production. Backfill and rollback validated. Data lineage visible end-to-end (K04). | Published runbook document, production validation evidence (re-run logs, cost tags), Unity Catalog lineage screenshots, CDRB Section K sign-off. |

| Deliverable | Acceptance Criteria | Evidence Required |
| --- | --- | --- |
| D11: Global Scalability Proof | Synthetic market ZZ passes end-to-end with zero code changes (CDRB H01). 3x volume within 1.5x runtime (H02). Market isolation confirmed (H03). Flexible reprocessing confirmed (H04). | Automated ZZ test results with code diff (Appendix C.4), volume test results, concurrent run logs, config-only onboarding evidence, CDRB Section H sign-off. |
| D12: Global Scalability Playbook | All 9 Playbook sections complete per Appendix D. 20 validated config-only examples documented. Effort model endorsed. Governance model approved by MONDELEZ D&A leadership. | Published Playbook document, code-diff evidence for 20 examples, signed endorsement from MONDELEZ leadership, CDRB Section L sign-off. |
| D13: Testing & Reconciliation | Unit tests for all shared functions (CDRB J01). Golden-data tests per procedure (J02). Parallel-run within tolerance (J03). All legacy defects tracked with resolution (J04). Re-run test in CI (E05). | Automated test suite results dashboard (Appendix C.4), reconciliation report, legacy defect register, CI pipeline evidence. |
| D14: Documentation & Governance | Design notes approved for all Tier 1 components (CDRB L01). Waivers explicit and time-bound (L02). Registry in sync with automated drift check (L03). Legacy mapping complete (L04). Security review complete (I01-I04). Complete metadata package provided to the Data Governance team for Ataccama registration, with Data Governance team confirmation of receipt and completeness. Evidence Required: Design note repository, waiver register, automated drift check report (Appendix C.3), legacy mapping document, security scan results, Data Governance team metadata package receipt confirmation | Design note repository, waiver register, automated drift check report (Appendix C.3), legacy mapping document, security scan results. |
| D15: Training & Enablement | Materials cover all user personas. Train-the-Trainer certified. End-user training delivered across all 4 BUs. Training portal published. Effectiveness feedback collected and gaps addressed. | Training materials repository, trainer certification records, attendance logs, training portal access, feedback survey results. |
| D16: Project Management | Status reports delivered on schedule. RAID log maintained. All milestones met or formally re-baselined. Lessons learned documented. | 4-Box report archive, RAID log, milestone tracker, lessons learned document. |

WORK PRODUCT / SUCCESS CRITERIA

Defect severity reflects both technical impact and product adoption impact, consistent with the MONDELEZ POET principle that success requires measurable user adoption and engagement alongside technical delivery excellence.

| Defect Class | Definition | Response Target | Resolution Target |
| --- | --- | --- | --- |
| Critical | KPI accuracy impact, data loss, or security breach or adoption-blocking defect affecting ≥…25% of target users | 4 hours | 24 hours |
| High | Functionality degraded, workaround available or defect causing measurable drop in engagement metrics (≥…10% WAU decline) | 8 hours | 3 business days |
| Medium | Cosmetic or minor functionality | 2 business days | 10 business days |

Warranty Period & Extension

The warranty period shall be ninety (90) calendar days from the accepted Go-Live date. Where a Critical defect is raised and resolved within the warranty period, the warranty period for the affected component shall be extended by a further thirty (30) calendar days from the date of resolution, to provide assurance that the fix is stable in production. All warranty obligations apply equally to defects classified under the expanded adoption-blocking and engagement-drop criteria defined in the table above.

9.1 Product Outcome Metrics

Consistent with the MONDELEZ POET product measurement framework, the following Product Outcome Metrics shall be jointly tracked by the Supplier and MONDELEZ from the phases indicated. These metrics complement (and do not replace) the deliverable-level acceptance criteria in Sections 5 and 9.

9.1.1 HEART Framework Metrics (measured from Phase 4 — UAT onward)

The HEART Framework (Happiness, Engagement, Adoption, Retention, Task Success) shall be applied to measure the product's impact on end users:

| HEART Dimension | What It Measures | Metric | Target | Measurement Method |
| --- | --- | --- | --- | --- |
| Happiness | User satisfaction with the product | Net Promoter Score (NPS) across 4 BUs | Baseline at UAT; ≥ 90% by Hypercare exit | Quarterly NPS survey to BU analytics leads and power users |
| Engagement | How actively users interact with the product | Weekly active users on AI/BI Dashboards + Genie Spaces; average session length | Baseline at Go-Live; ≥ 90% by Hypercare exit | Databricks usage analytics (Unity Catalog audit logs) |
| Adoption | How many target users are taking up the product | % of target user population onboarded and active across 4 BUs | ≥ 80% of identified target users active within 60 days of Go-Live | User provisioning records + Unity Catalog access logs |
| Retention | Whether users continue using the product | % of users returning weekly after initial onboarding | ≥ 70% 4-week retention rate | Databricks usage analytics |
| Task Success | Whether users can accomplish their goals | Genie question accuracy rate; time-to-insight for standard KPI queries | Genie: ≥ 50 benchmark questions answered correctly (per D5); time-to-insight: ≤ 5 minutes for standard queries | Genie benchmark test results; user observation during UAT |

9.1.2   Business Value Metrics (measured from Phase 4 — Go-Live onward)

| Metric | What It Measures | Target | Measurement Method |
| --- | --- | --- | --- |
| KPI consistency across BUs | Whether the harmonized KPI layer eliminates cross-market discrepancies | Zero unresolved KPI conflicts across 4 BUs at Go-Live; zero executive-reported KPI discrepancies during Hypercare | KPI registry reconciliation report (D6) + executive feedback |
| Decision-making acceleration | Whether the product reduces time from question to data-backed answer | ≥ 50% reduction in time-to-insight vs. current GCP/Power BI baseline (measured via user survey) | Pre/post user survey during Hypercare |
| Executive confidence in data | Whether leadership trusts the platform for decision-making | Qualitative: ≥ 3 of 4 BU leaders confirm "confident" or "very confident" in data accuracy | Structured interview at Hypercare exit |
| Self-service enablement | Whether business users can answer questions without analyst intervention | ≥ 30% of standard analytical queries resolved via Genie self-service (vs. analyst request) | Genie query logs vs. analyst request tickets |

9.1.3   Product Team Health Metrics (measured from Phase 2 onward)

| Metric | What It Measures | Target | Measurement Method |
| --- | --- | --- | --- |
| Deployment frequency | How often the product delivers value increments | ≥ bi-weekly deployment to DEV; ≥ monthly deployment to PROD (from Phase 3) | CI/CD pipeline logs |
| Lead time for changes | How quickly a change moves from backlog to production | ≤ 2 weeks for standard configuration changes; ≤ 4 weeks for new KPI additions | Jira/backlog tracking |
| Change failure rate | How often deployments cause incidents | ≤ 5% of deployments require rollback | Deployment logs + incident records |
| Time to restore | How quickly the team recovers from incidents | Critical: ≤ 24 hours; High: ≤ 3 business days (consistent with warranty SLAs) | Incident management logs |

9.2 Product Stabilization Warranty Windows

In alignment with POET Product Lifecycle Management principles — where every product transition represents the beginning of a new evaluation cycle, not the end of a delivery milestone — the Supplier shall provide two dedicated Product Stabilization Warranty Windows of ninety (90) calendar days each, applicable at the following phase transitions:

Window 1 — Working Prototype Stabilization (Phase 1 Completion)

Effective Date: Commencing upon formal acceptance of Gate 1 (Blueprint & Working Prototype Sign-Off), targeted end of January 2027.

Warranty Duration: Ninety (90) calendar days from Gate 1 acceptance.

Coverage: During this window, the Supplier shall ensure the stability, integrity, and readiness of all Working Prototype deliverables (D1 design, D2 design, D3, D4, D6 inventory, D14 design notes, D16) as the solution transitions from the Databricks exploration zone to the Databricks AWS Development environment. This window covers:

- Resolution of any defect, regression, or non-conformance identified in the prototype deliverables during the stabilization period, at no additional cost to MONDELEZ.

- Support for environment transition activities — including configuration validation, pipeline re-verification, and data reconciliation — arising from the migration to the new Databricks AWS Development environment.

- Joint resolution of challenges encountered by either party due to the new environment setup, including access provisioning, infrastructure readiness, connectivity, and toolchain integration, ensuring that such activities are absorbed within this stabilization window without impacting the agreed Phase 2 and subsequent milestone dates.

Timeline Protection: This stabilization window operates as a product-level mitigation mechanism. It provides both parties with a structured period to address environment-related and prototype-related stabilization needs without triggering formal change orders or re-baselining of the agreed project timeline. Activities performed within this window shall not constitute grounds for extending Phase 2 (Migration & Scalability Proof) or any subsequent phase milestone dates.

Window 2 — Full Product Build Stabilization (Phase 5 Completion)

Effective Date: Commencing upon formal acceptance of Gate 5 (Go-Live & Transition to Support), targeted December 2027.

Warranty Duration: Ninety (90) calendar days from Gate 5 acceptance.

Coverage: During this window, the Supplier shall ensure the stability, performance, and adoption readiness of the complete MATRIX AI production deployment across all four Latin American Business Units. This window covers:

Resolution of any defect, regression, or non-conformance identified in any deliverable (D1 through D16) during the stabilization period, at no additional cost to MONDELEZ, classified per the Warranty Defect Classification & SLAs table in Section 9.

Support for production environment optimization activities — including runtime tuning, cost baseline calibration, alert threshold refinement, and monitoring dashboard adjustments — arising from real-world production data patterns.

Joint resolution of challenges encountered by either party during the production stabilization period, including infrastructure scaling, cross-environment configuration alignment, and operational handover activities to the MONDELEZ AMS and Product teams, ensuring that such activities are absorbed within this stabilization window.

Timeline Protection: This stabilization window serves as the product's formal Introduction (Launch & Hypercare) evaluation period under POET Product Lifecycle Management. It provides both parties with a structured period to confirm production readiness, validate operational handover, and address any stabilization needs without requiring formal change orders. The Supplier shall not be released from this stabilization window until both the AMS team lead and Product team lead confirm in writing that the product is operating stably and the teams are capable of independent operation.

Relationship with Existing Warranty Provisions

These Product Stabilization Warranty Windows are additional to and do not replace the existing warranty provisions in Section 9. Specifically:

- The existing 90-day warranty from Go-Live (as defined in Section 9) applies to the production deployment and runs concurrently with Window 2 above.

- The existing 30-day Critical defect extension applies within both Window 1 and Window 2: where a Critical defect is raised and resolved within either stabilization window, the warranty period for the affected component shall be extended by a further thirty (30) calendar days from the date of resolution.

- The expanded defect definitions (adoption-blocking ≥25% of target users as Critical; engagement-drop ≥10% WAU decline as High) apply within both stabilization windows, consistent with the POET principle that product stability encompasses both technical performance and user adoption health.

POET alignment

| POET Principle | How This Clause Aligns |
| --- | --- |
| Product Lifecycle Ownership | Stabilization windows treat each phase transition as the beginning of a product evaluation cycle — not a handoff. The Supplier maintains accountability through the product's Introduction phase, consistent with POET's continuous ownership model. |
| Outcomes Over Outputs | Coverage extends beyond technical deliverable conformance to include adoption readiness, environment stability, and operational capability transfer — measuring success by outcomes (stable product, capable teams) rather than by outputs (deliverables accepted). |
| Continuous Improvement | The structured 90-day windows create dedicated space for learning, tuning, and optimizing based on real usage patterns, embodying POET's principle that every phase transition is an opportunity to improve. |
| Empowered Teams | Joint resolution provisions recognize that stabilization is a shared responsibility. Both parties contribute to resolving environment and operational challenges within the protected window, reinforcing POET's collaborative team model. |
| Risk Mitigation Without Timeline Impact | The windows absorb environment-related and transition-related risks within a defined, governed period — protecting agreed milestone dates and providing a structured mitigation mechanism rather than reactive change orders. |
| HEART Metrics Connection | Defect classification within both windows includes adoption-blocking and engagement-drop criteria (per Section 9 Warranty Defect Classification), ensuring product health during stabilization is measured against user outcome metrics, not solely technical metrics. |

Commercial Impact

This clause is additive only. No existing SLAs, warranty periods, milestone dates, commercial obligations, or fees are modified. The Supplier accepts the two Product Stabilization Warranty Windows as part of the POET-aligned product delivery commitment. No additional fees or change orders apply to activities performed within these windows.

- Costs - Fees and Expenses.

FEES. This SOW is based on a fixed-capacity product build engagement.

Phase 2 Invoicing Condition: Invoicing for Phase 2 deliverables (February 2027 onward) shall not commence until the Product Stabilization Warranty from phase 1 – Blueprint and Working Prototype, has been completed with no open Critical or High defects, and MONDELEZ has confirmed in writing that the Working Prototype is stable and fit for migration. Phase 2 work may proceed during the warranty period, but invoiced amounts shall be held and released only upon written warranty completion confirmation. This condition does not extend or modify Phase 2 milestone dates.

| Location | Year | Month | Product Description | Resource Cost |
| --- | --- | --- | --- | --- |
| Remote | 2026 | November | Matrix AI |  |
| Remote | 2026 | December | Matrix AI |  |
| Remote | 2026 | January | Matrix AI |  |
| Remote | 2027 | February | Matrix AI |  |
| Remote | 2027 | March | Matrix AI |  |
| Remote | 2027 | April | Matrix AI |  |
| Remote | 2027 | May | Matrix AI |  |
| Remote | 2027 | June | Matrix AI |  |
| Remote | 2027 | July | Matrix AI |  |
| Remote | 2027 | August | Matrix AI |  |
| Remote | 2027 | September | Matrix AI |  |
| Remote | 2027 | October | Matrix AI |  |
| Remote | 2027 | November | Matrix AI |  |
| Remote | 2027 | December | Matrix AI |  |
|  |  |  | Total Labor Cost |  |
|  |  |  | Total Labor Cost (after discount) |  |
|  |  |  | Total Expense |  |
|  |  |  | Total Product Build Cost |  |
|  |  |  | (Proposed Investment) |  |
|  |  |  | Final Proposed Product Build Investment |  |

Full MONDELEZ Rate Card (‘Attachment 1’ to MSA signed on April-12, 2024) is referenced for all resource costs and fees that are submitted within this document (including yearly COLA adjustments – ‘Attachment 2 to MSA’).

FEES AT RISK.  Seller agrees to put [0%] of the Fees 'at risk' for the product build phase. This means that if Seller fails to deliver any one Deliverable (in whole or in part) in accordance with the applicable Milestone Date, Buyer will pay Seller the Fees less [0%] once all Deliverables are delivered meeting the success criteria. Buyer shall not be obligated to pay any fees for Deliverables that fail to meet the Acceptance Criteria. In addition to deliverable-based acceptance, the parties shall jointly track Product Outcome Metrics (Section 9) during the Hypercare period. While these outcome metrics do not carry financial penalties under this fixed-price engagement, they shall inform: (a) the readiness assessment for transitioning to the POET persistent product funding model; and (b) the scope and commercial terms of any subsequent product capacity engagement.

EXPENSES. All expenses require prior written agreement from the Buyer.  Expenses not included in this SOW are subject to separate approval of the Buyer.

INVOICING. Seller will invoice Buyer in accordance with the Milestone/Deliverables schedule set forth herein following Buyer’s written acceptance. If this is a time and materials, fixed Fee or other type of SOW having no payment schedule identified, Seller will invoice for Services in the month following the month in which Services were provided. Buyer will pay for Services pursuant to the terms of the Master Service Agreement or, if no such terms are provided, within 180 days of receipt of a complete and accurate invoice or the maximum amount of time allowed by applicable local law (if shorter). Unless otherwise provided in the Master Service Agreement, payment will be made in the local currency for the country in which Services are provided.

Invoicing will be done monthly based on the agreed fixed amount. Presented below are expected monthly costs.

| Milestone/Deliverable | Billing Month | Expected Amount (USD) |
| --- | --- | --- |
| November 2026 | November 2026 |  |
| December 2026 | December 2026 |  |
| January 2027 | January 2027 |  |
| February 2027 | February 2027 |  |
| March 2027 | March 2027 |  |
| April 2027 | April 2027 |  |
| May 2027 | May 2027 |  |
| June 2027 | June 2027 |  |
| July 2027 | July 2027 |  |
| August 2027 | August 2027 |  |
| September 2027 | September 2027 |  |
| October 2027 | October 2027 |  |
| November 2027 | November 2027 |  |
| December 2027 | December 2027 |  |

- Miscellaneous. The Seller’s Invoice Number and Buyer Purchase Order (PO) Number must be included on the invoice. A list of the deliverables and/or services for which you are invoicing Buyer must be included on the invoice. Any expenses must be shown on a separate line item on the invoice.

- Changes to SOW. No change, modification, or waiver of any provision of this SOW shall be valid unless the same is in writing and signed by the parties hereto.

- Termination for Convenience. Buyer may terminate this SOW upon delivering thirty (30) days prior written notice of such termination to Seller. Following such notice and prior to the effective date of termination, Seller shall immediately cease all work with respect to this SOW, in a reasonable and orderly fashion in accordance with Buyer’s instructions.  Within the thirty (30) day prior notice period, Seller shall deliver to Buyer all Deliverables or partial Deliverables and any documentation relating to this SOW in an orderly manner. After delivery of such notice, Buyer shall have no further liability to Seller with respect to this SOW, except that Buyer shall be liable for Seller’s charges for work performed through the effective date of such termination in accordance with the Product Engagement Agreement.

10.1 Product Funding Transition

The parties acknowledge that this fixed-price engagement covers the Introduction (Launch & Hypercare) stage of the MATRIX AI product lifecycle. Upon successful completion of Phase 5 (Go-Live and Transition to Support), the ongoing funding for the MATRIX AI product shall transition to the POET persistent product funding model, governed through the following principles:

(a) TCO as the financial anchor: The cost baseline delivered in D9 shall serve as the foundation for ongoing product TCO management. The Product Lead shall present TCO per Product (Trend) at the quarterly MLT Meeting and MDS Strategic Portfolio Board, consistent with POET financial governance.

(b) Run vs Change allocation: Post-Go-Live costs shall be categorized as Run (operational support, incident management, infrastructure) or Change (enhancements, new market onboarding, new data products). The Run vs Change ratio shall be tracked and reported at the Product Council.

(c) Persistent product team capacity: Any subsequent engagement for ongoing MATRIX AI product evolution shall be structured as persistent product team capacity (dedicated headcount allocated to the product backlog) rather than project-based funding (time-bound budget for a defined scope). This aligns with the POET principle that "long-lived funding should be committed directly to stable Product Streams and Platform Lines."

(d) Investment governance: Any new investment exceeding the thresholds defined in the POET governance framework shall be submitted to the Investment Management Committee for approval, accompanied by a business case that references the product TCO baseline and projected value outcomes.

(e) Product Stream financial integration: As individual data products enabled by MATRIX AI (e.g., OTC Analytics, Market Share Analytics) transition into their respective Product Stream backlogs, their associated costs shall be absorbed into the respective Product Stream TCO, with the shared platform costs remaining within the D&A Platform Line TCO.

SIGNATURE PAGE FOLLOWS

The Parties have read this document and agree to be bound by its terms. The Parties’ authorized representatives execute this document by signing below, either physically or electronically (if legally valid), and may sign separate copies.

| [Mondelez Mexico S. de R.L. de C.V.] | [Lingaro Mexico S. de R.L. de C.V] |
| --- | --- |
| ___________________________________ Signature | ___________________________________ Signature |
| ___________________________________ Printed Name | ___________________________________ Printed Name |
| __________________________________ Title | ____________________________________ Title |

Appendices

Appendix A: Quality Review Sections A–L — Criteria Summary

The following table provides the complete criteria reference for all 12 CDRB quality review sections. These criteria are the formal definition of done for every deliverable in the program applied for all project phases. For the avoidance of doubt, CDRB sign-off across all applicable sections constitutes the technical Definition of Done for each deliverable, as referenced in Section 7 (Definition of Done). Sprint-level items are considered 'Done' when they meet the criteria defined in Section 7 and are submitted to the CDRB review queue with supporting evidence.

- Source Ingestion

- Data Harmonization & Standardization

- Core Domain Build (Source-Agnostic Gold Layer)

- Market Configuration Layer as configurable assets

- KPI Dictionary as configurable asset, governance and knowledge

- KPI Calculation Layer as configurable assets

- KPI Publication / Data Products

- Semantic / Consumption Layer: Unity Catalog Metric Views

- Consumption 1: AI/BI Dashboards,

- Consumption 2: Genie Agents

- Consumption 3: Knowledge Assistants

- Consumption 4: Functional Supervisor Agents

- Consumption 5: Cross-Functional Supervisor Agents

- End-to-End jobs monitoring, alerts, cost and runtime.

- End-to-End Data Quality monitoring, alerts for every process.

- Training materials

- Scalable playbook with detailed step applying the configurable approach / setup

- Show case 20 true examples to onboard a new market with existent data and no coding as reference North America

| Sec. | Criterion ID | Quality Standard |
| --- | --- | --- |
| A | A01–A05 | Layer separation confirmed; consistent naming convention enforced; market identity always from configuration; environment (Dev/QA/Prod) always from configuration; single orchestration conductor per layer with declared dependencies. |
| B | B01–B07 | Declared identity (primary key, business key, grain) on every Gold-layer table; market boundaries from configuration; all measures in base units (kg, local currency); source traceability columns on every record; inclusive joins preventing silent data loss; shared entity patterns codified; named domain ownership. |
| C | C01–C05 | All business rules stored as configuration rows (not IF-THEN-ELSE branches); zero magic numbers or hard-coded constants; no cloned procedures per market; single authoritative source per reference value; every configuration change versioned with author, timestamp, and effective dates. |
| D | D01–D08 | 8-block procedure template followed in sequence; shared logging utility used (no ad-hoc logging); transforms decomposed into named steps; all NULL and boundary conditions handled explicitly; division-by-zero protection on every ratio; consistent snake_case naming per project glossary; explicit data type declarations; no SELECT * in production code. |
| E | E01–E05 | Incremental processing by default with watermark; transaction-wrapped all-or-nothing loads; quality checks run before data is persisted; deterministic de-duplication with declared business key and tie-breaking rule; any procedure re-executable without duplication or corruption. |
| F | F01–F10 | All calculations in base units (kg, local currency); mutually exclusive and collectively exhaustive population splits; composite KPIs from registry only; business rules data-driven from configuration; calendar aggregation from configuration; long (narrow) KPI model throughout pipeline; parallel-run reconciliation against legacy GCP; formula accuracy proof documented; additivity declared per KPI; version and ownership recorded in registry. |
| G | G01–G07 | Declared runtime budget per procedure; full pipeline chain with runtime tracking; tables partitioned by most common filter column; incremental processing windows enforced; all joins reviewed for Cartesian risk; automated table maintenance scheduled; compute right-sized per workload; live cost dashboards with budget-threshold alerting. |

| Sec. | Criterion ID | Quality Standard |
| --- | --- | --- |
| H | H01–H04 | Synthetic Market Test (fictional market “ZZ”) added via configuration rows only (provide simulated market inclusion like Canada to prove configuration design works) — zero code changes, zero new procedures, end-to-end correct outputs; 3x data volume within 1.5x runtime; one market failure cannot cascade to other markets; any market can be independently reprocessed for any date range via configuration parameters. |
| I | I01–I04 | Least-privilege access for all users and service principals; automated scanning for sensitive data in code on every commit; row-level security on all consumption views; complete access audit trail retained per MONDELEZ governance policy. |
| J | J01–J04 | Unit test suite for every shared function (100% coverage, positive/negative/boundary cases); golden-data test per procedure with documented expected outputs; parallel-run reconciliation KPI-by-KPI x month x unit of measure within agreed tolerance; all legacy pipeline opportunities logged with documented resolution path in TO-BE design. |
| K | K01–K04 | Complete queryable run logs (start/end time, row counts, status, error messages); automated alerting for SLA breaches, quality threshold violations, pipeline failures, and unexpected row-count changes (>+/-20%); operational runbook for every production procedure in version control; data lineage visible in Unity Catalog automatically updated by pipeline. |
| L | L01–L04 | Design note approved before coding begins for every new procedure or significant change; any deviation from CDRB standard documented with explicit time-bound waiver (no open-ended exceptions); KPI registry and data dictionary always in sync with automated drift detection; every legacy GCP procedure mapped to its replacement with decommission date and sign-off owner. |

The 12 review sections below define what the CDRB checks. Each section has an objective (what we are trying to achieve), a benefit (why it matters for the business), individual criteria in plain English, and the expected output for solution design and build.

Section A — Architecture & Layering

Objective: Every component in the pipeline has one clear job and stays in its lane. Data flows through defined layers with clear contracts between them.

Benefit: When responsibilities are separated, a change to how we calculate a KPI does not break how we ingest data. Teams can work on different layers in parallel. New markets plug in without rewiring the whole pipeline.

| A01 | Each component does one job A procedure that loads customer data does not also calculate KPIs. A procedure that calculates sell-in does not also convert currencies. If a component crosses layer boundaries, it gets split. → Expected output: Every procedure includes a design declaration of its layer, inputs, and outputs. No procedure spans two layers. |
| --- | --- |

| A02 | Components are where they belong Every object in the pipeline matches the agreed TO-BE blueprint. If something new is needed, it goes through a formal design decision. No rogue objects or unofficial shortcuts. → Expected output: Object catalogue matches the TO-BE flow. Any new object has an approved design record before build begins. |
| --- | --- |

| A03 | Market is a setting, not code The pipeline works for any market — Mexico, Wacam, Brazil — by changing a setting, not by editing code. No "if Mexico, do this; if Wacam, do that" branches exist anywhere in the pipeline. → Expected output: Market identifier as a parameter on every procedure and a column on every table. Zero market-specific code branches. |
| --- | --- |

| A04 | Environment is a setting, not code Moving the pipeline from development to testing to production requires no code changes — just environment settings. No hard-coded database names or project identifiers. → Expected output: All catalogue and schema references come from environment variables. Confirmed clean in all environments. |
| --- | --- |

| A05 | One conductor per layer Each layer has one orchestrator that controls execution order. No external scheduling systems embedded in the code, no leftover placeholders from legacy tools. → Expected output: Workflow definition shows clean orchestration with no external scheduler IDs embedded in procedure logic. |
| --- | --- |

Section B — Core Domain Design

Objective: Build clean, reusable data tables that represent business objects (orders, invoices, deliveries) exactly once, with consistent quality.

Benefit: When every KPI starts from the same trusted core data, two dashboards will never show different numbers because they read from different source tables. Core domains are built once and shared — no duplication across markets.

| B01 | Every table has a declared identity Each table states what one row represents — for example, "one row per order line per market" — and what makes that row unique. The system enforces uniqueness automatically. Duplicates are caught before they reach downstream layers. → Expected output: Header declaration with grain and business key, plus automated uniqueness test results for every table. |
| --- | --- |

| B02 | Market boundaries come from configuration What counts as a "Mexico order" or a "Wacam invoice" is defined in a managed configuration table, not written into the code. Adding a new market means adding rows to the configuration table, not editing procedures. → Expected output: Market scope configuration table populated. No order ranges, organization codes, or channel identifiers in any procedure. |
| --- | --- |

| B03 | Business classifications come from reference tables What type of document an invoice is (billing, credit note, return), what a reason code means (refusal, cancellation) — these are looked up from managed reference tables, not written as lists inside procedures. → Expected output: Role tables for documents, reason codes, and item categories populated and used consistently across all procedures. |
| --- | --- |

| B04 | Measurements are standardized at the boundary All weights are converted to kilograms and all values to local currency at the point where data enters the core domain. Downstream layers never deal with raw units from the source system. → Expected output: Shared weight and currency conversion functions used consistently. No raw source-system unit exposed as a measure in any domain table. |
| --- | --- |

| B05 | Core tables describe what happened, not how to measure it The order table records that an order exists with its attributes. Whether that order counts as a "cancellation" or an "on-time delivery" for KPI purposes is decided later in the KPI engine — not baked into the core data. → Expected output: Domain tables contain attributes and document roles only. No KPI flags, no calculated measures, no business rule outcomes. |
| --- | --- |

| B06 | Every record is traceable Each row has a deterministic, reproducible identifier. When a customer or product code is missing from the master data, a documented "unknown" placeholder is used — so the row is never silently lost. → Expected output: Hashed keys and unknown-member function used consistently across all domain tables. |
| --- | --- |

| B07 | No data is silently lost When a delivery references a customer not found in the hierarchy, the delivery still appears in the output — tagged as "unknown" and counted by the quality gate. Today such deliveries are silently dropped. → Expected output: All joins to master data use outer joins with unknown-member handling. Quality gate reports the unknown record count in every run. |
| --- | --- |

Section C — Configuration: Business Rules as Data

Objective: Every business rule that might change — market definitions, document classifications, SISO customer rules, currency policies, cut-off windows — lives in a managed configuration table, not in the code.

Benefit: Business teams can request rule changes (for example, adding a new SISO customer chain) through a governed data update instead of waiting for a development cycle. Configuration is versioned with history — you can always trace what changed, when, and why. This is also what makes multi-market scalability possible: same code, different configuration per market.

| C01 | Rules are rows, not code Every rule the business might change — SISO customer assignments, FX policies, market scope, document roles — exists as a row in a versioned configuration table with an owner and effective dates. Changing a rule is a configuration update, not a code deployment. → Expected output: Ten configuration tables populated with owner, valid-from/valid-to dates, and full change history. |
| --- | --- |

| C02 | No hidden numbers or dates Thresholds like "reload the last 5 months" or "billing cut-off is 3 days before month end" are named in configuration, not buried as literals in procedures. The run date is always a parameter — the pipeline never calls "today's date" internally. → Expected output: All thresholds, time windows, and dates traced to named configuration entries. Run date passed as a parameter on every procedure. |
| --- | --- |

| C03 | No copy-paste procedures If two procedures are more than 70% similar, they should be one procedure with a parameter. Today we have near-identical monthly and weekly SISO procedures that have already drifted, and customer hierarchy procedures that are copies with differences. → Expected output: Similarity check confirms no procedure pairs exceed 70% overlap. |
| --- | --- |

| C04 | One source per reference dataset Unit-of-measure conversions, exchange rates, financial ratios, plant locations, and calendars each come from exactly one master table or function. No procedure bypasses the master to read from a different source. → Expected output: Lineage confirms a single source per reference type across all procedures. |
| --- | --- |

| C05 | Configuration changes are governed Every change to a configuration table is versioned, peer-reviewed, and accompanied by a test case. Configuration is treated with the same rigour as code. → Expected output: Pull request trail for every configuration change. Test case confirming the rule change produces the expected output. |
| --- | --- |

Section D — Code Structure & Readability

Objective: Every stored procedure follows the same predictable 8-block structure in the same order. Code is readable, clearly named, and handles edge cases explicitly.

Benefit: Predictable structure means faster onboarding, easier debugging, and more reliable reviews. When every procedure looks the same, the CDRB reviews efficiently because reviewers know exactly where to look.

| D01 | Every procedure follows the 8-block template Every procedure contains the same 8 sections in order: Contract (what it does and what it produces), Context (market and run date), Config (read business rules), Extract (get changed data), Transform (apply logic), Quality Gate (validate before saving), Load (persist safely), Log (record result). This makes every procedure predictable. → Expected output: Template compliance confirmed. Header complete with purpose, grain, business key, owner, and version on every procedure. |
| --- | --- |

| D02 | One logging method throughout All status logging goes through a single shared utility. Errors are caught, logged with context, and re-raised — never silently ignored. Today three different logging utilities are used across the pipeline. → Expected output: Single logging utility confirmed across all procedures. No direct status writes or silent error handling. |
| --- | --- |

| D03 | Readable, focused transforms Each step in the transformation is named after the business concept it represents — for example, "invoice roles" or "open order buckets" — not generic labels like "base 1" or "step 3". No single procedure exceeds 400 lines; no single step exceeds 80 lines. → Expected output: Named business-concept transformation steps. Procedure and step size limits enforced and verified. |
| --- | --- |

| D04 | Explicit handling of missing data When a value is missing, the code explicitly decides what to do: use a default for measures, use the "unknown" placeholder for dimensions. Every conditional branch has a default path. No reliance on arithmetic involving NULL values that silently erases results. → Expected output: Unknown-member function for dimensions, safe default for measures, every conditional branch with an explicit default path. |
| --- | --- |

| D05 | Safe calculations Division by zero is handled safely. Rounding only happens at the final output, never in intermediate steps. When a conversion factor is missing, the result is flagged with a warning — not set to zero silently. → Expected output: Safe division used throughout. Rounding at final output only. Missing conversion factors produce a NULL with a logged warning. |
| --- | --- |

| D06 | Consistent naming KPI codes follow a standard pattern. The unit of measure and currency are stored as separate columns, not embedded in the KPI name. Legacy names are mapped as aliases in the registry for backward compatibility. → Expected output: Naming convention applied consistently. Legacy alias mapping documented in the registry. |
| --- | --- |

| D07 | Strict type checking The database engine validates data types. A text value being compared to a number is caught before the code runs, not silently producing wrong results at runtime. Code passes automated quality checks. → Expected output: Strict mode enabled. Automated linting clean on all procedures. |
| --- | --- |

| D08 | No ambiguous column selections Production code explicitly lists every column it needs. No "select everything" shortcuts that break when upstream tables change structure. → Expected output: Explicit column lists confirmed in all production transformation steps. |
| --- | --- |

Section E — Data Loading & Quality Assurance

Objective: Every data load is safe to re-run, validates quality before persisting results, and uses incremental processing to manage costs.

Benefit: Safe, repeatable loads mean no more situations where a failed job leaves a report table empty until the next run. Quality gates catch data issues before they reach dashboards — not after the business has already made decisions on incorrect numbers.

| E01 | Incremental by default The pipeline processes only what changed since the last successful run, using a shared watermark mechanism. Full reloads are supported but require explicit justification and are documented. → Expected output: Shared watermark utility used. Incremental processing confirmed for all procedures, with full-load reasons documented where applicable. |
| --- | --- |

| E02 | Loads are all-or-nothing Data is persisted using merge operations that either complete fully or leave the table unchanged. No more delete-then-insert patterns that leave tables empty when the insert step fails. → Expected output: All procedures use merge operations or atomic replacement. Zero delete-then-insert or truncate-then-insert patterns. |
| --- | --- |

| E03 | Quality check before every load Before data is persisted, the system validates: Are record identifiers unique? Are any required identifiers missing? Do referenced records exist in master data? Does the total reconcile against the source? These thresholds are configurable per market. → Expected output: Quality check report for every procedure run, with pass, warn, or fail status. Thresholds defined per market in configuration. |
| --- | --- |

| E04 | Deterministic de-duplication When duplicates exist in source data, the rule for which record wins is explicit, documented, and produces the same result every time regardless of processing order. → Expected output: De-duplication with business-priority ordering and a unique tie-breaker. Results verified to be identical across repeated runs. |
| --- | --- |

| E05 | Re-run safety Running the same pipeline twice on the same data produces identical results. This is tested automatically as part of the build process. → Expected output: Automated re-run test passing in the continuous integration pipeline. |
| --- | --- |

Section F — KPI Calculation, Rules & Accuracy

Objective: KPIs are calculated once in base units (kilograms and local currency), then expanded to other units, currencies, and calendar periods by a generic publish layer. Every KPI is registered in a single registry that is the source of truth.

Benefit: "Calculate once, expand many". Adding a new unit or currency becomes a configuration change, not a code change. This section incorporates SISO rules, calendar aggregation, and currency conversion — all treated as configuration-driven extensions of the KPI calculation framework.

| F01 | Calculate in base units only The KPI engine produces results in kilograms and local currency only. Conversion to cases, pieces, USD, and other calendar periods happens in the publish layer using generic, configuration-driven logic. This eliminates the current pattern of manually writing the same KPI calculation dozens of times for different units. → Expected output: KPI calculation layer outputs in kilograms and local currency only. Publish layer handles all unit, currency, and calendar expansions. |
| --- | --- |

| F02 | Mutually exclusive population splits When records are classified into groups — for example, orders classified as in-process, on credit hold, or post-dated — every record lands in exactly one group, and the sum of all groups equals the total. Today an order at the period boundary falls into no group and disappears from reports. → Expected output: One exclusive classification per split with a completeness check confirming the sum of parts equals the total. |
| --- | --- |

| F03 | Composite KPIs from the registry When a KPI is a combination of others — for example, net revenue = billing minus returns minus refusals — that formula is defined in the KPI registry and evaluated by a generic engine. The formula is not written as a SQL expression inside a procedure, where it might disagree with the dictionary. → Expected output: Registry component definitions for all composite KPIs. Generic composite evaluation engine confirmed. |
| --- | --- |

| F04 | Adjustments and FX policies declared, not hidden Which KPIs receive a net-revenue adjustment, which receive a manual correction, and which use which currency conversion rule are all declared per KPI in the registry and applied by a shared block. Currency policies — which period's exchange rate to use, actual versus budget rate → Expected output: Registry declarations for all adjustment types and FX policies. Single application block confirmed. |
| --- | --- |

| F05 | Additivity is declared Each KPI declares whether it can be summed (additive), must be counted distinctly, must be recomputed as a ratio from components, or represents a snapshot (last value only, not sum). A surrogate key is stored as a "count" measure and inventory stock can be accidentally summed across time periods. → Expected output: Additivity flag per KPI in the registry. Aggregation logic honours the declared additivity type. |
| --- | --- |

| F06 | Long (narrow) KPI model throughout the pipeline KPIs are stored as rows — one row per KPI code, unit of measure, and grain level — not as columns. Adding a new KPI or a new unit means adding rows to the registry, not altering table structures. Any wide-format view for consumption purposes is created at the semantic layer, not in the pipeline itself. → Expected output: Long model confirmed in KPI calculation and publish layers. Wide-format pivot only at the metric view layer. |
| --- | --- |

| F07 | Every KPI has a registered owner Each KPI has a registry entry with a named data steward and a link to the global canonical KPI definition. → Expected output: Registry entry with named owner for every KPI. Global definition link populated. |
| --- | --- |

| F08 | Dictionary generated from code, not maintained separately The KPI dictionary is an export from the registry — it cannot drift from the code. → Expected output: Automated dictionary export from the registry. Drift detection in the continuous integration pipeline flags any discrepancy. |
| --- | --- |

| F09 | SISO rules are data-driven SISO customer chain assignments and formula types (for example, use real sell-out data, use sell-in as a proxy, roll forward the previous stock value) are read from a configuration table with priority-based matching. No customer names exist in the code. Changing a SISO rule for a chain means updating one configuration row. The SISO calculation happens at daily grain only — weekly and monthly figures are derived by the calendar service, eliminating the current duplicated monthly and weekly procedures that have already drifted apart. → Expected output: SISO configuration table populated. Daily-grain SISO calculation confirmed. Calendar-driven aggregation for weekly and monthly periods. No customer names in any procedure. |
| --- | --- |

| F10 | Calendar aggregation from daily base All KPIs are computed at the lowest grain (daily) exactly once. Weekly, monthly, and custom period aggregations are derived by a calendar service using the additivity rules from the registry. → Expected output: Single daily-grain calculation. Calendar periods produced by the shared calendar function. No duplicated weekly or monthly calculation procedures. |
| --- | --- |

Section G — Performance & Cost Efficiency

Objective: The pipeline runs within defined time and cost budgets. Processing is proportional to data changes. Daily runs do not re-scan full history.

Benefit: Predictable runtimes mean the business gets fresh data on time. Cost efficiency means we can afford hourly refreshes for operational decisions without exceeding the compute budget.

| G01 | Runtime budgets defined and tested Each procedure completes within 15 minutes. The full daily pipeline chain completes within 2 hours. The publish layer completes within 20 minutes. These are verified against reference data volumes before production deployment. → Expected output: Benchmark results per procedure and per full chain on reference volumes. |
| --- | --- |

| G02 | Data physically organized for fast querying Tables are partitioned by market and date so queries only read relevant data. Efficient file scanning is confirmed in query execution plans. → Expected output: Partition and clustering strategy documented. Query execution plan evidence showing effective data pruning. |
| --- | --- |

| G03 | Processing proportional to change Daily runs process only data that changed since the last run — not the full history. Full-history scans are reserved for weekend backfill runs only. → Expected output: Bytes read versus bytes changed analysis confirming incremental efficiency. |
| --- | --- |

| G04 | Safe joins that do not multiply data Small reference tables are handled efficiently to avoid unnecessary data movement. Join safety checks catch unexpected data multiplication before it affects results. → Expected output: Row-ratio checks on all joins. No accidental record multiplication confirmed. |
| --- | --- |

| G05 | No slow patterns in critical paths No row-by-row processing or computationally expensive patterns in high-volume procedures. All critical operations use native, optimised capabilities. → Expected output: Review confirms no slow processing patterns in any critical-path procedure. |
| --- | --- |

| G06 | Storage maintenance automated Data compaction, file cleanup, and statistics refresh happen on a defined schedule — not manually or ad hoc. → Expected output: Table maintenance policies defined and scheduled. |
| --- | --- |

| G07 | Cost tracked per layer and market Compute costs are tagged by layer, market, and procedure so expensive operations can be identified and addressed, including monitoring dashboards + Genie. → Expected output: Cost tags applied. Budget tracking confirmed for all layers and markets. |
| --- | --- |

Section H — Scalability & Multi-Market Readiness

Objective: The pipeline works for any market without code changes. Adding a new market means adding configuration rows only.

Benefit: This is the ultimate proof of the architecture. If Brazil and Southern Cone can onboard through configuration alone, the design is truly scalable — and ready for global rollout beyond Latin America.

| H01 | Synthetic market test A fictional market ("ZZ") is added with configuration rows only — zero code changes. The pipeline runs correctly end-to-end for this fictional market. This is the blocker test for scalability. If this test fails, the architecture is not ready. → Expected output: Automated synthetic market test passing end-to-end in the continuous integration pipeline. |
| --- | --- |

| H02 | Volume scalability Processing three times the current data volume stays within one-and-a-half times the normal runtime budget. Stress Test required. → Expected output: Load test results on 3× data volume. |
| --- | --- |

| H03 | Market isolation / Multiple time zones … multiple small refreshes during day Multiple markets can run concurrently without interfering with each other. No shared temporary objects between market runs. Need to have a clear plan and refreshes to deal with markets in different time zones with sharing same pipines. → Expected output: Concurrent multi-market run test passing. |
| --- | --- |

| H04 | Flexible reprocessing for full or market level scope The pipeline supports reprocessing any date range via parameters — no manual intervention or custom scripts needed for backfills or corrections. → Expected output: Backfill runbook with parameter-driven reprocessing confirmed. |
| --- | --- |

Section I — Security & Compliance

Objective: The pipeline follows least-privilege access, protects sensitive data, and maintains a clear audit trail.

Benefit: Proper security means the pipeline passes audits without scrambling, and sensitive data — pricing, customer-level sales — is protected by design, not as an afterthought.

| I01 | Least-privilege access Pipeline jobs run with minimal permissions through service accounts. No personal credentials exist in code, configuration files, or comments. → Expected output: Access grants reviewed and documented. No personal credentials in any pipeline artefact. |
| --- | --- |

| I02 | No sensitive data in code No passwords, tokens, email addresses, or personal identifiers exist in source code, comments, or configuration files. → Expected output: Automated scan confirms no sensitive data in code. |
| --- | --- |

| I03 | Sensitive data classified and protected Columns containing sensitive information are tagged in Unity Catalog and the classification information is provided to the Data Governance team for registration in Ataccama. → Expected output: Classification tags applied. Row-level security confirmed for all sensitive columns. |
| --- | --- |

| I04 | Full audit trail Every table carries audit columns: when it was loaded, by which job run, for which market, and as part of which pipeline execution. → Expected output: Audit columns on all tables. Audit trail queryable in Unity Catalog and audit metadata provided to the Data Governance team for Ataccama registration. |
| --- | --- |

Section J — Testing & Reconciliation

Objective: The pipeline is tested like software — with unit tests, integration tests, and parallel-run reconciliation against the legacy system. All known defects are explicitly addressed.

Benefit: Automated testing is the safety net that catches regressions before they reach production. Parallel-run reconciliation proves the new pipeline produces correct numbers before the team cuts over and decommissions legacy procedures.

| J01 | Unit tests for shared functions, including automate testing in a periodical way to anticipate potential data issues Every shared function — weight conversion, currency lookup, unknown member handling — has automated unit tests with known inputs and expected outputs. For example: convert 1 pound → expect 0.4536 kg. → Expected output: Test suite with pass/fail results for every shared function. |
| --- | --- |

| J02 | Golden-data tests per procedure Each procedure has a fixed test dataset with expected outputs. The test runs automatically and catches any unintended change in behaviour. → Expected output: Golden-data test suite integrated into the continuous integration pipeline. |
| --- | --- |

| J03 | Parallel-run reconciliation The new pipeline runs alongside the legacy pipeline. KPI values are compared per KPI, per month, and per unit of measure. Differences beyond defined tolerances trigger investigation and resolution before cutover. → Expected output: Reconciliation report within agreed tolerance for all KPIs. All material differences investigated and documented. |
| --- | --- |

| J04 | Legacy defects tracked Each of the known production defects is either confirmed as resolved in the new pipeline or explicitly documented as a known, accepted difference. Should also keep a register to track repetitiveness. → Expected output: Defect register with resolution status for all confirmed defects. |
| --- | --- |

Section K — Observability & Operations

Objective: The pipeline is transparent — you can see what ran, when, how long it took, what data quality issues were found, and what failed. Failures trigger alerts to the right team.

Benefit: When something goes wrong, the team finds and fixes it in minutes rather than discovering it from a wrong report days later.

| K01 | Complete run logs Every run records status, rows read and written, watermark position, duration, and quality gate results. This information is accessible to any team member. → Expected output: Log sample per procedure showing all required fields. |
| --- | --- |

| K02 | Alerts for failures and quality issues When a job fails or a quality gate produces a warning, an alert goes automatically to the owning team. No failures are discovered through user complaints. → Expected output: Alert routing configuration confirmed for all failure and warning conditions. |
| --- | --- |

| K03 | Operational runbook for each job or scenario How to re-run a failed job, execute a backfill, roll back a load, and handle known issues is documented and accessible to the operational team. → Expected output: Runbook published and reviewed by at least one team member not involved in writing it. |
| --- | --- |

| K04 | Visible data lineage Any KPI value can be traced back through the pipeline layers to its source record. Lineage is visible in Unity Catalog within the Databricks environment and the Supplier shall provide complete lineage documentation to the Data Governance team for registration in Ataccama as the enterprise data catalogue. → Expected output: End-to-end lineage visible in Unity Catalog for all KPI output tables. Lineage documentation provided to the Data Governance team in the agreed format for Ataccama registration. → Expected output: End-to-end lineage visible in the data catalogue for all KPI output tables. |
| --- | --- |

Section L — Documentation & Governance

Objective: Every design decision is documented. Every deviation from the CDRB standard has an approved waiver. The KPI registry and dictionary are always in sync. Legacy procedures are mapped to their replacements.

Benefit: Documentation is what makes the architecture maintainable beyond the initial build team. When a new team member joins, they can understand every design choice and why it was made.

| L01 | Design note before build Every Tier 1 component — core domains, KPI engine procedures, publish layer — has an approved design note before development begins. Build does not start without it. → Expected output: Design note at gate G0 for all Tier 1 components. |
| --- | --- |

| L02 | Waivers are explicit and time-bound Any deviation from the CDRB standard has a documented waiver with a named owner and an expiry date. No permanent exceptions. → Expected output: Waiver log maintained. All waivers with owner and expiry confirmed. |
| --- | --- |

| L03 | Registry and dictionary always in sync Every code change that affects KPIs must update the registry in the same pull request. The KPI dictionary is generated from the registry — never maintained separately. → Expected output: Automated sync check in continuous integration confirms no drift between registry and dictionary. |
| --- | --- |

| L04 | Legacy mapping maintained Every one of the current procedures is mapped to its replacement in the new architecture — retired, absorbed, or replaced by a specific new procedure. → Expected output: Decommission mapping table maintained and published. |
| --- | --- |

Appendix B: CDRB Section-to-Month Mapping & Monthly Deliverable Schedule

This appendix maps the 12 CDRB quality review sections (A through L) to their primary review months across the full project timeline, and defines the specific deliverables, build activities, and quality gate milestones expected in each month. It is organized into two delivery stages: (1) Blueprint and Working Prototype, and (2) Build, Migration, Testing, UAT, Go-Live, Hypercare, and Transition to Support. Each month identifies which CDRB sections are under primary review, ongoing review, or preparation, establishing a clear, auditable schedule of when every quality criterion must be satisfied.

Stage 1: Blueprint & Working Prototype (November 2026 – January 2027)

|  | Section | Nov 26 | Nov Deliverables | Dec 26 | Dec Deliverables | Jan 2027 | Jan Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Architecture & Layering | ⬤ Prim. | Design end-to-end 8-block pipeline architecture. Define layer contracts and responsibilities. Map each block to named resources and CDRB criteria. | ○ Review | Review architecture against prototype build. Validate layer separation in exploration zone. Confirm one orchestrator per layer. | ○ Review | Final architecture review against working prototype. Confirm zero market-specific code branches. Architecture design note signed off. |
| B | Core Domain Design | Prep | Core Domain fit/gap analysis against (a) the LA existing design (include Brazil) and (b) the DP&E canonical core domain entities currently under development. The fit/gap shall be conducted under DP&E guidance and shall identify: the 6 canonical entities and their grain/key definitions; which entities are available from DP&E and can be consumed and validated by the Supplier; which entities require LA-specific extensions or configuration; and which entities DP&E determines the Supplier shall build under DP&E technical direction. The fit/gap output shall be reviewed and approved by DP&E before the Supplier proceeds with core domain build or consumption. | ⬤ Prim. | Build core domain entities in Databricks exploration zone. Declare identity and uniqueness per table. Market boundaries from configuration only. Standardize measurements (kg, local currency). | ○ Review | Validate core domains against full LA data. Confirm no data silently lost. Every record traceable. Core tables contain attributes only, no KPI outcomes. |
| C | Configuration: Business Rules | ⬤ Prim. | Convert business rules from GCP stored procedures and PBI DAX into configuration objects using AI-assisted extraction. Design 10 configuration table schemas. Harmonize manual files for MX and WC. | ○ Review | Review configuration tables populated with MX/WC rules. Validate no hidden numbers or dates in code. Confirm single source per reference dataset. | ○ Review | Full LA configuration tables populated (all 4 markets). Configuration changes governed with version history. Validate no copy-paste procedures remain. |
| D | Code Structure & Readability | ⬤ Prim. | Establish standard 8-block stored procedure template (Contract, Context, Config, Extract, Transform, Quality Gate, Load, Log). Define naming conventions and coding standards. | ○ Review | Review all prototype procedures against 8-block template. Confirm consistent naming. Verify explicit handling of missing data and safe calculations. | ○ Review | All prototype procedures follow template. No ambiguous column selections. Strict type checking confirmed. Run date passed as parameter on every procedure. |
| E | Data Loading & Quality | Prep | Design DQ framework architecture. Define quality gate rules for each pipeline stage. Design incremental processing with shared watermark mechanism. | ⬤ Prim. | Build DQ expectation rules at every quality gate. Implement merge-based loads (all-or-nothing). Build deterministic de-duplication. Implement watermark-driven incremental processing. | ○ Review | Validate DQ gates across all prototype pipelines. Confirm re-run safety (idempotent execution). Verify incremental processing on prototype data. |
| F | KPI Calculation & Accuracy | Prep | Initiate KPI inventory: code, kind, formula, filters, adjustments, units, calendars, additivity, owner, version for all 4 BUs. Identify harmonization conflicts. | ⬤ Prim. | Build KPI calculation engine for MX/WC common design. Calculate in base units only (kg, local currency). Define composite KPI rules in registry. Build SISO rules as data-driven configuration. | ⬤ Prim. | Extend KPI engine to full LA (BR, SC). KPI harmonization finalized with all 4 BU business owner sign-off. Calendar aggregation from daily grain confirmed. Every KPI has registered owner. Dictionary generated from code. |
| G | Performance & Cost Efficiency | — |  | ⬤ Prim. | Define runtime budgets per procedure (target ≤ 15 min each, ≤ 2 hrs full chain). Design partitioning by market and date. Design cost tagging by layer, market, procedure. Build storage maintenance policies. | ○ Review | Benchmark prototype: runtime per procedure, full chain duration. Validate partitioning and pruning in query plans. Confirm no slow patterns. Cost tags applied to prototype pipelines. |
| H | Scalability & Multi-Market | — |  | Prep | Plan synthetic market test (ZZ). Define configuration rows needed for fictional market. Design Brazil/SC config-only onboarding approach. | ⬤ Prim. | Prepare ZZ configuration rows for all 10 tables. Validate market identifier as parameter on every procedure. Confirm zero market-specific code branches. Scalability Playbook outline agreed. |
| I | Security & Compliance | — |  | ⬤ Prim. | Design least-privilege access model. Scan for sensitive data in code (passwords, tokens, PII). Design RLS at metric view layer. Define audit trail requirements. | ○ Review | Validate no sensitive data in code. Confirm pipeline service accounts with least-privilege. RLS design validated on prototype metric views. Audit trail structure confirmed. |
| J | Testing & Reconciliation | — |  | ⬤ Prim. | Establish unit test suite for all shared functions. Define golden-data test structure per procedure. Set up parallel-run reconciliation framework (new vs GCP legacy). Create legacy defect tracking register. | ○ Review | Run unit tests on prototype shared functions. Execute initial golden-data tests. Begin parallel-run reconciliation on MX/WC prototype outputs. Log legacy defects found. |
| K | Observability & Operations | — |  | ⬤ Prim. | Build run log schema (status, rows, watermark, duration, quality gate results). Build alert routing for failures and DQ warnings. Design monitoring dashboard wireframes (DQ, jobs, cost). Build per-market watermark tracking. | ○ Review | Validate run logs on prototype pipelines. Confirm alert routing configuration. Review monitoring dashboard wireframes. Validate watermark isolation per market. |
| L | Documentation & Governance | Prep | Establish documentation standards. Create design note template. Set up CDRB review register for all applicable items. | ⬤ Prim. | Document design notes for all Tier 1 components (core domains, KPI engine, configuration layer). Populate CDRB review register with status per section. Begin legacy procedure mapping. | ○ Review | All prototype design notes approved. Waivers documented (explicit and time-bound). KPI registry in sync with built procedures. CDRB review register fully populated. Blueprint sign-off documentation complete. |

⬤ Primary = primary quality gate this month    ○ Review = ongoing review    Prep = preparation activities    — = not yet active    QA = Quality environment gate    UAT = User acceptance gate    ✓ Sign-off = final acceptance

November 2026 — Foundations & Configuration Objects: Design end-to-end 8-block pipeline architecture (CDRB A). Convert business rules from GCP stored procedures and Power BI DAX into configuration objects using AI-assisted extraction (CDRB C). Establish the standard 8-block stored procedure template: Contract, Context, Config, Extract, Transform, Quality Gate, Load, Log (CDRB D). Manual files harmonization for Mexico and Wacam. KPI inventory initiated: code, formula, filters, units, calendars, owner. Core Domain fit/gap analysis against LA existing design. Design DQ framework architecture, jobs monitoring schema, cost tracking model, and alert routing rules (CDRB K design). Begin Databricks Academy and Pluralsight training assignments for technical teams. Develop Training Needs Assessment.

December 2026 — Solution Design & Sandbox Build: Full solution design finalization: base measures, loading/error handling, KPI engine, performance, scalability. Build foundations in Databricks exploration zone: config tables, shared functions, utilities. Core domains design readiness and build (CDRB B). AI-assisted redesign of market-level objects as configurable assets. KPI domain design and build end-to-end for Mexico and Wacam as common design (CDRB F). Data quality rules implemented at quality gates (CDRB E). Security review initiated: least-privilege access, no sensitive data in code (CDRB I). Testing framework established: unit tests for shared functions, golden-data test structure (CDRB J). Jobs monitoring and run log infrastructure built (CDRB K). Documentation and design notes for all Tier 1 components (CDRB L). Full LA manual files harmonization including Brazil and Southern Cone.

January 2027 — Full LA Prototype & Blueprint Sign-Off: Deliver the full Latin American working prototype in the Databricks exploration zone. KPI harmonization finalized for all four BUs with business owner sign-off (CDRB F). Full LA common design with pipelines and configurable steps for all domains. Synthetic market test preparation: configuration rows for fictional market ZZ defined (CDRB H). Performance benchmarking on prototype: each procedure ≤ 15 min target (CDRB G). Cost tracking tags applied to prototype pipelines. Global Scalability Playbook outline agreed. DQ monitoring dashboards wireframes validated. Blueprint Sign-Off milestone: all CDRB sections reviewed, design notes approved, prototype demonstrated to MONDELEZ stakeholders. Train-the-Trainer preparation initiated. Custom MONDELEZ training module development begins.

Stage 2: Build, Migration, Testing, UAT, Go-Live, Hypercare & Transition to Support (February – December 2027)

| CDRB Section | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A - Architecture & Layering | ⬤ | ⬤ | ○ | ○ | ○ | QA | UAT | ✓ | — | — | — |
| B - Core Domain Design | ⬤ | ⬤ | ○ | ○ | ○ | QA | UAT | ✓ | — | — | — |
| C - Configuration: Business Rules | ⬤ | ⬤ | ○ | ○ | ○ | QA | UAT | ✓ | — | — | — |
| D - Code Structure & Readability | ⬤ | ⬤ | ○ | ○ | ○ | QA | UAT | ✓ | — | — | — |
| E - Data Loading & Quality | ⬤ | ⬤ | ⬤ | ○ | ○ | QA | UAT | ✓ | — | — | — |
| F - KPI Calculation & Accuracy | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | QA | UAT | ✓ | — | — | — |
| G - Performance & Cost Efficiency | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | QA | UAT | ✓ | — | — | — |
| H - Scalability & Multi-Market | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | QA | UAT | ✓ | — | — | — |
| I - Security & Compliance | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | QA | UAT | ✓ | — | — | — |
| J - Testing & Reconciliation | Prep | Prep | ⬤ | ⬤ | ⬤ | QA | UAT | ✓ | — | — | — |
| K - Observability & Operations | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | QA | UAT | ✓ | ○ | ○ | ○ |
| L - Documentation & Governance | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | QA | UAT | ✓ | ○ | ○ | ✓ |

Legend:   ⬤ = Primary responsibility     ○ = Review / Support     Prep = Preparation phase     QA = Quality gate     UAT = User Acceptance gate     ✓ = Sign-off     — = Not active

February 2027 — Migration Begins (Exploration → Databricks AWS Dev): Full migration of 8-block pipeline from exploration zone to Databricks AWS Dev starts. Migrate all procedures following the standard template. Unit tests confirmed for all shared functions (CDRB J01). Golden-data tests per procedure (CDRB J02). Parallel-run reconciliation active: new pipeline vs legacy GCP (CDRB J03). Build DQ checks at every quality gate across all 8 blocks (CDRB E). Build jobs monitoring infrastructure: run logs, per-market watermarks (CDRB K01). Build cost tracking: tags by layer, market, procedure (CDRB G07). Build alert framework: failure, SLA-breach, DQ threshold alerts (CDRB K02). Configure scalability testing: Brazil and Southern Cone config-only onboarding begins (CDRB H). Runtime budget testing initiated (CDRB G01). Complete Databricks/Pluralsight certifications for technical team.

March 2027 — Migration Complete, Scalability Proven: Full migration finishes. All procedures migrated to Databricks AWS Dev with 8-block template compliance. Unit testing complete for all shared functions and procedures (CDRB J). Performance evidence documented: each procedure ≤ 30% less from existent steps min, full chain 30% less from existent steps hours (CDRB G01). Reconciliation confirmed: new vs legacy pipeline, KPI-by-KPI, market-by-market, within tolerance (CDRB J03). Brazil and Southern Cone onboarded through configuration only, zero code changes (CDRB H). All CDRB design notes approved (CDRB L01). Waivers explicit and time-bound (CDRB L02). Registry and dictionary in sync (CDRB L03). Legacy mapping complete (CDRB L04). CDRB final sign-off on migration. Build operational runbook for each job (CDRB K03). Deploy monitoring and cost dashboards in DEV. Train-the-Trainer sessions delivered to BU trainers.

April 2027 — Project Team Testing in DEV: Full project team testing in Development environment. All 8 pipeline blocks, all configuration tables, all KPI domains, all metric views, and all Genie spaces tested end-to-end. Quality gate confirmation: all CDRB checklist items accepted, reconciliation within tolerance, all known issues logged and resolved (CDRB J). Security review: least-privilege access (CDRB I01), no sensitive data in code (CDRB I02), RLS confirmed (CDRB I03), audit trail complete (CDRB I04). Performance confirmation: CDRB G07 cost monitoring dashboards live, compute cost within budget. DQ dashboards, jobs monitoring dashboards, and cost dashboards fully operational in DEV. Validate all alerting end-to-end: simulate failures, DQ breaches, SLA violations, cost overruns. Validate runbook: execute single-market re-run, backfill, rollback. Internal gate: project team certifies solution ready for business users.

May–June 2027 — Full User Testing in DEV: Business users from all four markets (Mexico, Wacam, Brazil, Southern Cone) test the complete solution (between 30-50 users per Business Unit / Function). KPI validation against legacy reports. Genie space usability testing. AI/BI dashboard validation. CDRB H01 scalability test: synthetic market ZZ onboarded via configuration only, passes all 8 blocks end-to-end with zero code changes. Global Scalability Playbook draft completed with 20 validated config-only onboarding examples (CDRB H, L). Triage and resolution: all critical and high-priority items addressed before promotion to Quality. Comprehensive Train-the-Trainer program delivered: trainers certified and conduct supervised pilot sessions. All custom training materials finalized (guides, videos, FAQs). Training portal launched with Databricks Academy + Pluralsight + custom content.

July 2027 — Integration Testing in Quality Environment (between 50-100 users per Business Unit / Function).: Solution promoted from DEV to Quality environment. Full integration testing: end-to-end pipeline execution, cross-domain data flows, multi-market concurrent runs (CDRB H market isolation confirmed). Performance and volume testing against CDRB G benchmarks in QA. Security review in QA: CDRB I01-I04 re-confirmed. CDRB J reconciliation: final parallel run between QA pipeline and legacy GCP. All monitoring dashboards (DQ, jobs, cost) promoted to QA and validated. Alerts verified in QA environment. Cost tracking confirmed against actual QA Databricks billing.

August 2027 — User Acceptance Testing in Quality Environment (between 100-200 users per Business Unit / Function).: Full UAT with business stakeholders from all four markets. Final business sign-off on KPI accuracy, dashboard correctness, Genie response quality, and data lineage (CDRB F final). Parallel-run: QA pipeline vs legacy GCP, final reconciliation and acceptance. CDRB L governance artifacts confirmed: documentation complete, dictionary current, lineage confirmed. Certified MONDELEZ trainers lead end-user training sessions across all four BUs. Training effectiveness feedback collected. Go/no-go decision for production release agreed with MONDELEZ Digital Analytics Leadership.

September 2027 — Go-Live: Production readiness confirmed: all CDRB sections A–L signed off, all testing evidence documented, all reconciliation within tolerance. Operational readiness: runbooks published (CDRB K03), alerts configured (CDRB K02), cost monitoring live (CDRB G07), data lineage visible (CDRB K04). Go-live for MATRIX-AI across all four Latin American markets. All monitoring dashboards activated in Production from day one. Legacy GCP decommission plan activated (CDRB L04). Global Scalability Playbook published (Appendix C).

October–December 2027 — Go-live completed and Hypercare, Stabilization & Transition to Support: Active monitoring during Hypercare: DQ regressions, runtime anomalies, cost trends across all four markets. Alert threshold tuning based on production patterns (first 30 days). Runbook validated in production: single-market re-run, backfill, rollback executed. Final cost baseline report delivered: cost per market/month, per layer, projected annual run cost. Formal knowledge transfer to AMS and Product teams following MONDELEZ methodology. Shadowed support period: Supplier works alongside AMS and Product teams. Documentation governance finalized: CDRB L final sign-off. Dual sign-off gate: AMS team lead and Product team lead confirm KT complete. Formal Transition to Support. Supplier released only upon both sign-offs.

Appendix C: Automated Full Project Quality Review and Evidence

This appendix defines the automated quality review and evidence framework that the Supplier shall implement to provide continuous, objective, and auditable proof that the MATRIX-AI platform code, architecture, and design conform to the CDRB quality standards and the agreed product vision. The framework leverages industry-standard static analysis tools (SonarQube), AI-powered code review agents, and automated reverse-engineering validation to eliminate subjective assessments and ensure that every deliverable is machine-verified against the contractual design specifications. This framework operates continuously throughout all project phases, not as a one-time audit.

C.1 — Static Code Analysis (SonarQube)

Actions: Deploy a SonarQube instance (or equivalent MONDELEZ-approved static analysis platform) connected to the project repository from Phase 1 onward. Configure quality gates aligned with CDRB Section D (Code Structure and Readability) criteria. Define custom rules enforcing: (a) the 8-block stored procedure template compliance (Contract, Context, Config, Extract, Transform, Quality Gate, Load, Log) with mandatory block headers detected via pattern matching; (b) naming convention enforcement for KPI codes, table names, column names, configuration keys, and shared functions per the agreed naming standard; (c) no hardcoded market identifiers, environment references, dates, thresholds, or business rules in code (CDRB C01, C02); (d) no duplicate or near-duplicate procedures exceeding 70% similarity (CDRB C03); (e) safe calculation patterns (division-by-zero protection, null handling) enforced on all arithmetic operations (CDRB D05); (f) no sensitive data (passwords, tokens, PII) in code or configuration files (CDRB I02); (g) explicit column selections only, no SELECT * patterns in production code (CDRB D08); and (h) strict type checking with no implicit conversions in critical paths (CDRB D07). Every code commit must pass the SonarQube quality gate before merge. No exceptions without a CDRB-approved waiver. Expected Outcome: Zero critical or blocker issues in production code. All code conforms to the 8-block template with machine-verified compliance. No hardcoded values, no duplicate logic, no security vulnerabilities detected. Success Measurement: SonarQube dashboard showing: (i) quality gate pass rate = 100% on all merged code; (ii) zero critical/blocker issues open; (iii) technical debt ratio below agreed threshold; (iv) code coverage on shared functions ≥ 80%; (v) zero security hotspots classified as high or critical. Dashboard accessible to MONDELEZ at all times.

C.2 — AI-Powered Code Review & Optimization

Actions: Deploy AI code review agents (e.g., GitHub Copilot Code Review, Amazon CodeGuru, or equivalent MONDELEZ-approved AI tools) integrated into the code review workflow. Configure AI agents to perform: (a) semantic analysis of every stored procedure to verify that business logic matches the KPI registry definition (formula, filters, aggregation rules, unit-of-measure handling) ensuring the code implements what the registry declares (CDRB F03, F08); (b) performance optimization recommendations identifying slow patterns, unnecessary full-table scans, inefficient joins, and row-by-row processing in critical paths (CDRB G05); (c) configuration completeness check verifying that every market-specific parameter is sourced from configuration tables and no business rule is embedded in code (CDRB C01); (d) idempotency verification confirming that every procedure produces identical results when re-run on the same data (CDRB E05); (e) documentation quality check ensuring every procedure has a complete contract block (purpose, sources, targets, version history, dependencies) per CDRB D01; and (f) cross-procedure dependency analysis mapping data lineage from source ingestion through core domains, KPI calculation, publication, to metric views, flagging any broken or undeclared dependencies. Expected Outcome: AI-augmented reviews catch logic mismatches, performance anti-patterns, and configuration gaps before human review, reducing review cycle time and increasing defect detection rate. Every procedure is verified against its KPI registry entry programmatically. Success Measurement: (i) AI review coverage = 100% of all procedures before CDRB review; (ii) AI-detected issues resolved before merge; (iii) KPI registry-to-code match rate = 100% (every registered KPI formula verified in code); (iv) zero performance anti-patterns in production code; (v) AI review findings log maintained and accessible to MONDELEZ.

C.3 — Automated Reverse Engineering & Architecture Conformance

Actions: Implement automated reverse-engineering tools that parse the complete production codebase and generate: (a) an actual architecture diagram showing all pipeline components, their layer assignments, data flows, and dependencies, which is then compared against the approved 8-block architecture design (CDRB A01, A02); any deviation is flagged as a conformance violation; (b) a complete data lineage map from every source table through every transformation to every KPI output and metric view, verified against the declared lineage in Unity Catalog (CDRB K04); (c) a configuration dependency matrix showing every procedure's configuration table references, confirming that all market-specific logic is externalized (CDRB A03, C01); (d) a market parameterization audit verifying that every procedure accepts market_id as a parameter and that no market-specific code branches exist anywhere in the codebase (CDRB A03); (e) an environment portability check confirming no hardcoded database names, schema references, or environment-specific paths exist in any procedure (CDRB A04); and (f) a KPI registry reconciliation report matching every registered KPI (code, formula, filters, units, calendars) against the actual implementation in code, flagging any drift between the registry and the built solution. Expected Outcome: Machine-generated proof that the as-built solution matches the as-designed architecture. Any architectural drift, undeclared dependencies, or configuration gaps are detected automatically before phase gate reviews. Success Measurement: (i) architecture conformance score = 100% (zero deviations between design and implementation); (ii) data lineage coverage = 100% (every KPI output traceable to source); (iii) market parameterization audit = 100% pass (zero market-specific code branches); (iv) environment portability = 100% (zero hardcoded references); (v) KPI registry-to-code drift = zero (registry and implementation in perfect sync). Reports generated automatically and available to MONDELEZ before every CDRB review session.

C.4 — Automated Pipeline Testing & Continuous Reconciliation

Actions: Build an automated testing and reconciliation pipeline that runs continuously in the CI/CD environment: (a) unit test suite executing automatically on every code commit for all shared functions, with test results published to a dashboard (CDRB J01); (b) golden-data tests per procedure: known inputs produce known outputs, validated automatically on every build (CDRB J02); (c) automated re-run safety test: run every procedure twice on the same data and verify identical results (CDRB E05); (d) parallel-run reconciliation engine comparing new pipeline KPI outputs against legacy GCP outputs, KPI-by-KPI, market-by-market, month-by-month, with automated tolerance checking and variance flagging (CDRB J03); (e) synthetic market test automation: the fictional market ZZ is tested end-to-end on every major build, with automated verification that zero code changes were required (CDRB H01); and (f) volume scalability test: automated 3x data volume test confirming runtime stays within 1.5x budget (CDRB H02). Expected Outcome: Every build is automatically validated against quality, accuracy, and scalability criteria. Regressions are detected within minutes, not days. The reconciliation engine provides continuous proof that the new pipeline matches legacy outputs. Success Measurement: (i) unit test pass rate = 100% on every build; (ii) golden-data test pass rate = 100%; (iii) re-run safety test = 100% pass; (iv) parallel-run reconciliation within agreed tolerance for all KPIs, all markets, all months; (v) synthetic market ZZ test passing on every major build with zero code changes; (vi) all test results published to a dashboard accessible to MONDELEZ in real time.

C.5 — Evidence Package & Continuous Audit Trail

Actions: Maintain a continuously updated evidence package that serves as the auditable proof of quality for every CDRB review, phase gate, and final acceptance: (a) SonarQube quality gate history showing pass/fail status for every code commit with trend analysis; (b) AI review findings log with resolution status for every flagged issue; (c) architecture conformance reports generated before every CDRB session; (d) KPI registry-to-code reconciliation reports generated weekly; (e) parallel-run reconciliation results with variance analysis, updated after every pipeline run; (f) unit test and golden-data test results dashboard updated on every build; (g) synthetic market test evidence (configuration rows, execution logs, code diff, KPI outputs) archived per build; (h) performance benchmark results (runtime, cost, volume scalability) updated monthly; and (i) security scan results (SonarQube security hotspots, sensitive data scan, access audit) updated weekly. (j) Data Governance metadata package status: confirmation log showing all metadata submissions to the Data Governance team (dataset descriptions, lineage documentation, DQ rule definitions, data classification tags, and KPI registry exports) with Data Governance team receipt acknowledgement and any open items. Updated at each phase gate. All evidence is stored in a shared repository accessible to MONDELEZ at all times and is preserved for a minimum of 24 months after project completion. Expected Outcome: At any point during the project, MONDELEZ can access machine-generated, objective evidence of the solution's quality, accuracy, and conformance to the agreed design. No deliverable acceptance depends solely on subjective human assessment. Success Measurement: (i) evidence package completeness = 100% (all items above available before every phase gate); (ii) evidence freshness: all reports generated within the last 7 days at any review point; (iii) zero phase gate approvals without a complete, current evidence package; (iv) MONDELEZ auditors confirm evidence package is sufficient for independent verification.

C.6 — Governance & Tooling Requirements

The Supplier shall deploy and maintain all automated quality tools at its own cost as part of the fixed-price engagement. MONDELEZ shall provide: (a) repository access for SonarQube integration; (b) compute resources for CI/CD pipeline execution in the agreed Databricks environments; and (c) read access to legacy GCP pipeline outputs for parallel-run reconciliation. The Supplier shall not disable, bypass, or lower the threshold of any automated quality gate without a CDRB-approved waiver documented in the waiver register (CDRB L02). MONDELEZ retains the right to audit any automated tool configuration, quality gate threshold, or test coverage metric at any time. The Supplier shall provide a monthly Automated Quality Summary report to the Weekly 4-Box governance session, covering: SonarQube quality gate status, AI review coverage, architecture conformance score, reconciliation results, test pass rates, and any open waivers.

Data quality and lineage tooling will leverage Ataccama (MDLZ enterprise standard) and Databricks Unity Catalog as the primary governance platforms, consistent with the POET-Tooling Approach and mandatory Ataccama integration directive. Where a documented gap exists between pipeline-native DQ execution and Ataccama connectivity during the build phases, the Supplier may deploy the following specific interim accelerators:

(i) Databricks-native DQ expectation rules (CDRB E03, K01) — executing inline within stored procedures at the Quality Gate section, with results structured for automated Ataccama sync;

(ii) Unity Catalog metadata registration — automated tagging of dataset descriptions, column lineage, and data classification at procedure deployment, structured for Ataccama catalogue import;

(iii) KPI registry-to-code reconciliation engine — automated drift detection between the KPI registry and implemented code (CDRB K04), with outputs exportable to Ataccama lineage format.

C.7 — Enterprise Data Governance Integration (Ataccama)

Ataccama is the MONDELEZ enterprise standard for Data Quality governance, Data Catalog, and Data Lineage. The Supplier shall ensure alignment between the Databricks-native DQ implementation and the Ataccama governance layer as follows:

(a) DQ Rule Registration: All data quality rules implemented in the Databricks pipeline (CDRB E03, K01) shall be registered in Ataccama as the authoritative governance record. Databricks runtime DQ checks generate inline quality results that are synced to Ataccama.

(b) Metadata Cataloguing: All datasets, tables, and KPI definitions created within the MATRIX AI platform shall be catalogued in Ataccama, complementing the Unity Catalog registration.

(c) Data Lineage Alignment: Data lineage generated by Unity Catalog (CDRB K04) shall be visible in Ataccama. The Supplier shall ensure lineage from source ingestion through KPI output is traceable in both Unity Catalog and Ataccama.

(d) MONDELEZ Dependency: Ataccama integration requires MONDELEZ to provide: (i) Ataccama instance access and API credentials; (ii) enterprise DQ rule templates and cataloguing standards; (iii) technical guidance on Ataccama-Databricks connectivity. If Ataccama access or connectivity is not available during the build phases, the Supplier shall implement DQ rules in Databricks with metadata structured for future Ataccama import, and the Ataccama sync shall be executed during Hypercare or as a post-Go-Live activity.

- If Ataccama access or connectivity is not available during the build phases, the Supplier shall implement DQ rules in Databricks with metadata structured for automated Ataccama import, following the schema and API specifications provided by the MDLZ Data Governance team (Dmitry Maleykovich / Paul Danifo). This interim approach is consistent with POET Walk phase allowances, which permit gap-fill tooling provided it does not introduce a parallel governance platform. The Ataccama sync shall be completed no later than the end of the Hypercare phase (December 2027), and its completion shall be a condition of final program acceptance. The Supplier shall report Ataccama sync readiness at every phase gate from User Testing (May 2027) onwards

(e) Accelerator Sunset Plan: Each interim accelerator identified in this section shall include a documented transition plan to full Ataccama integration. The transition plan shall specify: (i) the specific Ataccama capability that will replace the accelerator function; (ii) the data format and API mapping required for migration; (iii) the target transition date, which shall be no later than the end of the Hypercare phase (December 2027); and (iv) acceptance criteria confirming Ataccama has assumed the function. Upon Ataccama assuming each function, the corresponding interim accelerator shall be decommissioned. The Supplier shall present the accelerator sunset status at each phase gate as part of the Data Governance metadata package.

Appendix D: Global Scalability Playbook — Detailed Requirements

The Global Scalability Playbook is a mandatory June 2027 deliverable, produced during user testing in the Development environment (Phase 3). Its purpose is to provide definitive, evidence-based proof that the MATRIX-AI platform architecture is globally scalable — that any new market can onboard through configuration alone, with zero code changes, and that the design has been validated end-to-end through the CDRB quality framework. The Playbook shall be accepted by MONDELEZ before the solution is promoted to the Quality environment. The following sections define the required content, acceptance criteria, and evidence standards for each chapter of the Playbook.

Section 1 — Architecture Overview

This section shall document how the 8-block pipeline architecture enforces configuration-driven market differences. It must clearly distinguish what changes per market (configuration rows in the market-keyed tables) versus what remains identical across all markets (code, stored procedure templates, shared utility functions, KPI calculation engine, and the generic publish layer). The section shall include: (a) a visual architecture diagram showing all 8 blocks (Source Ingestion, Harmonization & Standardization, Core Domain Build, Market Configuration Layer, KPI Calculation Engine, KPI Publication, Semantic/Consumption Layer, Consumption Layer) with data flow arrows and layer contracts; (b) a mapping table showing each block's inputs, outputs, configuration dependencies, and CDRB sections governing it; (c) an explanation of the canonical core domain entities and why they are source-agnostic; (d) the standard 8-block stored procedure template (Contract, Context, Config, Extract, Transform, Quality Gate, Load, Log) with annotated examples; and (e) a clear statement of the configuration-only onboarding principle: new markets add rows to configuration tables, not branches to code.

Section 2 — Configuration-Only Onboarding Checklist

This section shall provide a step-by-step operational guide for adding a new market to the platform using configuration alone. The checklist must cover all configuration table types with specific instructions for each: (1) Market Scope Definitions — how to register a new market identifier, define its data perimeter, and set the run-scope parameter; (2) Document Type Classifications — how to map the new market's data types to the canonical classification; (3) Reason Code Roles — how to assign reason codes (examples like returns, refusals, free goods) for the new market; (4) Item Category Roles — how to configure product category classifications; (5) Cut-Off Rules — how to define period-end cut-off windows and open-order treatment; (6) Open Order Bucket Conditions — how to configure order aging buckets; (7) FX Conversion Policies — how to register the new market's local currency and FX rate sources; (8) Business Rules — how to configure sell-in/sell-out matching rules, customer chain mappings, and calculation parameters; (9) KPI Registry Entries — how to register market-specific KPI definitions, formulas, filters, units of measure, calendars, additivity flags, and ownership; and (10) Quality Rule Thresholds — how to set DQ gate thresholds for the new market's data characteristics. Each checklist step must include: the configuration table name, required columns, example values from an existing market, validation criteria, and a sign-off checkbox.

Section 3 — Synthetic Market Test Evidence (CDRB) … Use USA or Canada as fictional market test with true data

This section shall provide complete, auditable evidence from the ZZ fictional market test — the definitive proof that the architecture is globally scalable. The ZZ market is a fictional market with synthetic data that has never existed in the pipeline. It must be onboarded exclusively by adding configuration rows, with absolutely zero code changes to any stored procedure, shared function, or pipeline component. The evidence package must include: (a) Pre-test baseline — documented state of the codebase (Git commit hash or equivalent) before ZZ configuration rows are added, proving no code was modified; (b) Configuration rows added — complete listing of every row inserted into each of the configuration tables for market ZZ, with business justification for each value; (c) Synthetic test data — description of the test dataset injected for market ZZ (volume, date range, data domains covered, edge cases included); (d) End-to-end pipeline execution log — full run log showing ZZ processed successfully through all 8 pipeline blocks, with status, row counts, duration, and quality gate results per block; (e) KPI output validation — ZZ KPI outputs verified against expected values for all KPI domains, all units of measure, and all calendar aggregations; (f) Metric view confirmation — Unity Catalog metric views correctly expose ZZ data with row-level security applied; (g) Genie validation — at least 3 natural-language (English, Spanish and Portuguese) queries against ZZ data returning correct, governed answers; (h) Post-test code diff — automated diff confirming zero code changes between pre-test and post-test codebase; and (i) CDRB sign-off — formal sign-off by the CDRB that the synthetic market test passes all applicable criteria across Sections A through L. If the synthetic market test fails, the architecture is not ready for global rollout, and the Supplier must remediate before proceeding.

Section 4 — Handling Unique KPI Types

This section shall document how the platform accommodates new markets whose KPI calculations are not currently in the registry. Two paths must be defined with decision criteria for each: Path A (Configuration Extension) — extending the KPI registry with new entries and configuring composite rules within the existing calculation engine, requiring no code changes. This path covers scenarios such as new units of measure, new calendar aggregation periods, new FX conversion policies, new matching rules, and new composite KPI formulas built from existing base measures. The Playbook must document at least examples of Path A extensions from the Latin American deployment. Path B (Engine Extension) — extending the KPI calculation engine with a new parameterized function when a genuinely novel calculation type is required that cannot be expressed through the existing registry schema. This is a contained change: the new function follows the standard 8-block template, is registered in the shared function library, and is unit-tested. It does not create a code fork or market-specific branch. The Playbook must document the governance process for approving a Path B extension, including who requests it, who approves it, what CDRB sections apply, and how the extension is validated to ensure it does not break existing markets.

Section 5 — Estimated Effort & Timeline per New Market

This section shall provide a documented, evidence-based estimate for onboarding any new market to the platform. The estimate must be grounded in actual data from the Latin American deployment and must include: (a) Configuration effort — number of configuration rows required per table type, based on averages from Brazil, Southern Cone, Mexico, and Wacam onboarding; (b) Data ingestion setup — estimated effort to establish source connections and ingestion pipelines for typical source system profiles (SAP, third-party market data, manual files); (c) KPI harmonization cycle — expected duration for KPI inventory, business rule alignment workshops, conflict resolution, and formal sign-off with business owners; (d) Testing cycle — expected duration for unit testing, golden-data tests, and parallel-run reconciliation for the new market; (e) CDRB review scope — which of the 12 CDRB sections require full review versus lightweight review for subsequent market onboardings; (f) Parallel-run duration — expected duration for running the new market's pipeline alongside legacy systems before cutover; (g) Total elapsed time — end-to-end estimated timeline from onboarding initiation to production go-live, broken down by phase; and (h) Resource requirements — estimated team composition and FTE allocation for a typical new market onboarding. The estimates must be presented in a table format with minimum, expected, and maximum ranges, and must include assumptions and dependencies.

Section 6 — Governance for Global Rollout

This section shall define how the CDRB quality framework applies to future market onboardings beyond Latin America. It must cover: (a) CDRB applicability matrix — which of the 12 sections (A through L) require full review, lightweight review, or are pre-approved for subsequent market onboardings that follow the configuration-only path; (b) Acceptance gate definition — the specific criteria that constitute a "pass" for each new market go-live, including minimum quality gate thresholds, reconciliation tolerance levels, and synthetic test requirements; (c) Change governance — how configuration changes for one market are reviewed to ensure they do not affect other markets' KPI accuracy or pipeline performance; (d) Registry governance — how the KPI registry is maintained as the global source of truth when multiple regions are simultaneously operational, including conflict resolution procedures for KPI definition disagreements between regions; (e) Escalation path — the decision rights and escalation path for resolving cross-region architectural decisions (e.g., a new region requests a Path B engine extension that could affect existing markets); and (f) Continuous improvement — how lessons learned from each new market onboarding feed back into the Playbook, configuration checklists, and CDRB criteria for the next onboarding.

Section 7 — 20 Validated Configuration-Only Onboarding Examples

This section shall document at least twenty (20) true, validated examples demonstrating configuration-only market onboarding, using North America as the reference target. Each example must be a discrete, end-to-end scenario covering a specific data domain or KPI type, and must include: (a) Scenario description — what business domain, KPI, or data flow is being onboarded; (b) Configuration changes — the exact configuration rows added or modified across the 10 configuration table types; (c) Code change status — explicit confirmation of zero code changes (automated diff evidence); (d) Pipeline execution — run log showing successful end-to-end processing through all 8 blocks; (e) KPI output — verified output values against expected results; and (f) CDRB criteria met — which CDRB sections were validated by this example. Examples must collectively cover all  business domains in scope and demonstrate both Path A (registry extension) and Path B (engine extension) scenarios where applicable.

Section 8 — Acceptance Criteria for the Playbook

The Global Scalability Playbook shall be accepted by MONDELEZ when all of the following conditions are met: (a) All seven content sections (1 through 7) are complete and have been reviewed by the CDRB; (b) The synthetic market test (Section 3) passes with zero code changes and full CDRB sign-off; (c) new market onboarding evidence (Section 4) confirms configuration-only deployment with reconciliation within agreed tolerance; (d) At least 20 validated examples (Section 8) are documented with automated code-diff evidence; (e) The effort estimation model (Section 6) is reviewed and endorsed by MONDELEZ project leadership; (f) The governance model (Section 7) is approved by MONDELEZ D&A leadership and the Global D&A Product team; and (g) The Playbook is published in the project documentation repository and accessible to all stakeholders. Rejection of the Playbook shall require written justification identifying specific deficiencies.