## Slide 1: Weekly Status Update date

## Slide 2
AGENDA – 90 MINUTES MEETING
Section | Produced by | Content | Time
Bravos / High fives | Project Lead | Named recognition with the standard legend: above & beyond · outstanding performance · innovation · milestone win · precision · teamwork · delivery success. Keep it — it is the only page in the pack that builds the team. | 15 min
High Risks | PMO with risk owners | Risk # · Title · Score (movement, e.g. VH → H) · Status with dated update · Owner · Due · Impact on which workstream. Closed risks struck through and kept visible for one week. | 
Change / Decision Log | PMO with change owners | DEC or CHG · ID · Title · Description · Owner · Confirmed on · Workstream · Category (tier) · Dated status. Every decision taken anywhere in the governance model lands here. | 
High-Level Timeline | PMO | Gantt by sub-wave in weekly buckets, with phase colors, tollgates, and the three May 2027 go-lives marked. Status per objective: Complete / On track / Off track / Blocked / Not started. | 
Program Status Report — Overall | Project Lead | Executive summary page. Status headline (% completion, movement week on week, overall RAG and the one reason for it) · milestone status table by sub-wave with estimated end, % complete with movement, RAG and a summary line · Very High and High risks repeated. This is the page that gets forwarded. | 10 min
Workstream 4-box | Sub-wave leads | Workstream detailed update … total of updates = 11 | 5 min each 55 min total
Q&A | Project Lead | Open for Q&A session | 10 min

## Slide 3
BRAVOS
Free text

## Slide 4
HIGH RISKS / Dependencies
ID Number | Risk description and impact assessment | Mitigation / Resolution update | Workstreams impacted | Status | Owner | Due
 |  |  | W01 – Mexico DSD | G |  | 
 |  |  | W01 – Market Share | A |  | 
 |  |  | W01 – Promotions | C |  | 
 |  |  | W01 – Shipments | NS |  | 
 |  |  | W02 – Perfect / Right Store | R |  | 
 |  |  | W02 – OTC / Inventory / EPOS / Lenses / PVC / VR | G |  | 

## Slide 5
CHANGE / DECISION LOG
Change Number | Change Title | Change Description / Impact | Decision made | Workstreams impacted | Owner | Due | Status
 |  |  |  | W01 – Mexico DSD |  |  | Approved
 |  |  |  | W01 – Market Share |  |  | Rejected
 |  |  |  | W01 – Promotions |  |  | On-hold
 |  |  |  | W01 – Shipments |  |  | 
 |  |  |  | W02 – Perfect / Right Store |  |  | 
 |  |  |  | W02 – OTC / Inventory / EPOS / Lenses / PVC / VR |  |  | 

## Slide 6: Executive timeline (Plan in a Page)
Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Integration Testing
(~75 per BU / Function)
Biz Impact
Training design & Build
Training
Sign-off
Train-Trainers
UAT
(~200 per BU / Function)
Go
Live
HYPERCARE
ADOPTION
SUSTAIN
1. OTC / EPOS / Master Data
Production Readiness
Full Setup
Interactive final build and improvements , defects fixes, monitoring, quality improvements, changes, cost monitoring, jobs scheduling, data governance, refresh validation, consumption layers, KPIs logics fine tuning, scalability / reusability confirmation, Global rollout playbook
2. MDLZ INVENTORY & SHIPMENT
3. MARKET MEASUREMENT AND PROMOTIONS
4. MEXICO DSD
PROTOP. TESTING
5. BRAZIL PVC / VR / EASTER
6. STORE OPERATIONS (PERFECT & RIGHT STORE)
7. SNACKSYNC
FULL CODE MIGRATION
TO DATABRICKS
AWS
PROJECT
UNIT TESTING
DBX-AWS DEV
KEY USER TESTING IN
DBX-AWS DEV
(~20 PER BU/FUNCTION)
WE ARE HERE!
Phase 01 – Blueprint & Build into Databricks-GCP Dev
Phase 02
Migration
DBX– AWS
Dev
Phase 03 – Testing & Improvements into
DBX–AWS Dev
Phase 03 – Acceptance into
DBX–AWS QA
Phase 04 – Production
DBX–AWS Prod
Phase 05 – Hypercare
DBX–AWS Prod
Business Commitment 20%-35%
Business Commitment 30%-40%

## Slide 7
PROGRAM STATUS REPORT – EXECUTIVE UPDATE
G | G |  | G | G | G | G | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
EXECUTIVE STATUS HEADLINE
Date | Nov 4TH, 2026
Workstreams | Phase | Status | Status Summary | Risk / Mitigation update
1. OTC / EPOS / Master Data | Blueprint / Prototype build | G |  | 
2. MDLZ INVENTORY & SHIPMENT | Blueprint / Prototype build | A |  | 
3. MARKET MEASUREMENT AND PROMOTIONS | Blueprint / Prototype build | C |  | 
4. MEXICO DSD | Blueprint / Prototype build | NS |  | 
5. BRAZIL PVC / VR / EASTER | Blueprint / Prototype build | R |  | 
6. STORE OPERATIONS (PERFECT & RIGHT STORE) | Blueprint / Prototype build | G |  | 
7. SNACKSYNC | Blueprint / Prototype build |  |  | 
EXECUTIVE STATUS HEADLINE
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 8
1. OTC / EPOS / Master Data
G | G |  | G | G | G | G | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Oct 30th, 2026
Key Accomplishments
Development team established Team members assigned to Data Products/ Workstreams MDLZ accounts requested Team onboarding started
Data Engineering Lead | Name
Gen BI Lead | Name
Type | Number | Description / Mitigation | Status | Owner | Due
Key upcoming activities & decisions
MDLZ accounts setup for new team members Team onboarding completed. Prototype: KPI Inventory analysis and harmonization
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Jan 31st
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Market Share Lead | Fabio A., Marvi M, Maria B. Gustavo P.
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 9
2. MDLZ INVENTORY & SHIPMENT
G | G |  | G | G | G | G | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Oct 30th, 2026
Key Accomplishments
Development team established Team members assigned to Data Products/ Workstreams MDLZ accounts requested Team onboarding started
Data Engineering Lead | Name
Gen BI Lead | Name
Type | Number | Description / Mitigation | Status | Owner | Due
Key upcoming activities & decisions
MDLZ accounts setup for new team members Team onboarding completed. Prototype: KPI Inventory analysis and harmonization
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Jan 31st
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Market Share Lead | Name
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 10
3. MARKET MEASUREMENT AND PROMOTIONS
G | G |  | G | G | G | G | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Oct 30th, 2026
Key Accomplishments
Development team established Team members assigned to Data Products/ Workstreams MDLZ accounts requested Team onboarding started
Data Engineering Lead | Name
Gen BI Lead | Name
Type | Number | Description / Mitigation | Status | Owner | Due
Key upcoming activities & decisions
MDLZ accounts setup for new team members Team onboarding completed. Workshops preparation. Development: Core Domain analysis. Lift and shift possibility consideration
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Jan 31st
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Market Share Lead | Name
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 11
4. MEXICO DSD
G | G |  | G | G | G | G | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Oct 30th, 2026
Key Accomplishments
Development team established Team members assigned to Data Products/ Workstreams MDLZ accounts requested Team onboarding started
Data Engineering Lead | Name
Gen BI Lead | Name
Type | Number | Description / Mitigation | Status | Owner | Due
Key upcoming activities & decisions
MDLZ accounts setup for new team members Team onboarding completed. Workshops preparation. Development: Core Domain analysis. Lift and shift possibility consideration
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Jan 31st
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Market Share Lead | Name
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 12
5. BRAZIL PVC / VR / EASTER
G | G |  | G | G | G | G | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Oct 30th, 2026
Key Accomplishments
Development team established Team members assigned to Data Products/ Workstreams MDLZ accounts requested Team onboarding started
Data Engineering Lead | Name
Gen BI Lead | Name
Type | Number | Description / Mitigation | Status | Owner | Due
Key upcoming activities & decisions
MDLZ accounts setup for new team members Team onboarding completed. Prototype: KPI Inventory analysis and harmonization
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Jan 31st
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Market Share Lead | Name
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 13
6. STORE OPERATIONS (PERFECT & RIGHT STORE)
G | G |  | G | G | G | G | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Oct 30th, 2026
Key Accomplishments
Text ….
Data Engineering Lead | Name
Gen BI Lead | Name
Type | Number | Description / Mitigation | Status | Owner | Due
Key upcoming activities & decisions
1.1 Ingestion from Source System • 1.1.1 Inventory and lock multi-BU source system ingestion scope (BRD, HLD, IIT): Confirm source systems, tables, grain, volumetrics, refresh windows and access per BU; classify each source as global-common vs BU-specific; [CDRB: E03, G01, J01] • 1.1.2 Harvest and validate existing GCP ingestion design as build baseline: Extract production GCP ingestion logic per source; validate against current business behavior; [CDRB: E03, G01, J01] 1.2 Ingestion from Manual Files • 1.2.1 Inventory and standardize manual files across the 4 BUs (BRD, HLD, IIT): Inventory all manual files across 4 BUs; standardize file formats, naming conventions and delivery schedules; [No direct CDRB ref] • 1.2.2 Harvest existing GCP manual file ingestion design as build baseline: Extract production GCP manual file processing logic; validate against current behavior; classify as carry-forward, refactor or retire; [No direct CDRB ref] 1.3 Core Domain • 1.3.1 Assess Core Domain 1.0 and document target 2.0 vision (CDM & LDM): Assess current Core Domain 1.0; document the target 2.0 vision for CDM (Conceptual Data Model) and LDM (Logical Data Model); [CDRB: B01, C01, G01, H01] • 1.3.2 Harvest existing GCP data model and transformation logic as design baseline: Extract production GCP data model and transformation logic; validate against business behavior; classify as carry-forward, refactor or retire; [CDRB: B01, C01, G01, H01] 1.4 KPIs (Core & Derived) and Metric View • 1.4.1 Inventory existing KPIs and calculation logic across the 4 BUs: Inventory all existing KPIs across 4 BUs including code, formula, filters, adjustments, units, calendars, additivity, owner, version; [CDRB: F01, F02, F03, F07, F08] • 1.4.2 Harvest existing GCP KPI calculation logic (stored procedures, Power BI DAX): Extract production KPI calculation logic from GCP and Power BI; validate against business definitions; identify discrepancies between BUs; [CDRB: F01, F02, F03, F07, F08] 1.5 Gen BI Consumption (AI/BI, Genie, Knowledge Assistant and Supervisor) • 1.5.1 Inventory dashboards, users, personas and business decisions across 4 BUs: Inventory all existing dashboards, active users, personas and business decisions; classify by frequency, criticality and persona; [CDRB: A12] 1.6 Change Management & Training • 1.6.1 Develop Training Needs Assessment and Training Strategy per persona: Develop Training Needs Assessment identifying all user personas (commercial analysts, KAMs, field sales, trade marketing, technical ops, data engineer… [No direct CDRB ref] • 1.6.2 Map stakeholders, personas and business impacts across 4 BUs: Map all stakeholders per BU; identify business impacts of platform migration; classify change impact per persona; create stakeholder engagement plan [No direct CDRB ref] 1.7 Data Governance / Architecture / Quality • 1.7.1 Define OSA 2.0 governance framework aligned to CDO and global standards: Define the OSA 2.0 governance framework aligned to CDO and global standards; integrate with POET governance model; [CDRB: E03, G01, G07, K01, K02, K03, K04]
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Jan 31st
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Market Share Lead | Name
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 14
7. SNACKSYNC
G | G |  | G | G | G | G | G
Overall | Trending |  | Budget | Schedule | Scope | Issues/ Risk | Resources
Date | Oct 30th, 2026
Key Accomplishments
Text ….
Data Engineering Lead | Name
Gen BI Lead | Name
Type | Number | Description / Mitigation | Status | Owner | Due
Key upcoming activities & decisions
1.1 Ingestion from Source System • 1.1.1 Inventory and lock multi-BU source system ingestion scope (BRD, HLD, IIT): Confirm source systems, tables, grain, volumetrics, refresh windows and access per BU; classify each source as global-common vs BU-specific; [CDRB: E03, G01, J01] • 1.1.2 Harvest and validate existing GCP ingestion design as build baseline: Extract production GCP ingestion logic per source; validate against current business behavior; [CDRB: E03, G01, J01] 1.2 Ingestion from Manual Files • 1.2.1 Inventory and standardize manual files across the 4 BUs (BRD, HLD, IIT): Inventory all manual files across 4 BUs; standardize file formats, naming conventions and delivery schedules; [No direct CDRB ref] • 1.2.2 Harvest existing GCP manual file ingestion design as build baseline: Extract production GCP manual file processing logic; validate against current behavior; classify as carry-forward, refactor or retire; [No direct CDRB ref] 1.3 Core Domain • 1.3.1 Assess Core Domain 1.0 and document target 2.0 vision (CDM & LDM): Assess current Core Domain 1.0; document the target 2.0 vision for CDM (Conceptual Data Model) and LDM (Logical Data Model); [CDRB: B01, C01, G01, H01] • 1.3.2 Harvest existing GCP data model and transformation logic as design baseline: Extract production GCP data model and transformation logic; validate against business behavior; classify as carry-forward, refactor or retire; [CDRB: B01, C01, G01, H01] 1.4 KPIs (Core & Derived) and Metric View • 1.4.1 Inventory existing KPIs and calculation logic across the 4 BUs: Inventory all existing KPIs across 4 BUs including code, formula, filters, adjustments, units, calendars, additivity, owner, version; [CDRB: F01, F02, F03, F07, F08] • 1.4.2 Harvest existing GCP KPI calculation logic (stored procedures, Power BI DAX): Extract production KPI calculation logic from GCP and Power BI; validate against business definitions; identify discrepancies between BUs; [CDRB: F01, F02, F03, F07, F08] 1.5 Gen BI Consumption (AI/BI, Genie, Knowledge Assistant and Supervisor) • 1.5.1 Inventory dashboards, users, personas and business decisions across 4 BUs: Inventory all existing dashboards, active users, personas and business decisions; classify by frequency, criticality and persona; [CDRB: A12] 1.6 Change Management & Training • 1.6.1 Develop Training Needs Assessment and Training Strategy per persona: Develop Training Needs Assessment identifying all user personas (commercial analysts, KAMs, field sales, trade marketing, technical ops, data engineer… [No direct CDRB ref] • 1.6.2 Map stakeholders, personas and business impacts across 4 BUs: Map all stakeholders per BU; identify business impacts of platform migration; classify change impact per persona; create stakeholder engagement plan [No direct CDRB ref] 1.7 Data Governance / Architecture / Quality • 1.7.1 Define OSA 2.0 governance framework aligned to CDO and global standards: Define the OSA 2.0 governance framework aligned to CDO and global standards; integrate with POET governance model; [CDRB: E03, G01, G07, K01, K02, K03, K04]
RAID (Risk, Action, Issue, Decision) with Mitigation Plan/Owner & Due date
Phase | Tasks & Summary | Status | Due
Blueprint / Working Prototype | Scope, design & build working prototype | G | Jan 31st
Migration to new DBX | Migrate all pipelines to Databricks AWS | N.S. | Mar 31st
Project Unit Testing | Unit & parallel-run testing in DEV | N.S. | Apr 30th
Business Testing | End-to-end validation by product team | N.S. | July 02nd
Integration Testing | Cross-domain integration testing in QA | N.S. | July 30th
User Acceptance | Business stakeholder UAT across 4 BUs | N.S. | Sept 03rd
Production Readiness | Technical go-live readiness sign-off | N.S. | Sept 24th
Go-live | Business go-live across all markets | N.S. | Oct 11th
Hypercare | Support, parallel run & transition to BAU (Business as Usual) | N.S. | Dec 31st
Upcoming Milestones Status Updates
MDLZ Market Share Lead | Name
Notes: Key Accomplishments
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Ingestion
TDDs, etc
Domains
TDDs etc
Dashboards
TDDs etc
Governance
Timeline, Cadence and SteerCo meetings, TG Sign offs, Lessons Learned, Change management
Key upcoming decisions & events
List accomplishments throughout project execution (Scoping, Funding, timeline, Partner Onboarding, Change management, security, master data, ingestion, domains, data governance, test/go live/hypercare/T2S readiness.
Upcoming TG Reviews and SteerCo Meetings.

## Slide 15: Q&A

## Slide 16: 1. PROTOTYPE OTC / EPOS
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25
. Inventory and harmonize KPI definitions across Wacam & Mexico with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
AI / BI, Genie Agent, Knowledge, Orchestration
BR & SC
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
. Establish federated integration from GCP Harmonized Layer into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for WC & MX
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
SonarQube and AI audit review
. AI/BI dashboard prototypes per persona for MX & WC
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
. Inventory and harmonize KPI definitions across Brazil & S. Cone with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Onboard BR & SC onto KPI engine proven with WC & MX, config-only, zero code changes
. Market-specific rules (currency, UOMs, hierarchies) via parameterized config tables
. Refresh Metric Views from certified WC & MX template, proving global reusability
. KPI-by-KPI reconciliation vs legacy GCP to confirm calculation parity
. Validates parametrization design for future market rollouts
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
Travel Argentina
Travel Brazil
Travel Argentina
Travel Brazil
Travel Argentina

## Slide 17: 2. MDLZ INVENTORY & SHIPMENT
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across full LA with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
(+WC + MX + SC)
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for full LA
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
SonarQube and AI audit review
. AI/BI dashboard prototypes per persona for full LA
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
Travel Brazil
(+WC + MX + SC)

## Slide 18: 3. MARKET MEASUREMENT AND PROMOTIONS
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across full LA with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
(+WC + MX + SC)
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for full LA
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
SonarQube and AI audit review
. AI/BI dashboard prototypes per persona for full LA
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
Travel Brazil
(+WC + MX + SC)
. Ingest FMT datasets with validated schemas, volumetrics, and refresh cadence with DQ gate controls applied
. Onboard new Market Measurement & Promo sources into GCP Harmonized
. Federated integration into Databricks
. Metadata and lineage registered in Unity Catalog

## Slide 19: 4. MEXICO DSD
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across MEXICO DSD with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for MEXICO DSD
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
SonarQube and AI audit review
. AI/BI dashboard prototypes per persona for MEXICO DSD
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
Travel Mexico

## Slide 20: 5. BRAZIL PVC / VR / EASTER
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across BRAZIL with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for BRAZIL
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
. AI/BI dashboard prototypes per persona for BRAZIL
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
. Ingest FMT datasets with validated schemas, volumetrics, and refresh cadence with DQ gate controls applied
. Onboard new Market Measurement & Promo sources into GCP Harmonized
. Federated integration into Databricks
. Metadata and lineage registered in Unity Catalog
Reverse-engineer Brazil PVC/VR/Easter GCP pipelines, stored procs, and DAX logic
Document calculation flows, business rules, and exception handling
Extract GCP production reconciliation baselines
Map legacy logic to 8-Block Architecture and KPI engine design
Formalize undocumented rules and workarounds into config objects
Travel Brazil
Travel Brazil
Travel Brazil

## Slide 21: 6. STORE OPERATIONS (PERFECT & RIGHT STORE)
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
. Inventory and harmonize KPI definitions across full LA with Global D&A inventory
. Align calculation logic, UOMs, and aggregation rules to single regional KPI dictionary + business context
. Map KPI placement: pre-calculated vs on-demand per consumption need
. Inventory existing dashboards, reports, personas, cases
. Full LA demo: AI/BI, Genie, Knowledge Assistant, Supervisor across 4 BUs
. Benchmark evaluation: accuracy, latency, and guardrails across all personas
. RLS validation per BU, persona, and market hierarchy
. DQ, Job Observability, and Cost Monitoring dashboards production-ready
. Agent orchestration: routing, handoffs, and tools live
. Amazon Quick MCP integration for enterprise agent connectivity
. Regression benchmark: no accuracy loss post BR & SC onboarding
Data Quality: Automated DQ gate at ingestion: completeness, freshness, schema-drift, type enforcement; Quality thresholds and tolerance rules per source and BU; Quarantine and rejection handling with full audit trail; Reconciliation baselines from GCP production; DQ scoring and alerting embedded in pipeline orchestration
Job Observability: End-to-end pipeline monitoring: status, duration, SLA, and failure alerts; Centralized job dashboard across ingestion, transformation, and KPI layers; Automated retry/restart with idempotency per pipeline stage; Anomaly detection: runtime deviations, volume spikes, data gaps; Full lineage traceability from source to KPI for root-cause analysis
Cost Monitoring: Real-time cost tracking per pipeline, BU, and environment; Budget baselines and automated threshold alerts from prototype phase; Cluster sizing and job scheduling optimization to control spend; Cost attribution by workstream (ingestion, KPI, AI/BI) and market; Monthly benchmarking vs GCP legacy for TCO comparison
Demonstrate
Data Quality,
Job Observability,
Cost Monitoring,
Refresh schedule,
Data Governance,
Live Documentation
Travel Brazil
(+WC + MX + SC)
. Establish federated integration from GCP Harmonized into Databricks GCP
. Optimize manual files into single similar entities before core domains
. Define parameterized mapping layer from GCP Harmonized tables to target Agnostic Core Domain entities
. Run fit / gap analysis against Core Domain agnostic with DP&E, and build
. Build parameterized Market Configuration Layer with versioned, market-keyed rules for full LA
. Deploy configuration-driven KPI Calculation Engine, no hard-coded BU logic
. Design and publish certified Metric Views in Unity Catalog with row-level security
. AI/BI dashboard prototypes per persona for full LA
. Genie Agent spaces with curated business context and example queries
. Benchmark evaluation (250+ questions) with accuracy tuning cycles
. Knowledge Assistant build with indexed business documents
. Agent orchestration (routing, tools, handoffs)
SonarQube and AI audit review
SonarQube and AI audit review
Refresh: Weekend: full historical refresh across all layers and BUs; Nightly (Mon-Fri): incremental rolling 3-month window refresh; Daily workday: scheduled intraday refresh with automated watcher; Dependency-aware orchestration, downstream triggers post-validation; Freshness monitoring and staleness alerts per refresh tier
WE ARE HERE!
Data Governance: Unity Catalog: centralized metadata, lineage, and access control; RLS and column masking per BU, persona, and sensitivity tier; Dataset and KPI registration in MDLZ governance framework (Ataccama); Data ownership model: stewards per domain with BU accountability; Weekly automated security scans and access reviews; Full audit trail on access, transformations, and policy changes
Documentation: 8-Block Pipeline Architecture (HLD) signed by DaaS Architecture Lead; Living playbooks: Ingestion, Market Config, KPI Engine, Semantic Layer, Consumption; Auto-generated data dictionaries and lineage from Unity Catalog; CDRB evidence package: SonarQube, AI reviews, conformance, reconciliation; Approved design before build for all Tiers; Live Knowledge transfer docs creation for MDLZ AMS handover
. Ingest FMT datasets with validated schemas, volumetrics, and refresh cadence with DQ gate controls applied
. Onboard new Market Measurement & Promo sources into GCP Harmonized
. Federated integration into Databricks
. Metadata and lineage registered in Unity Catalog
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Evaluate MC1 ingestion and standardization via SnackSync in GCP
Assess data quality, completeness, and schema consistency for Store Ops
Document SnackSync logic, refresh cadence, and known gaps
Federated integration from SnackSync into Databricks Harmonized Layer

## Slide 22: WORKSHOPS IN A PAGE
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
Travel Brazil
Travel Argentina
Travel Brazil
Travel Argentina
Travel Brazil
Travel Argentina
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Mexico
Travel Brazil
Travel Brazil
Travel Brazil
Travel Brazil
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
Travel Brazil
(+WC + MX + SC)
OTC / EPOS
Inventory/ Shipment
Market Measurement / Promotions
Mexico DSD
Brazil PVC/ VR/ Easter
Store Operations

## Slide 23: 7. SNACKSYNC
Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22
WE ARE HERE!