## Executive agenda
MATRIX-AI / OSA 2.0 — Technical Blueprint Workshop Agenda, 19–23 October 2026
Sessions run 09:30–12:30 and 13:30–17:30. Detailed agenda (input, output, team members, approval) in the sheet 'Workshop details'.
phase 1 scope
please take it from the doc that we created
Assumptions | No new KPIs and no KPI adjustments within the POC.
Executive agenda
Day | Date | Session | Workshop agenda | Executive summary | Comments
Day 1 | 2026-10-19 | Morning | Design Rules & Patterns | Introduce the workshop team and present the agenda Align the design rules and patterns | Covered by materials provided by MDLZ (doc link)
Day 1 | 2026-10-19 | Afternoon | CDRB Rules and Governance Establishment | Align coding principles Align CDRB work principles and governance (frequency, scope, SLA) Draft / establish the CDRB team | Covered by materials provided by MDLZ (doc link)
Day 2 | 2026-10-20 | Morning | TO-BE Pipeline Blocks 1–4 | Align source ingestion and the silver layer Align core domains and the market configuration layer Align new data sources and manual files harmonization | Covered by materials provided by MDLZ (doc link)
Day 2 | 2026-10-20 | Afternoon | Pipeline Blocks 5–8 + Build Sequence | Align KPI calculation and publication Align metric views, Genie and dashboards Agree refresh strategy and build sequence | Covered by materials provided by MDLZ (doc link)
Day 3 | 2026-10-21 | Morning | WS-1: Mexico & Wacam (Nov & Dec) | Plan the WS-1 POC for the full MX & WC KPI scope Agree November and December deliverables Assign resources per track | Covered by materials provided by Lingaro(doc link)
Day 3 | 2026-10-21 | Afternoon | WS-2: Brazil & Southern Cone (Nov & Dec) | Plan reverse engineering and market visits Agree the KPI inventory review and sign-off Agree the POC on 20–30 selected KPIs | Covered by materials provided by Lingaro(doc link)
Day 4 | 2026-10-22 | Morning | Program Governance | Agree program governance: Steering Committee, change requests, communication, Jira task management, timeline maintenance | Covered by materials provided by Lingaro(doc link)
Day 4 | 2026-10-22 | Afternoon | Lingaro Readiness, Resources & Meeting Calendar | Validate Lingaro ways of working and use cases Confirm named resources, travel and environments Agree the meeting calendar and 2 Nov commitments | Covered by materials provided by Lingaro(doc link)
Day 5 | 2026-10-23 | Morning | Blueprint Sign-off, Scalability Playbook & Roadmap | Agree the blueprint sign-off scope Agree the Global Scalability Playbook outline and the February–September 2027 roadmap | Covered by materials provided by Lingaro(doc link)
Day 5 | 2026-10-23 | Afternoon | SOW Review & Final Agreement | Review the SOW, agree in- and out-of-scope items and reach final agreement | Covered by materials provided by Lingaro(doc link)

## Workshop details
Day | Date | Hour | Subjects |  | MDLZ Team | Details | Input | Output | Approval
Day 1 | 2026-10-19 | Morning 09:30–13:30 | Design Rules & Patterns | Ewelina G. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Introduction : Issues to agree: • Introduce the workshop team from Lingaro and MDLZ: names, roles and which days each person attends • Present the agenda for Days 1–5: sessions, expected outputs and decisions needed each day | • Participant list (Lingaro and MDLZ) • Workshop agenda (Days 1–5) | • Workshop team introduced • Agenda for the five days presented and confirmed
Day 1 | 2026-10-19 | Morning 09:30–13:30 | Design Rules & Patterns | Ewelina G. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | 10 design rules : Issues to agree: • Accept or amend each rule: layers with contracts · market as parameter · clean core domains · one procedure template · readable transforms · idempotent, quality-gated loads · calculate once, expand late · registry as dictionary · lowest grain once · prove it • Base units (kg, local currency) and daily lowest grain for every KPI • "Prove it": scope of golden-data tests and parallel-run reconciliation; monitoring of runtime, failures and cost per run | • 10 design rules (v07, Day 1) | • 10 design rules agreed as the shared quality standard
Day 1 | 2026-10-19 | Morning 09:30–13:30 | Design Rules & Patterns | Ewelina G. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Patterns to carry forward and anti-patterns : Issues to agree: • The 12 Mexico practices to carry forward (headers, exception handling, hashed keys, de-dup, watermark loads, merge loads, narrow SISO model, multi-calendar, data-driven adjustments, SISO rule docs, safe division, wrapper procedure) • v07 lists Mexico practices only: confirm whether Wacam has additional or conflicting patterns • Mapping of anti-patterns to CDRB criteria | • MX & WC code review findings | • Carry-forward patterns confirmed • Anti-patterns mapped to CDRB criteria
Day 1 | 2026-10-19 | Afternoon 14:30–17:30 | CDRB Rules and Governance Establishment | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Clean-code principles : Issues to agree: • P1–P6: core domains first · rules as data · one KPI engine and registry · one procedure template · idempotent and incremental · fix known defects while rebuilding • P6: are all 21 known defects in scope for the POC, or only those touching POC KPIs? | • 6 principles (v07) • List of 21 production defects | • Clean-code principles agreed
Day 1 | 2026-10-19 | Afternoon 14:30–17:30 | CDRB Rules and Governance Establishment | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | CDRB review sections A–L : Issues to agree: • Criteria per section and the expected output for each • KEEP / IMPROVE / AVOID verdict for each current practice • Inconsistency in v07: the text announces "13 review sections" but lists 12 (A–L); Section C is named "Business Rules as Data" in one place and "Configuration & Master Data" in another | • CDRB sections A–L (v07) • MX & WC code review findings | • Code review register with verdicts • Design requirements list agreed
Day 1 | 2026-10-19 | Afternoon 14:30–17:30 | CDRB Rules and Governance Establishment | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Pull request checklist : Issues to agree: • Checklist adopted as the formal definition of done per section A–L • Waiver process: who can grant a waiver and how it is recorded | • Draft PR checklist (v07) | • CDRB checklist formally adopted
Day 1 | 2026-10-19 | Afternoon 14:30–17:30 | CDRB Rules and Governance Establishment | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | CDRB governance and architecture review : Issues to agree: • Frequency: twice a week during the POC • Members and chair: named people for Chair · Functional Leads MX & WC · Data Architect · Data Modeler · Senior Data Engineer · Governance, Quality & Testing Lead · KPI Steward • Scope: architecture and design decisions, work checked against the CDRB rules (A–L), deviations from the 10 design rules • SLA: decision within 2 business days of submission; escalation to SteerCo • CDRB rules A–L revised by Marek with MoSCoW priority: Must and Should fixed by the project team; Could and Won't depending on complexity and timeline • Validity: this format applies until POC completion and can be eased for the development phase | • CDRB roles (v07) • Governance Proposal draft • CDRB rules A–L with MoSCoW (Marek) | • CDRB governance agreed: frequency, members, scope, SLA, MoSCoW rules • CDRB team constituted
Day 2 | 2026-10-20 | Morning 09:30–13:30 | TO-BE Pipeline Blocks 1–4 | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Target architecture: blocks and layers : Issues to agree: • Inconsistency in v07: the Day 2 text describes a "5-layer model" (Ingestion → Core Domains → Shared Building Blocks → KPI Engine → Publish) alongside the 8 blocks. The Solution Blueprint on Databricks maps the 8 blocks onto 5 Unity Catalog layers (bronze, silver, gold, publish, consumption) with block 4 as a configuration plane. Agree one model • Inconsistency in v07: Block 3 calls the core domains a "gold layer"; the Solution Blueprint on Databricks places them in silver | • v07 Day 2 • Solution Blueprint on Databricks: target architecture | • One agreed layer model and block-to-layer mapping
Day 2 | 2026-10-20 | Morning 09:30–13:30 | TO-BE Pipeline Blocks 1–4 | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Block 1 — Source ingestion (two scenarios) : Issues to agree: • Ingestion contract content (recommended: schema hash, market code, row-count floor, freshness timestamp) • Federated GCP bridge: latency, refresh frequency, cost, and retirement trigger (recommended: native freshness equals federated freshness for 5 business days) • Ownership: DP&E builds both scenarios, OSA team owns requirements and validation | • MX & WC source system inventory (15 Oct) • Solution Blueprint on Databricks: S-01, S-02, decisions table | • Ingestion scenarios, contract and retirement trigger agreed
Day 2 | 2026-10-20 | Morning 09:30–13:30 | TO-BE Pipeline Blocks 1–4 | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Blocks 2–3 — Silver layer and core domains : Issues to agree: • D1–D6 entities and grain; the Solution Blueprint on Databricks corrects D4 to schedule-line grain and keys D5 / D6 so partial deliveries and invoices are kept • Which of the 9 new domains and delivery domains (Sell-in, Sell-out, Market analytics, Customer P&L, Shipments) are in the POC • Customer P&L: requirements and owner (no requirement in v07); Shipment as own domain or part of D3 • DP&E product dependencies: OTC, EPOS, Distributor, LAFPA ready 1 Nov; Shipments and Market analytics to confirm by 16 Nov • Inconsistency in v07: Day 4 describes the core domains as "6 canonical entity types (OTC, EPOS, SISO, Master Data, Manual Files, Market Share)", which differs from D1–D6 on Day 2 | • Existing MX & WC domain tables • core domains review (16 Oct) • Solution Blueprint on Databricks: silver core data domain model | • Core domain list and grain agreed • POC domain scope and DP&E dates confirmed
Day 2 | 2026-10-20 | Morning 09:30–13:30 | TO-BE Pipeline Blocks 1–4 | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Block 4 — Market configuration layer : Issues to agree: • Number of configuration tables: 10 in v07 vs 22 in five groups in the Solution Blueprint on Databricks • How the business edits configuration (recommended: Git-backed review app instead of direct table edits) • Ownership of locked vs flexible rows: Global KPI Owner, Local KPI Steward, data architect | • Business rules found in MX & WC procedures • Solution Blueprint on Databricks: F-16 market configuration layer | • Configuration layer scope and ownership agreed
Day 2 | 2026-10-20 | Morning 09:30–13:30 | TO-BE Pipeline Blocks 1–4 | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | New data & harmonization : Issues to agree: • Snacksync and MDLZ inventory: in POC scope or later • Brazil VR and PVC: purpose, scope and sources (open items in the Solution Blueprint on Databricks) • Nielsen market share without components (recommended: store percentages as snapshots, request components where available) • Manual files harmonization design | • Manual files inventory (14 Oct) • Solution Blueprint on Databricks: Brazil domains, decisions table | • Source scope decisions logged • Manual files harmonization design agreed
Day 2 | 2026-10-20 | Afternoon 13:30–17:30 | Pipeline Blocks 5–8 + Build Sequence | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Block 5 — KPI calculation : Issues to agree: • KPI procedures by domain: sell-in order/invoice, delivery, targets, SISO daily base and rules engine, inventory, shipment • Output shape: narrow KPI rows (v07) / component fact, never finished ratios (Solution Blueprint on Databricks) • SISO KPIs depend on both sell-in and sell-out being live • POC adjustment: engine scope is the full MX & WC KPI set plus the 20–30 BR & SoCo KPI pool; no new KPIs or KPI adjustments | • MX & WC KPI inventory • Solution Blueprint on Databricks: KPI registry and fact model | • KPI engine scope and output shape agreed
Day 2 | 2026-10-20 | Afternoon 13:30–17:30 | Pipeline Blocks 5–8 + Build Sequence | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Block 6 — KPI publication and the long vs wide decision : Issues to agree: • Long format in the pipeline, wide pivot at the metric view layer • Wide pivots generated from the registry or defined manually; any need for wide format before metric views; DirectQuery performance impact • Where calendar aggregation lives: publish step 5 in v07 vs metric-view measures in the Solution Blueprint on Databricks | • v07 Block 6 discussion questions • Solution Blueprint on Databricks: S-10, decisions table | • Storage format and publish steps agreed
Day 2 | 2026-10-20 | Afternoon 13:30–17:30 | Pipeline Blocks 5–8 + Build Sequence | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Block 7 — Metric views : Issues to agree: • Which KPIs and metric views are in scope for Wave 1 ("Wave 1" is not defined in v07) • Views per domain or per persona (Solution Blueprint on Databricks: one Universal view per domain plus one Product view per BU × persona) • Metadata, descriptions and synonyms required per view; where the Genie prompt-to-KPI mapping lives | • v07 Block 7 design decisions • Solution Blueprint on Databricks: metric view design | • Wave 1 scope and metric view model agreed
Day 2 | 2026-10-20 | Afternoon 13:30–17:30 | Pipeline Blocks 5–8 + Build Sequence | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Block 8 — Consumption and refresh : Issues to agree: • Priority Genie spaces for Wave 1: personas and KPI domains • Report migration: phased or big-bang; Power BI vs AI/BI for migrated dashboards • Governance of metric view changes: who approves a new or changed view • Three-tier refresh: weekend full rebuild · nightly 3-month · hourly 15-day | • v07 Block 8 design decisions • Current MX & WC dashboards and users | • Consumption plan and refresh strategy agreed
Day 2 | 2026-10-20 | Afternoon 13:30–17:30 | Pipeline Blocks 5–8 + Build Sequence | Mariusz M. Vadzim N. Marek K. Michal H. Malgorzata M. Harish R. Radoslaw U. |  | Phase build sequence : Issues to agree: • Phases: Foundations → Core Domains → KPI Domains, and the critical path • Inconsistency in v07: the KPI domain template has 6 steps on Day 2 (Register → Configure → Build → Publish → Reconcile → Sign-off), 8 steps on Day 3 (adds Parallel Run and Quality Gate), and on Day 4 it is labelled as Block 6, which elsewhere is the 6 publish steps. Agree one sequence | • Blocks 1–8 as agreed during the day | • 8-block architecture signed off • Critical path and phases agreed
Day 3 | 2026-10-21 | Morning 09:30–13:30 | WS-1: Mexico & Wacam (Nov & Dec) | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | WS-1 POC scope and tracks : Issues to agree: • POC adjustment: the POC builds the full scope of Mexico & Wacam KPIs, with no new KPIs or KPI adjustments • Six tracks: OTC · EPOS · SISO · Master data & manual files · Market Share · Gen BI • Build in the current Databricks / GCP sandbox, migration to Databricks on AWS later | • Day 2 architecture • Full MX & WC KPI inventory | • WS-1 POC scope confirmed
Day 3 | 2026-10-21 | Morning 09:30–13:30 | WS-1: Mexico & Wacam (Nov & Dec) | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | November deliverables (CDRB A, C, D) : Issues to agree: • AS-IS → TO-BE design, manual files, Nielsen recommendations, business rules as config, core domain fit/gap, KPI harmonization • "KPI harmonization finalized" in November while CDRB Section F (KPI accuracy) is primary in December: agree the timing • Core domain fit/gap "including Brazil" sits in WS-1 although Brazil is WS-2: agree the owner | • v07 WS-1 November deliverables | • November deliverables with owners and dates
Day 3 | 2026-10-21 | Morning 09:30–13:30 | WS-1: Mexico & Wacam (Nov & Dec) | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | December deliverables and build sequence : Issues to agree: • What "working prototype foundations by end of December" includes • Inconsistency in v07: the roadmap shows December as CDRB B, E, F, G while the December deliverables cite B and E–L | • v07 WS-1 December deliverables and roadmap | • December deliverables and definition of done agreed
Day 3 | 2026-10-21 | Morning 09:30–13:30 | WS-1: Mexico & Wacam (Nov & Dec) | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | WS-1 resources : Issues to agree: • Named person per track and role: Senior Architect, Partner Architect, DE 1 & 5, Gen BI 1 & 2 • Daily cadence across tracks | • Lingaro staffing proposal | • Named WS-1 resources per track
Day 3 | 2026-10-21 | Afternoon 13:30–17:30 | WS-2: Brazil & Southern Cone (Nov & Dec) | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | WS-2 POC scope and tracks : Issues to agree: • POC adjustment: three steps: (1) reverse engineering of Brazil & SoCo; (2) ~2-week KPI inventory review and sign-off by business and Lingaro; (3) POC on 20–30 selected KPIs on Databricks; no new KPIs or KPI adjustments • Eight tracks: Brazil PVC & VR · OTC · EPOS · SISO · Master data & manual files · Market Share · Snacksync · Gen BI | • Day 2 architecture • POC scope notes | • WS-2 POC scope confirmed
Day 3 | 2026-10-21 | Afternoon 13:30–17:30 | WS-2: Brazil & Southern Cone (Nov & Dec) | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | Step 1 — Reverse engineering (back-office and market visits) : Issues to agree: • AI reading of GCP procedures and Power BI DAX: tools, access, and the KPI inventory fields to fill • Market visits to São Paulo and Buenos Aires: dates, people and local contacts (v07 requires confirmation before 31 Oct) | • GCP and Power BI access for BR & SoCo • KPI inventory template | • Reverse engineering plan and visit schedule
Day 3 | 2026-10-21 | Afternoon 13:30–17:30 | WS-2: Brazil & Southern Cone (Nov & Dec) | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | Step 2 — KPI inventory review and sign-off : Issues to agree: • POC adjustment: a ~2-week window for business and Lingaro: dates, reviewers per market, decision rules for conflicts, escalation • The review confirms what each market calculates today; no new KPIs or adjustments | • Reverse-engineered KPI inventory and conflict register | • Review and sign-off plan with dates
Day 3 | 2026-10-21 | Afternoon 13:30–17:30 | WS-2: Brazil & Southern Cone (Nov & Dec) | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | Step 3 — POC on the selected KPI pool : Issues to agree: • POC adjustment: selection criteria for the 20–30 KPIs and who selects them • Which v07 December deliverables stay at full LA design level (manual files template, core domain fit/gap) and which are limited to the KPI pool | • Signed-off KPI inventory • v07 WS-2 December deliverables | • KPI pool criteria and deliverable scope agreed
Day 4 | 2026-10-22 | Morning 09:30–13:30 | Program Governance | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | Program governance : Issues to agree: • Steering Committee: members (Lingaro PM, Delivery Lead, Account Director; MDLZ PM, PO, MDS Heads of 4 regions, LA DA), weekly meeting, standing agenda and decision rights • Change request process: raised by email → analysis by the team incl. edge cases → business Q&A if needed → estimation → PM sends the estimate to SteerCo for approval • Communication: status reporting, cross-stream sync, escalation path, decision log • Task management in Jira (Lingaro): board per stream, workflow, MDLZ read access • Timeline maintenance: baseline plan approved by SteerCo, weekly forecast, dependency log | • Governance Proposal draft • SOW assumptions | • Program governance agreed • SteerCo members named • change request process agreed
Day 4 | 2026-10-22 | Afternoon 13:30–17:30 | Lingaro Readiness, Resources & Meeting Calendar | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | New ways of working : Issues to agree: • Daily task assignments mapped to the 8 blocks and 3 build phases; PR workflow; escalation and risk management • Lingaro material must use the block definitions agreed on Day 2 (v07 Part 1 describes Blocks 3 and 6 differently from Day 2) | • Lingaro methodology material | • Methodology validated against CDRB
Day 4 | 2026-10-22 | Afternoon 13:30–17:30 | Lingaro Readiness, Resources & Meeting Calendar | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | Use case showcase : Issues to agree: • Evidence required per use case and reference contacts • Differences from OSA 2.0 and their mitigations | • 2–3 comparable Lingaro projects | • Comparable delivery evidence and mitigations documented
Day 4 | 2026-10-22 | Afternoon 13:30–17:30 | Lingaro Readiness, Resources & Meeting Calendar | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | staffing requirements for Phase 1, travel and environments : Issues to agree: | • Lingaro staffing plan • Environment and access status | Staffing plan agreed
Day 4 | 2026-10-22 | Afternoon 13:30–17:30 | Lingaro Readiness, Resources & Meeting Calendar | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | Meeting calendar and commitment round : Issues to agree: • SteerCo weekly · weekly call (4-box review) · daily call with the PO · CDRB twice a week · backlog and change request review weekly · cross-stream sync twice a week · daily stand-ups per stream · sprint planning and review every 2 weeks • Commitment round: first deliverable per person for 2 Nov | • Governance Proposal draft (meeting calendar) | • Meeting calendar agreed with owners and invitees • Commitments recorded
Day 5 | 2026-10-23 | Morning 09:30–13:30 | Phase 1 scope and delivery plan sign off | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | SOW Scope proposition | SOW Scope draft | Scope of Phase 1 confirmed
Day 5 | 2026-10-23 | Morning 09:30–13:30 | Phase 2 scope review and agreement | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | SOW Scope Phase 2 | SOW Scope draft | Scope of Phase 2 confirmed
Day 5 | 2026-10-23 | Afternoon 13:30–17:30 | SOW Review & Final Agreement | Tim K. Ewelina G. Mariusz M. Vadzim N. Marek K. |  | SOW review and final agreement : Issues to agree: • In scope: WS-1 existing Mexico and WACAM KPIs; WS-2 reverse engineering, 2-week KPI inventory sign-off and a limited set of agreed KPIs through to the consumption layer; KPIs per region and in the Global LA view • Out of scope: new KPIs and KPI adjustments, KPIs outside the agreed WS-2 set, and the other out-of-scope items finalised with Marek • Prototype scope vs v07, which states a "full LA solution" • Fixed-price commitment and acceptance criteria for the prototype | • Draft SOW • SOW assumptions • out-of-scope list (finalised with Marek) • Day 1–5 decisions | • In- and out-of-scope items agreed • SOW wording agreed • final agreement